| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | March 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $586,627 | 6% | $6,046,275 | 62% |  |  | $6,046,275 | 62% | $3,759,469 |
| Admin | $1,905,210 | $81,228 | 4% | $969,430 | 51% |  |  | $969,430 | 51% | $935,780 |
| Marketing | $3,055,234 | $182,880 | 6% | $2,038,429 | 67% |  |  | $2,038,429 | 67% | $1,016,805 |
| DI | $4,648,300 | $322,519 | 7% | $3,038,416 | 65% |  |  | $3,038,416 | 65% | $1,609,884 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 2,550 | 4.2% | 53,615 | 87.9% | 0 | 0% | 53,615 | 87.9% | 7,385 |
| CTAC/AGTAC event seminars | 352 | 19 | 5.4% | 250 | 71.0% | 0 | 0% | 250 | 71.0% | 102 |
| Outreach events | 170 | 10 | 5.9% | 111 | 65.3% | 0 | 0% | 111 | 65.3% | 59 |

  - Activities/Accomplishments

    - Administrative

- In March, continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| CTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail Hand Deliver | 31,191 7,700 |
| How to Manage your Business’s Energy Costs (Hesperia) | Flyer | US Mail | 1000 |
| Industrial Maintenance | Email | Email | 3025 |
| LEED NC: Technical Review | Email | Email | 2764 |
| Basic Lighting for Commercial & Industrial Facilities | Email | Email | 3025 |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| Workshops March Classes | Email Invite | Email | 400 |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail | 9000 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during March of 2005 include:

Energy Centers:

Following are accomplishments from March 1st – March 31st 2005.

EE Events completed March = 19

Attendance at those events March = 542

EE Events completed YTD = 47

Attendance at those events YTD = 1125

EE HTR Events completed March = 7

Attendance at those events March = 85

EE HTR Events completed YTD = 17

Attendance at those events YTD = 259

Joint Utility events completed March = 7

Joint Utility events YTD = 21

EE consultations March = 51

Attendees in those consultations March = 51

EE consultations YTD = 115

Attendees in those consultations YTD = 368

EE equipment demonstrations March = 107

Attendees at those demonstrations March = 152

EE equipment demonstrations YTD = 156

Attendees at those demonstrations YTD = 277

New displays developed include:

- AGTAC

Ground Source Heat Pump Display is nearing 40% completion. Once completed the working system will be able to compare the efficiency of three ground heat exchange systems to that of a standard heat pump.

- CTAC

No new displays at CTAC in March.

RTTC:

The summary description of activities which took place at the RTTC in March of 2005 is as follows:

	 EE Information Dissemination

- Tours

  - Performed RTTC tours for staff of XXXXX

	EE Program Support

  - Developed test material for CSBU employees on Basic Refrigeration

- Publications

  - None

- Customer EE Support

  - None

Information Services Program:

There were 2,550 EE contacts conducted in the month of March of 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 53,615.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

The Energy Centers are working with California Community Colleges (Crafton Hills and Victor Valley) to provide a series of Energy Efficiency workshops featuring educational training and materials on the following technologies: Heating, Ventilation, and Air Conditioning (HVAC), and Lighting. The energy centers also work with the other utilities to present joint utility classes.  These classes, also included in the workbook, are developed by one utility and presented by more than one utility or are jointly developed and presented.  7 were presented by the SCE energy centers in March of 2005.

- Changes to Subcontractors or Staffing

None

- Additional Items

None