| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | November 2004 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $466,175 | 5% | $4,175,291 | 43% |  |  | $4,175,291 | 43% | $5,630,453 |
| Admin | $1,905,210 | $63,616 | 3% | $704,823 | 37% |  |  | $704,823 | 37% | $1,200,387 |
| Marketing | $3,055,234 | $148,515 | 5% | $1,491,854 | 49% |  |  | $1,491,854 | 49% | $1,563,380 |
| DI | $4,648,300 | $254,045 | 5% | $1,978,614 | 43% |  |  | $1,978,614 | 43% | $2,669,686 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 30,500 | 1,966 | 6.4% | 46,068 | 151% | 0 | 0% | 46,068 | 151% | 0 |
| CTAC/AGTAC event seminars | 176 | 27 | 15.3% | 196 | 111.4% | 0 | 0% | 196 | 111.4% | 0 |
| Outreach events | 85 | 5 | 5.9% | 92 | 108% | 0 | 0% | 92 | 108% | 0 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element – In November, continued program administration tasks, including management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| Energy Efficiency in Education Series | Flyer | US Mail | 760 |
| Impact of TDV on Whole Building Energy Compliance & Design | Flyer | E-Mail | 3025 |
| www.sce.com/ctac_work_classes | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| Workshops – December classes | Email invite | Email | 400 |
| Festival of Lights | Email | Email | 400 |
| Festival of Lights | Flyer | U.S. Mail | 9848 |
| Festival of Lights | Participation Packet | U.S. Mail | 49 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during November of 2004 include:

Energy Centers:

Following are accomplishments from November 1st – November 30th 2004.

EE Events completed November = 27

Attendance at those events November = 509

EE Events completed YTD = 196

Attendance at those events YTD = 4602

EE HTR Events completed November = 12

Attendance at those events November = 182

EE HTR Events completed YTD = 82

Attendance at those events YTD = 1254

Joint Utility events completed November = 10

Joint Utility events YTD = 79

EE consultations November = 26

Attendees in those consultations November = 24

EE consultations YTD = 608

Attendees in those consultations YTD = 1372

EE equipment demonstrations November = 95

Attendees at those demonstrations November = 86

EE equipment demonstrations YTD = 1797

Attendees at those demonstrations YTD = 1217

New displays developed include:

- AGTAC

Lobby kiosk that monitors Santa Monica Green Building performance on a real-time basis.

- CTAC

No new displays at CTAC in November.

RTTC:

The summary description of activities which took place at the RTTC in November 2004 will be reflected in the December update:

	 EE Information Dissemination

	EE Program Support

- Publications

- Customer EE Support

Information Services Program:

There were 1,996 EE contacts conducted in the month of November 2004; bringing the YTD total EE contacts to 46,068.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Statewide Education, Training and Services 2003 Program Study - This statewide study has been initiated involving utility-owned energy centers throughout the State of California with two objectives:  (1) To evaluate 2003 program success by measuring indicators of program effectiveness and testing the assumptions underlying the program theory; (2) To provide ongoing feedback and corrective guidance regarding program design and implementation while identifying best practices.  The study is expected to be completed by year end.