| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | September 2004 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $335,529 | 3% | $3,308,247 | 34% |  |  | $3,308,247 | 34% | $6,497,497 |
| Admin | $1,905,210 | $74,118 | 4% | $592,858 | 31% |  |  | $592,858 | 31% | $1,312,352 |
| Marketing | $3,055,234 | $143,340 | 5% | $1,186,226 | 39% |  |  | $1,186,226 | 39% | $1,869,008 |
| DI | $4,648,300 | $118,072 | 3% | $1,529,162 | 33% |  |  | $1,529,162 | 33% | $3,119,138 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 30,500 | 2,859 | 9.4% | 42,137 | 138.2% | 0 | 0% | 42,137 | 138.2% | 0 |
| CTAC/AGTAC event seminars | 176 | 23 | 13.1% | 150 | 85.2% | 0 | 0% | 150 | 85.2% | 26 |
| Outreach events | 85 | 12 | 14.1% | 79 | 92.9% | 0 | 0% | 79 | 72.9% | 6 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element – In September, continued program administration tasks, including management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| Basico de HVAC (Basic HVAC presented in Spanish) | Flyer | Hand Deliver | 700 |
| Commercial & Industrial Lighting | Flyer | U.S. Mail | 429 |
| Cleanrooms: Can They Be Energy Efficient? | Flyer | U.S. Mail | 557 |
| CTAC Quarterly Calendar of Events | Calendar | U.S. Mail Hand Deliver | 33,148 7,500 |
| www.sce.com/ctac_work_classes | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| Workshops – October Classes | Email invite | Email | 400 |
| Dairy Workshop | Flyer | Hand Deliver | 50 |
| AGTAC Quarterly Calendar of Events | Calendar | U.S. Mail Hand Deliver | 9170 600 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during September of 2004 include:

Energy Centers:

Following are accomplishments from September 1st – September 30th 2004.

EE Events completed September = 23

Attendance at those events September = 422

EE Events completed YTD = 150

Attendance at those events YTD = 3746

EE HTR Events completed September = 13

Attendance at those events September = 133

EE HTR Events completed YTD = 62

Attendance at those events YTD = 1011

Joint Utility events completed September = 10

Joint Utility events YTD = 61

EE consultations September = 47

Attendees in those consultations September = 76

EE consultations YTD = 540

Attendees in those consultations YTD = 1230

EE equipment demonstrations September = 162

Attendees at those demonstrations September = 71

EE equipment demonstrations YTD = 1348

Attendees at those demonstrations YTD = 1002

New displays developed include:

- AGTAC

A viewing pad, railing, and steps have been added to the existing landing 			on the low pressure exhibit. These features will allow easy access to the 			middle of the two canals for viewing of control structures and 				instrumentation. Additionally, AgTAC received an ultrasonic flow sensor 			for use in open channel flow metering, and a solar gate structure that will 			automatically adjust to control the upstream water level or downstream 			flow rate.

- CTAC

No new displays at CTAC in September.

RTTC:

The following provides a summary description of activities which took place at the RTTC in September 2004:

EE Information Dissemination

- Performed RTTC tour for Cal Poly HVAC Technicians.

- Performed RTTC tour for Sriswetha Modem, Technical Sales Engineer for Fluent Inc.

Publications

- Food Marketing Institute Energy Conference

  - Presented the results of the RTTC’s Codes & Standards project at Food Marketing Institute’s energy conference.

- ASHRAE Handbook Chapters 47 & 48 Revision

  - In the process of drafting a section on refrigerated vending machines which shares some of the knowledge we have gained through our ongoing Codes and Standards projects.

Customer EE Support

  - Best Western Hotel, Long Beach - developed a solution package and submitted to the customer.

  - Frank Smith’s Residence - Received a request from Frank Smith, a SCE customer regarding air conditioning problems at his residence.  The RTTC developed a system diagnostic plan to ascertain the possible problem causes.

Energy Efficiency Tool Development:

The RTTC developed and rolled out an energy analyses tool (in Excel) for the Field Engineering group.  The tool will assist field engineers in estimating the impacts of EEMs in walk-in coolers and freezers with minimal input.

Information Services Program:

There were 2,859 EE contacts conducted in the month of September 2004, bringing the YTD total of EE contacts to 42,137.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Statewide Education, Training and Services 2003 Program Study - This statewide study has been initiated involving utility-owned energy centers throughout the State of California with two objectives:  (1) To evaluate 2003 program success by measuring indicators of program effectiveness and testing the assumptions underlying the program theory; (2) To provide ongoing feedback and corrective guidance regarding program design and implementation while identifying best practices.  The study is expected to be completed by year end.