| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | June 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $459,426 | 5% | $7,236,545 | 74% |  |  | $7,236,545 | 74% | $2,569,199 |
| Admin | $1,905,210 | $57,446 | 3% | $1,146,207 | 60% |  |  | $1,146,207 | 60% | $759,003 |
| Marketing | $3,055,234 | $136,632 | 4% | $2,427,872 | 79% |  |  | $2,427,872 | 79% | $627,362 |
| DI | $4,648,300 | $265,347 | 6% | $3,662,466 | 79% |  |  | $3,662,466 | 79% | $985,834 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jun-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 0 | 0% | 72,116 | 118.2% | 0 | 0% | 72,116 | 118.2% | 0 |
| CTAC/AGTAC event seminars | 352 | 20 | 3.9% | 306 | 81.3% | 0 | 0% | 306 | 81.3% | 46 |
| Outreach events | 170 | 8 | 4.7% | 163 | 95.9% | 0 | 0% | 163 | 95.8% | 7 |

  - Activities/Accomplishments

    - Administrative

- In June, continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| How To Manage Your Business Energy Costs | Flyer | US Mail | 937 |
| Basic Heating, Ventilation & Air Conditioning (HVAC) | Flyer | US Mail | 627 |
| CTAC July Classes | Email | Email | 4394 |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail | 50 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during June of 2005 include:

Energy Centers:

Following are accomplishments from June 1st – June 30th 2005.

EE Events completed June = 20

Attendance at those events June = 389

EE Events completed YTD = 103

Attendance at those events YTD = 2285

EE HTR Events completed June = 11

Attendance at those events June = 169

EE HTR Events completed YTD = 41

Attendance at those events YTD = 612

Joint Utility events completed June = 5

Joint Utility events YTD = 41

EE consultations June = 33

Attendees in those consultations June = 98

EE consultations YTD = 237

Attendees in those consultations YTD = 756

EE equipment demonstrations June = 103

Attendees at those demonstrations June = 84

EE equipment demonstrations YTD = 514

Attendees at those demonstrations YTD = 506

New displays developed include:

- AGTAC

XXXXX - XXXXX held a training session to finalize the installation 	of the Digital Microwatt lighting controls in the ICF building. The 	computer based system includes features such as load shedding, 	maintenance tracking, daylighting control and KW/KWH monitoring. The 	system also interfaces with the Solatube skylights to turn natural lighting 	off for audio video scenes and demonstration. To maximize the efficiency 	of the daylighting controls Lutron's Hi-Lume 1% dimming ballasts were 	used along with T5 High Output lamps.

- CTAC

CTAC has installed a 5 Ton Commercial Package Air Conditioner Exhibit 	for use in our seminars and training classes.  The unit features:

    - High Efficiency (SEER rating of 14.2 & EER rating of 12.0)

    - Environmental friendly R410A refrigerant

    - Economizer section for additional energy savings

High performance commercial grade belt drive blower

RTTC:

The summary description of activities which took place at the RTTC in June of 2005 is as follows:

EE Information Dissemination

- Tours

- Performed RTTC and SCLTC tours for XXXXX

- Performed RTTC and SCLTC tours for XXXXX.

- Performed RTTC and SCLTC tours for XXXXX

- Publications

  - Presented results from RTTC’s energy efficiency research of vending machines at American Society of Heating, Refrigerating and Air conditioning engineers conference in Denver.

  - Published an article on the RTTC’s energy efficiency research of supermarket display cases in appliance design magazine.

- Customer Care

- Established communication with Long Beach School District regarding the energy efficiency opportunities for vending machines on their 90 campuses.  They have over 1500 units on their campuses and are anxious to reduce their demand and energy usage.  A meeting with their energy management team is planned for July 2005.

Information Services Program:

There were no EE contacts reported in the month of June of 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 72,116.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None