| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Codes and Standards Advocacy Program – PGC |
| Program Number: | 1266-04 |
| Month: | December 2004 |

1.	Program Status

Program Description

The Statewide Codes and Standards (C&S) program is an information-only program that advocates upgrades and enhancements in energy efficiency standards and codes. Program activities are conducted over long-term code upgrade cycles; for example, support for building code cycles may require four years of continuous support.  Codes and Standards Enhancement (CASE) studies for energy efficiency improvements are performed for promising design practices and technologies and are presented to standards and code-setting bodies.  Since many stakeholders who typically oppose improvements to building and appliance standards participate in public workshops and hearings, the Statewide Codes and Standards Advocacy program provides expert testimony to promote standards that approach best practices in energy efficiency.  Additionally, the program supports implementation of energy efficiency standards through strategic initiatives or training.  The program targets all market segments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $2,485,099 | $133,757 | 5% | $563,411 | 23% | $796,300 | 32% | $1,359,711 | 55% | $1,921,688 |
| Admin | $802,600 | $32,912 | 4% | $268,135 | 33% |  |  | $268,135 | 33% | $534,465 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $1,597,400 | $100,845 | 6% | $295,277 | 18% | $796,300 | 50% | $1,091,577 | 68% | $1,302,123 |
| EM&V | $85,099 |  |  |  |  |  |  |  |  | $85,099 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Initiate or continue case studies | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 6 |
| Evaluation of potential studies |  |  | 100% |  | 100% |  | 0% |  | 100% | 0% |
| Commitment of new studies | 6 | 3 | 50% | 10 | 167% | 0 | 0% | 10 | 167% | 0 |
| Conduct training courses | 4 | 1 | 25% | 4 | 100% | 0 | 0% | 4 | 100% | 0 |

  - Activities/Accomplishments

    - Administrative -

- All active studies are being pursued and are on time and within budget.

- Work has concluded regarding the final commitments for 2004. Three additional CEC collaborated projects were initiated and are described below.

- Our training goal was met as we conducted the last training session involving Title-24 compliance and Time Dependant Valuation.

    - Marketing -

None

    - Direct Implementation –

- SCE exceeded its target goal of initiating 6 new CASE studies in 2004. Eleven new studies we initiated and are described below.

  - Closed Front Vending Machine (Phase 2)

    - This test is designed to evaluate possible energy efficiency design opportunities for closed front vending machines.

  - Glass Front Vending Machines

    - This evaluation will study the performance of glass front beverage dispensers and identify possible energy efficiency improvement opportunities.

  - Stagged Volume AC

    - Investigation of a “two staged” air conditioning system designed for high peak cooling environments such a churches and assembly rooms. It also incorporates a variable speed fan for air circulation.

  - Dairy Industry Guide

    - Development of a guide that will provide “best practices” for the dairy industry so that they can follow the most energy efficient approaches.

  - Dairy Guide 2

    - Continued focus on dairy industry end use “best practices” with particular attention to manure handling equipment.

  - Side-lighting Study

    - Conducted jointly with PG&E and the New Building Institute, this study will evaluate the feasibility of controlling lighting levels within business using side-lighting and photometric controls. At present this is not possible.

  - Streaming Video

    - Development of a streaming video “help menu” to be used in conjunction with e-quest energy analysis tool.

  - Benchmarking Studies

    - Review the current energy analysis tools that are available for Title-24 compliance and compare their strengths and weaknesses.

  - Evaluation of TDV Implications

    - Scoping study to investigate the key issues associated with the development of a process to introduce new measures into the T-24 standards that takes into account TDV

  - Alternates to EER/SEER

    - A study was completed that quantified the problems with using EER and SEER as a predictor of actual building peak loads and energy consumption. Possible solutions to this issue will be explored as part of this study.

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None