| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Codes and Standards Advocacy Program – PGC |
| Program Number: | 1266-04 |
| Month: | April 2004 |

- Program Status

Program Description

The Statewide Codes and Standards (C&S) program is an information-only program that advocates upgrades and enhancements in energy efficiency standards and codes. Program activities are conducted over long-term code upgrade cycles; for example, support for building code cycles may require four years of continuous support.  Codes and Standards Enhancement (CASE) studies for energy efficiency improvements are performed for promising design practices and technologies and are presented to standards and code-setting bodies.  Since many stakeholders who typically oppose improvements to building and appliance standards participate in public workshops and hearings, the Statewide Codes and Standards Advocacy program provides expert testimony to promote standards that approach best practices in energy efficiency.  Additionally, the program supports implementation of energy efficiency standards through strategic initiatives or training.  The program targets all market segments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $2,485,099 | $31,423 | 1% | $89,497 | 4% |  |  | $89,497 | 4% | $2,395,602 |
| Admin | $802,600 | $18,644 | 2% | $62,537 | 8% |  |  | $62,537 | 8% | $740,063 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $1,597,400 | $12,779 | 1% | $26,961 | 2% |  |  | $26,961 | 2% | $1,570,439 |
| EM&V | $85,099 |  |  |  |  |  |  |  |  | $85,099 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Apr-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Initiate or continue case studies | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 6 |
| Evaluation of potential studies |  |  | 90% |  | 90% |  | 0% |  | 90% | 10% |
| Commitment of new studies | 6 | 6 | 100% | 6 | 100% | 0 | 0% | 6 | 100% | 0 |
| Conduct training courses | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |

  - Activities/Accomplishments

    - Administrative -

The program continues to evaluate new 2004 codes and standards projects for possible inclusion in the program.  Numerous discussions have occurred within the Design and Engineering Service staff regarding candidate projects.

    - Marketing -

None

    - Direct Implementation –

Commitments have been made on 6 new studies/ training courses. They are:

  - The testing of vending machines (phase 2). This test is designed to evaluate possible energy efficiency design opportunities within the machine.

  - Vending machine testing- glass front. This evaluation will study the performance of a glass front beverage dispenser and indicate possible ways to improve its energy efficiency.

  - The development of a dairy farm workshop at AGTAC. Information regarding the energy efficiency of dairy related process will be shared with the industry.

  - Dairy Industry Guide development. A guide will be developed that will provide “best practices” guidelines for the dairy industry so that they can follow the most energy efficient approaches.

  - Side-lighting photo-controls study. Conducted jointly with PG&E and the New Building Institute, this study will evaluate the feasibility of controlling lighting levels within business using side-lighting and photometric controls. At present this is not possible.

  - Development of a compressed air dryer design guideline (phase 2). This is a continuation of work that was initiated in 2003 regarding the evaluation of compressed air systems for industrial usage. The guideline is designed to minimize energy usage through compressor system and dryer design optimization.

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None