| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Small Nonresidential Hard To Reach Program - PGC |
| Program Number: | 1313-04 |
| Month: | February 2005 |

- Program Status

Program Description

The Small Nonresidential Hard To Reach Program, also known as the Small Business Equipment Retrofit Program is designed to produce cost-effective, long term annual demand and energy savings by providing no-cost energy-efficient equipment retrofits to hard-to-reach small business customers in Southern California Edison’s (SCE) service territory.  This program will also provide training and jobs for individuals in economically disadvantaged areas. The program will target underserved communities within SCE territory by coordinating with selected community based organizations (CBOs) and faith based organizations (FBOs) to package a customized program delivery plan that fits the specific needs of their communities thereby reducing market barriers to adoption of energy efficiency alternatives in these communities.  These organizations can leverage SCE’s portfolio of energy efficiency programs that effectively deliver long term energy and peak demand savings.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $6,801,440 | $20,685 | 0% | $260,276 | 4% |  |  | $260,276 | 4% | $6,541,164 |
| Admin | $583,003 | $14,431 | 2% | $233,747 | 40% |  |  | $233,747 | 40% | $349,256 |
| Marketing | $110,000 |  |  |  |  |  |  |  |  | $110,000 |
| DI | $6,028,434 | $717 | 0% | $18,493 | 0% |  |  | $18,493 | 0% | $6,009,941 |
| EM&V | $80,002 | $5,537 | 7% | $8,035 | 10% |  |  | $8,035 | 10% | $71,968 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 3,790 |  |  |  |  |  |  |  |  | 3,790 |
| Annual kWh | 19,534,660 |  |  |  |  |  |  |  |  | 19,534,660 |
| Lifecyc kWh | 308,006,610 |  |  |  |  |  |  |  |  | 308,006,610 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- Purchase order issued by SCE’s procurement department for both the direct install component and the CBO/FBO component.

- Prime contractor shall sign contracts with selected CBOs/FBO by March 16, 2005.

- Jobs skills training to commence on March 21st and March 22nd.

- CBOs/FBO to commence marketing on March 23rd.

    - Marketing -

Collateral marketing materials used by the prime contractor and the CBOs have been reviewed and approved by SCE.  Customer program introduction has been letter approved by SCE to be mailed prior to outreach.

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

No activities to date.

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

EM&V study kickoff occurred July 21, 2004.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

A new project manager has been assigned to the program.

- Additional Items

None