| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Pump Test and Hydraulic Services Program – PGC |
| Program Number: | 1317-04 |
| Month: | October 2005 |

- Program Status

Program Description

Southern California Edison’s (SCE) Pump Test and Hydraulic Services (PTHS) Local Program proposal represents an energy information and management services program.  The program will be delivered to agricultural and water customers throughout SCE’s service territory.  The PTHS program is designed to increase the adoption rate and implementation of energy efficiency recommendations provided to customers with pumping accounts.   It will accomplish these goals by testing customers’ pumping systems, and delivering information to a customer that contains a site specific energy efficiency report with cost analysis that the customer can easily understand and act upon.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,200,000 | $153,765 | 5% | $2,803,883 | 88% |  |  | $2,803,883 | 88% | $396,117 |
| Admin | $1,316,600 | $11,135 | 1% | $668,784 | 51% |  |  | $668,784 | 51% | $647,816 |
| Marketing | $18,400 |  |  |  |  |  |  |  |  | $18,400 |
| DI | $1,745,000 | $140,896 | 8% | $2,046,120 | 117% |  |  | $2,046,120 | 117% | -$301,120 |
| EM&V | $120,000 | $1,734 | 1% | $88,978 | 74% |  |  | $88,978 | 74% | $31,022 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings or demand reductions.

    - Performance Goals

| Performance Goals | Goals | Oct-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Pump Tests | 7200 | 354 | 4.9% | 8,442 | 117% | 0 | 0% | 8,442 | 117% | 0 |

  - Activities/Accomplishments

    - Administrative -

None

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

| Time Period | # of Pump Tests | Cost Per Site |
| --- | --- | --- |
| September 2005 | 354 | $434 |
| Year to Date (’04 &’05) | 8,442 | $332 |

- PTHS continues to work to attract new customer participants, as defined in the PTHS program implementation plan.  In October 2005, of the pumping systems tested by PTHS, 37.2% were systems of new customer participants.

- As of October 2005, 32.2% of the pumping systems tested were located in hard-to-reach (HTR) designations.  Recognition should continue to be given to the fact most customers receiving the services and benefits from the PTHS program are traditionally considered HTR customers.

.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

Research plan has received approval.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

New Customer Participants are customers that have not benefited from an SCE pump test in the last 3 years.

In addition to the generally recognized definition of hard-to-reach customers as they apply to PTHS’ customers, SCE also tracks the participation of hard-to-reach customers as defined by geographical location, i.e. rural zip code.