| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Government Initiatives – PGC |
| Program Number: | 1318-04 |
| Month: | May 2005 |

- Program Status

Program Description

Through partnering with Local Governments and cities (collectively referred to as Jurisdictions), Southern California Edison’s (SCE) Local Government Initiative (LGI) offers energy efficiency information and education, hardware upgrades, and subsidized energy efficiency improvements to SCE’s small to medium-business owners, lower-to-moderate income residential customers, single and multifamily existing residential consumers, and residential and small commercial builders.

The core of this program approach is to work with the jurisdictions as a delivery channel for SCE's broad portfolio of energy efficiency information, services and incentives, thereby deepening the reach of our program offerings.  However, the added benefit of our partnership approach is that it allows us, working side-by-side with the cities, to customize offerings (either through bundled offerings or modifying individual programs) to either fill a specific need within a Jurisdiction, and/or better reach an identified Hard-to-Reach (HTR) component within a city.  Collaboration with Jurisdictions is an effective adjunct to the utility-to-customer approach used in many of SCE’s programs, leveraging the influence of the Jurisdictions who share similar energy efficiency goals.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | $22,741 | 2% | $559,432 | 56% |  |  | $559,432 | 56% | $440,568 |
| Admin | $277,000 | $2,629 | 1% | $60,592 | 22% |  |  | $60,592 | 22% | $216,408 |
| Marketing | $90,000 |  |  | $14,022 | 16% |  |  | $14,022 | 16% | $75,978 |
| DI | $561,000 | $20,112 | 4% | $466,448 | 83% |  |  | $466,448 | 83% | $94,552 |
| EM&V | $72,000 |  |  | $18,371 | 26% |  |  | $18,371 | 26% | $53,629 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Completed 2004/05 Enrollment Forms | 32 | 0 | 0% | 28 | 87.5% | 0 | 0% | 28 | 87.5% | 4 |
| Expand to New Jurisdiction Identified as HTR | 10 | 0 | 0% | 4 | 40% | 0 | 0% | 4 | 40% | 6 |
| Conduct Building Department Training or Imformation Updates on 2005 Title 24 Code Revisions | 12 | 0 | 0% | 12 | 100% | 0 | 0% | 12 | 100% | 0 |
| Coordinate Activities Promoting Residential and Multifamily Retrofit Programs | 10 | 0 | 0% | 6 | 60% | 0 | 0% | 6 | 60% | 4 |
| Coordinate Activities Promoting Nonresidential Programs | 10 | 0 | 0% | 6 | 60% | 0 | 0% | 6 | 60% | 4 |

  - Activities/Accomplishments

    - Administrative –

- SCE continues to work closely with XXXXX and the XXXXX to strategize the best way to market the LGI program to local governments.  To assist in preparing builders and those in the construction industry for the upcoming October 2005 Title-24 changes, SCE continues to participate in Building Energy Code Training (BECT) sessions that began in February and will continue throughout the year.

- As of May, twelve Building Energy Code Training (BECT) sessions have been conducted in the following cities:

  - Rancho Cucamonga, Temecula, Santa Clarita, Norco, Oxnard, Agoura Hills, Glendale, Burbank, Newport Beach, Fullerton, Calaveras, and Kern County

- For 2005, ConSol attended five outreach events at city council meetings.  The city council meetings took place in Commerce, Mission Viejo, Palm Springs and Corona.  In April, ConSol attended the Palm Springs City Council meeting.

    - Marketing –

- 2005 program marketing materials are printed and in circulation. In addition, RNC’s website has been updated and now displays 2005 program information.

    - Direct Implementation –

      - Audits, Site Surveys and Partnerships -

- SCE will continue to work with the Building Industry Institute on the outreach and implementation of this program, particularly in those areas with significant building activity.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

RNC is working closely with M&E in developing and enhancing LGI to make a more viable program.  The primary focus is on improving:

- Availability of program materials to the public through local jurisdictions

- Communications and relationships with city, county and state building officials

- Extending outreach and marketing materials to include the city/county Community Services Departments

- Internal relationships within SCE’s public relations departments (i.e., Public Affairs, Regional Affairs, Consumer Affairs, etc.)

- Interface with builders, architects and building industry vendors

- Attendance and support with Title 24 training sessions

- Program Challenges

SCE continues to work closely with internal and external organizations to promote and enhance the value of the LGI program.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

On-going

- Changes to Subcontractors or Staffing

None

- Additional Items

None