| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Government Initiatives – PGC |
| Program Number: | 1318-04 |
| Month: | October 2005 |

- Program Status

Program Description

Through partnering with Local Governments and cities (collectively referred to as Jurisdictions), Southern California Edison’s (SCE) Local Government Initiative (LGI) offers energy efficiency information and education, hardware upgrades, and subsidized energy efficiency improvements to SCE’s small to medium-business owners, lower-to-moderate income residential customers, single and multifamily existing residential consumers, and residential and small commercial builders.

The core of this program approach is to work with the jurisdictions as a delivery channel for SCE's broad portfolio of energy efficiency information, services and incentives, thereby deepening the reach of our program offerings.  However, the added benefit of our partnership approach is that it allows us, working side-by-side with the cities, to customize offerings (either through bundled offerings or modifying individual programs) to either fill a specific need within a Jurisdiction, and/or better reach an identified Hard-to-Reach (HTR) component within a city.  Collaboration with Jurisdictions is an effective adjunct to the utility-to-customer approach used in many of SCE’s programs, leveraging the influence of the Jurisdictions who share similar energy efficiency goals.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | $25,448 | 3% | $660,293 | 66% |  |  | $660,293 | 66% | $339,707 |
| Admin | $277,000 | $4,172 | 2% | $84,413 | 30% |  |  | $84,413 | 30% | $192,587 |
| Marketing | $90,000 |  |  | $14,022 | 16% |  |  | $14,022 | 16% | $75,978 |
| DI | $561,000 | $20,751 | 4% | $540,355 | 96% |  |  | $540,355 | 96% | $20,645 |
| EM&V | $72,000 | $525 | 1% | $21,503 | 30% |  |  | $21,503 | 30% | $50,497 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Oct-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Completed 2004/05 Enrollment Forms | 32 | 3 | 9.4% | 32 | 100% | 0 | 0% | 32 | 100% | 0 |
| Expand to New Jurisdiction Identified as HTR | 10 | 0 | 0% | 9 | 90% | 0 | 0% | 9 | 90% | 1 |
| Conduct Building Department Training or Information Updates on 2005 Title 24 Code Revisions | 12 | 1 | 8.3% | 15 | 125% | 0 | 0% | 15 | 125% | 0 |
| Coordinate Activities Promoting Residential and Multifamily Retrofit Programs | 10 | 2 | 20% | 11 | 110% | 0 | 0% | 11 | 110% | 0 |
| Coordinate Activities Promoting Nonresidential Programs | 10 | 1 | 10% | 11 | 110% | 0 | 0% | 11 | 110% | 0 |

  - Activities/Accomplishments

    - Administrative –

- SCE continues to work closely with XXXXX and the XXXXX to strategize the best way to market the LGI program to local governments.  To assist in preparing builders and those in the construction industry for the upcoming October 2005 Title-24 changes, SCE continues to participate in Building Energy Code Training (BECT) sessions that began in February and will continue throughout the year.

- Goal:  Re-register 32 Existing Jurisdictions

  - The 2005 re-register goal of 32 jurisdictions has been met.  To date, 33 jurisdictions have been re-registered bringing the percent of goal to 103%.  The final three re-registrations completed in October were:

    - Huntington Beach

    - Kern County

    - Banning

  - Outreach events completed by LGI management for October include:

    - Palm Springs – a follow-up meeting to the September presentation was held with City staff for suggestions on how to launch a Green Building program.

    - Santa Clarita –  LGI management is working closely with the City of Santa Clarita to discuss energy efficiency.  An event upcoming in Palmdale will provide the arena for discussion and suggestion.

- Goal: Support Existing Jurisdictions; Promote LGI Programs – 10 Residential and 10 Non-Residential Community Outreach Activities

  - Currently 18 community outreach events have been completed with 2 remaining to meet goal for 2005.

  - In October, the LGI team paid visits to officials in the following cities:

    - Downey – Green Building 101 - The LGI team conducted a presentation to an audience of approximately 200 attendees from the building industry, city building officials, utility companies, green building suppliers, and California building officials at SoCalGas’ energy center in Downey.

    - Alhambra - Los Angeles ICC Chapter Meeting – the LGI team conducted a presentation to local building officials.

    - Monterey Park –  Harmony Community Fair – The LGI team utilized the MEU to represent Edison at this cultural event that attracted approximately 1,000 community residents.

Three future outreach events are planned in November:

- Rialto – presentation at a city council meeting

- Temecula – Public Safety Expo

- Westminster – presentation at a city council meeting

- Goal:  Obtain Participation/Registration from 10 new jurisdictions in Hard-To-Reach (HTR) markets

  - Even though the HTR goal is met, outreach efforts will continue to those HTR jurisdictions that are not currently signed on with LGI.

  - Outreach to new jurisdictions include the following cities/areas:

    - Baldwin Park

    - Whittier

- Goal:  Train 12 Building Department Staff by coordinating with BII’s BECT training program

  - To date 12 BECT training sessions have occurred within SCE’s service territory and consequently the goal is met; however, BECT training sessions are still conducted on an as needed/requested basis.  As of August, 28 training sessions have taken place.

  - For October, 1 BECT training session was conducted in the following city:

    - San Gabriel

    - Marketing –

- 2005 program marketing materials are printed and in circulation.

    - Direct Implementation –

      - Audits, Site Surveys and Partnerships -

- None.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

LGI is working closely with M&E in developing and enhancing LGI to make a more viable program.  The primary focus is on improving:

- Availability of program materials to the public through local jurisdictions

- Communications and relationships with city, county and state building officials

- Extending outreach and marketing materials to include the city/county Community Services Departments

- Internal relationships within SCE’s public relations departments (i.e., Public Affairs, Regional Affairs, Consumer Affairs, etc.)

- Interface with builders, architects and building industry vendors

- Attendance and support with Title 24 training sessions

- Program Challenges

SCE continues to work closely with internal and external organizations to promote and enhance the value of the LGI program.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

On-going

- Changes to Subcontractors or Staffing

None

- Additional Items

None