| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | County of Los Angeles/SCE/SCG Partnership - PGC |
| Program Number: | 1321-04 |
| Month: | September 2004 |

- Program Status

Program Description

The County of Los Angeles, Southern California Edison Company, and Southern California Gas Partnership will continue to implement energy efficiency projects in existing County facilities and leverage the County’s existing energy management infrastructure. The County maintains an “in-house” energy management organization including administrators, project managers, energy analysts, technical support, and facility databases.  The County has implemented its Enterprise Energy Management Information System – a “real-time,” internet-based energy management program that archives and displays detailed facility consumption and operations information.  The County’s energy management organization maintains relationships with all 38 County departments, other County affiliated agencies (including the Office of Education, Public Housing, Metropolitan Transit Authority, Office of Small Business), and other local governments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,000,000 | $9,974 | 0% | $70,611 | 2% |  |  | $70,611 | 2% | $2,929,389 |
| Admin | $298,401 | $9,974 | 3% | $70,035 | 23% |  |  | $70,035 | 23% | $228,366 |
| Marketing | $2 |  |  |  |  |  |  |  |  | $2 |
| DI | $2,580,333 |  |  | $551 | 0% |  |  | $551 | 0% | $2,579,781 |
| EM&V | $121,264 |  |  | $25 | 0% |  |  | $25 | 0% | $121,239 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,902 |  |  |  |  |  |  |  |  | 1,902 |
| Annual kWh | 4,723,641 |  |  |  |  |  |  |  |  | 4,723,641 |
| Lifecyc kWh | 73,304,294 |  |  |  |  |  |  |  |  | 73,304,294 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Retro-Commissioning Element –

  - EMC Engineers, Inc. was selected in a competitive bid process.

  - Scope of work includes RCx of 10 County of LA Building at approximately 1.5 Million square feet.

  - Fix-Price cost: $791,868.00

  - Estimated Energy Savings (1.5 million square feet): 945 kW, 1.83 MkWh

  - A purchase order is being generated and will be executed by October 22, 2004.

  - RCx projects expected to commence by early November.

- Retrofit Element

  - Retrofit element has 3 different components (lighting, building-wide lighting controls, chillers)

  - The program team is currently reviewing 4 proposals submitted in response to the RFP. Proposal review meeting is scheduled for Tuesday, October 19, 2004.  The goal of the meeting is to discuss the scoring of the proposals and select the proposal with the highest score.  The vendor for lighting retrofit element will be selected by end of October and a purchase order will be executed by 2nd week of November.

  - The proposals will be scored according to the following criteria.

      - Skills and Experience

      - Technical Approach

      - Timelessness of proposed Schedule

      - Conformity of the proposal to the RFP

      - Project Costs

  - Scope of work for Lighting Retrofit element will include 62 fire stations and libraries with a total square footage of 468,963 square feet. The team will select a vendor to implement the lighting retrofit element.

  - After further assessment of the facility targeted for building-wide lighting controls, the partners felt that it is more cost effective to install occupancy sensors in specified zones in some of those buildings.  As such, the partners will include a change order to the lighting retrofit for the vendor to install the occupancy sensors.

  - Scope of work for Building-wide lighting controls has been modified due to the low response of the RFP for this element.  As noted above, LACo will design lighting control configuration for one building and two other buildings will receive occupancy sensors to control specific zones in the buildings.

  - Scope of work for Chiller retrofit will include the replacement of 2 chillers (230 tons) in two County of Los Angeles buildings. Partners are currently requesting a rebid from the two vendors that had submitted proposals for the chiller replacement.  The bid addendum requests the vendor to rebid for replacement of the smaller (65 ton) chiller which currently has R22 refrigerant.  The new bid is for a chiller with R134A refrigerant.

- Public Agency Feasibility Study and Technology Transfer Element

  - Partners have commenced the activities for the feasibility study.  A cover letter and a set of questionnaires are being developed to solicit information from potential public agency participants.

  - A workshop is also being planned to present the results of the study to prominent public agency officials as well as CPUC commissioners and representatives from state agencies.  The proposed date for this workshop is Wednesday, February 16, 2005.

- Public Housing, Multi Family Metering Element

  - All the team members are in place for this program element.

  - 350 Meters will be installed in 5 different districts within the County of LA.

  - All the partners (SCE/SCG/LACo) including USCL and LACDC are on board with the project scope. The scope includes:

    - Meter acceptance testing, purchase and installation of meters,

    - Installation of optical sensors and display units.

    - Los Angeles CDC’s involvement in identifying and providing access to public housing facilities for meter, sensor and display installation. CDC will also provide notifications and assist in training of tenants on how to fully utilize the LCD display to encourage positive behavioral changes in conservation and to use appliances more efficiently.

    - SCE Emerging Technologies Group will establish an evaluation protocol to study the impacts of this meter and display technology.  Project will evaluated a test case and a control case for each of the five facilities. Each facility will have an equal number of tenants with meters and without meters. Energy usage analysis will be conducted for all participating tenants to establish the pre and post impacts of the project. ET will generate a final report for the project.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

Based on input from the evaluation project kick-off meeting and from other discussions with the SCE project manager, XXXXX modified their proposed scope of work and submitted a Revised Work Plan to the Energy Division and their Master Evaluation Contract Team (MECT) for approval on August 9, 2004, the deadline set by the ALJ in her ruling.  The MECT comments on the plan were sent back to the evaluation team on August 20, 2004 and we have had several phone conversations with MECT representatives and among the evaluation project staff.  The MECT comments had to do with parts of the plan that do not completely correspond to specific M&E requirements in the Energy Efficiency Policy Manual.  To meet the requirements, we need only to add some clarifying text.  A draft revised plan was prepared and is being reviewed by the evaluation team.  We expect to submit it for MECT review shortly.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

None

- Additional Items

None