| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | County of Los Angeles/SCE/SCG Partnership - PGC |
| Program Number: | 1321-04 |
| Month: | May 2004 |

- Program Status

Program Description

The County of Los Angeles, Southern California Edison Company, and Southern California Gas Partnership will continue to implement energy efficiency projects in existing County facilities and leverage the County’s existing energy management infrastructure. The County maintains an “in-house” energy management organization including administrators, project managers, energy analysts, technical support, and facility databases.  The County has implemented its Enterprise Energy Management Information System – a “real-time,” internet-based energy management program that archives and displays detailed facility consumption and operations information.  The County’s energy management organization maintains relationships with all 38 County departments, other County affiliated agencies (including the Office of Education, Public Housing, Metropolitan Transit Authority, Office of Small Business), and other local governments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,000,000 | $3,304 | 0% | $45,268 | 2% |  |  | $45,268 | 2% | $2,954,731 |
| Admin | $298,401 | $3,304 | 1% | $45,268 | 15% |  |  | $45,268 | 15% | $253,133 |
| Marketing | $2 |  |  |  |  |  |  |  |  | $2 |
| DI | $2,580,333 |  |  |  |  |  |  |  |  | $2,580,333 |
| EM&V | $121,264 |  |  |  |  |  |  |  |  | $121,264 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,902 |  |  |  |  |  |  |  |  | 1,902 |
| Annual kWh | 4,723,641 |  |  |  |  |  |  |  |  | 4,723,641 |
| Lifecyc kWh | 73,304,294 |  |  |  |  |  |  |  |  | 73,304,294 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- The partners met on May 27, 2004 to work on implementation issues, including the contract between the partners, requests for proposals for the retrofit and continuous/retro-commissioning (“RCx”) programs, EM&V and additional funding for the public housing meter-reading program.  Program critical paths and critical path dates were also discussed.

- A Partnership Master agreement has been drafted and is now under final review by the partners. The attorneys from the County of Los Angeles, SCE and SCG are working diligently to identify and resolve most of the remaining issues.  The Partnership Master agreement is expected to be completed and signed in June between all partnership parties.

- In process of drafting two RFP’s for Retrofit and Retro-Commissioning projects.  Partners are reviewing  the first draft of RFP package for retrofit program and developing RFP package for RCx program. Completion and release of both RFP packages to potential bidding contractors expected in July 2004.

- In process of contacting county facilities to gather facility data for the request for proposal packages.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

RFP has been released to potential contractor bidders. Contractor proposals are due by end of June 2004 and potential contract award expected in July 2004.

- Program Challenges

The program challenges and opportunities for RCx program require an innovative creation of a custom RFP package which may provide standards for future programs.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

None

- Additional Items

None