| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | CU/CSU Partnership Program – PGC |
| Program Number: | 1324-04 |
| Month: | January 2005 |

- Program Status

Program Description

The University of California/California State University (UC/CSU) and Investor-Owned Utility (IOU) Energy Efficiency Partnership is a unique, statewide energy efficiency program that accomplishes immediate, long-term energy efficiency and demand savings, and establishes a permanent framework for a sustainable  comprehensive energy management program at the thirty three (33) UC and CSU campuses served by California’s four large IOUs.  This program capitalizes on the vast resources and expertise of the UC/CSU and the California IOU’s to ensure a successful and cost effective program that meets all objectives of the California Public Utilities Commission (CPUC or Commission) as articulated in Decision 03-08-067. In lays the groundwork for not only a continued UC/CSU comprehensive energy efficiency program but also establishes a model for statewide partnership programs and will allow expansion of this program to California’s community colleges in the next funding cycle. The UC/CSU/IOU partnership program is comprised of three elements, which will operate on a statewide, integrated basis, providing immediate energy savings and setting the foundation for a long-term program focused on sustainability and best practices: Energy Efficiency Retrofits, Facility Retro-and Continuous Commissioning, and Energy Efficiency Education and Best Practices Development and Training.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,500,000 | $259,480 | 6% | $2,607,497 | 58% | $3,676,255 | 82% | $6,283,752 | 140% | $1,892,503 |
| Admin | $618,540 | $19,029 | 3% | $655,303 | 106% |  |  | $655,303 | 106% | -$36,763 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $3,746,460 | $235,197 | 6% | $1,876,949 | 50% | $3,676,255 | 98% | $5,553,204 | 148% | $1,869,511 |
| EM&V | $135,000 | $5,254 | 4% | $75,245 | 56% |  |  | $75,245 | 56% | $59,755 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,004 |  |  |  |  | 2,187 | 218% | 2,187 | 218% | 1,004 |
| Annual kWh | 6,817,104 |  |  |  |  | 7,558,646 | 111% | 7,558,646 | 111% | 6,817,104 |
| Lifecyc kWh | 102,778,298 |  |  |  |  | 127,574,119 | 124% | 127,574,119 | 124% | 102,778,298 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

Activities/Accomplishments –

- The Management Team approved MBCx projects for UC Davis, UC San Francisco, UCLA, CSU Dominguez Hills, CSU Los Angeles, CSU Pomona, CSU San Bernardino, CSU San Diego, CSU San Jose and CSU Stanislaus.  Estimated savings for these projects are approximately 1.6 MkWh and 380,000 therms.

- The Management Team approved Retrofit projects for UC Riverside and CSU Humboldt.  Estimated savings for these projects are approximately 56,000 kWh and 170,000 therms.

- The partnership has launched the program website that provides information about the program as well as status towards the energy efficiency goals.  The website is intended for general use, but also has a password protected portion that enables program team members to update project related information.  The website is located at: http://www.uccsuiouee.org/

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

Values shown in the workbook or the above tables do not accurately represent reality at the campus level.  Through December 2004, the total signed commitments to the campuses equal $1,334,028.  (This amount represents the total amount committed by the program and does not reflect any campus co-funding contributions.  By including the combined campus contribution of $405,948, the true overall project cost is $1,739,976.)  The net projected energy savings for the portfolio of projects are 3,182,496 kWh (78% of goal) and 823 kW (114% of goal).  These totals are obtained as follows:

- T-12 to T-8 Retrofit:

  - Campus project to retrofit 17,884 T12 fixtures.  Campus’ cost estimate of $26 per fixture differs greatly from the workbook estimate of $84 per fixture.  Total estimated project costs are $403,754. Net projected energy savings for the project are 868,530 kWh and 246 kW.

  - Campus project to retrofit existing T12 fixtures with 3,936 T8 fixtures.  Estimated project cost of $674,430 was provided by the campus.  Net projected energy savings for the project are 811,574 kWh and 132 kW.

  - Campus project to retrofit 3,000 2, 3, and 4 lamp T8 fixtures with advanced T8s.  Total estimated project costs are $66,330.  Net projected energy savings are 125,558 kWh and 32 kW.

- LED Exit Sign Retrofit: Actual measure funded was for LED traffic signal retrofit at a cost of $250 per unit (total of red, amber and green lights).  This is slightly higher than the $203 estimate for an exit sign.  Total estimated project costs are $60,000.  Net projected energy savings for the project are 54,416 kWh and 6.4 kW.

- Incandescent to CFL Retrofit: Actual measure funded was for an incandescent to fluorescent retrofit with occupancy sensors at 450 toilet rooms throughout the campus.  Installed cost per unit provided by the campus was $600 per toilet room.  Total estimated project costs are $270,000.  Net projected energy savings for the project are 425,526 kWh and 73 kW.

- Chiller Replacement:	Actual measure funded was five chiller/cooling tower optimization controllers at a cost of just over $18,000 per chiller.  Total estimated project costs are $91,907.  Net projected energy savings for the project are 627,691 kWh and 300 kW.

- HID to T5 Retrofit:

  - Campus project includes two separate retrofits.  One was to replace 32 MH fixtures with 18 T5 (F54T5/HO) and the other was to replace 76 500 W quartz fixtures with 71 F32T8 fixtures.  Estimated project cost of $44,375 was provided by the campus.  Net projected energy savings for the project are 106,014 kWh and 28 kW.

  - Campus project includes retrofitting a combination of MH and HPS fixtures with T5 fixtures. A total of 295 HPS fixtures will be replaced with 234 T5 fixtures and 392 HPS fixtures will be replaced with 263 T5 fixtures.  Total estimated project costs are $33,180.  Net projected energy savings are 38,330 kWh and 5.4 kW.

- VAV Retrofit:  Retrofit project is to convert an existing gym HVAC system to a VAV system.  Total estimated project cost is $96,000.  Net projected energy savings for the project are 124,857 kWh and 0 kW.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The partnership has renamed this program element as “Monitoring Based Commissioning” (MBC) to better reflect the actual scope of the activity.  The program goals and overall approach remain the same.