| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | CU/CSU Partnership Program – PGC |
| Program Number: | 1324-04 |
| Month: | June 2004 |

- Program Status

Program Description

The University of California/California State University (UC/CSU) and Investor-Owned Utility (IOU) Energy Efficiency Partnership is a unique, statewide energy efficiency program that accomplishes immediate, long-term energy efficiency and demand savings, and establishes a permanent framework for a sustainable  comprehensive energy management program at the thirty three (33) UC and CSU campuses served by California’s four large IOUs.  This program capitalizes on the vast resources and expertise of the UC/CSU and the California IOU’s to ensure a successful and cost effective program that meets all objectives of the California Public Utilities Commission (CPUC or Commission) as articulated in Decision 03-08-067. In lays the groundwork for not only a continued UC/CSU comprehensive energy efficiency program but also establishes a model for statewide partnership programs and will allow expansion of this program to California’s community colleges in the next funding cycle. The UC/CSU/IOU partnership program is comprised of three elements, which will operate on a statewide, integrated basis, providing immediate energy savings and setting the foundation for a long-term program focused on sustainability and best practices: Energy Efficiency Retrofits, Facility Retro-and Continuous Commissioning, and Energy Efficiency Education and Best Practices Development and Training.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,500,000 | $64,242 | 1% | $243,212 | 5% |  |  | $243,212 | 5% | $4,256,788 |
| Admin | $618,540 | $60,332 | 10% | $227,070 | 37% |  |  | $227,070 | 37% | $391,470 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $3,746,460 |  |  |  |  |  |  |  |  | $3,746,460 |
| EM&V | $135,000 | $3,910 | 3% | $16,142 | 12% |  |  | $16,142 | 12% | $118,858 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jun-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,004 |  |  |  |  |  |  |  |  | 1,004 |
| Annual kWh | 6,817,104 |  |  |  |  |  |  |  |  | 6,817,104 |
| Lifecyc kWh | 102,778,298 |  |  |  |  |  |  |  |  | 102,778,298 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

Activities/Accomplishments –

- The Training and Education (T&E) program component conducted a “Sustainability Conference” at UCSB on June 21 and 22, 2004. The two days of conference seminars covered a wide range of energy efficiency topics and technology.

- The Management Team approved a second round of retrofit projects on June 15.  A total of five projects were pre-screened and submitted by the Retrofit Team.  Of these five projects, four were eventually approved for UC Irvine, Cal State San Bernardino, Cal State Hayward and Cal State San Francisco.  Specific measures include lighting upgrades and VAV retrofits.  Estimated savings for this second round of projects are approximately 847 kW, 4,409,645 kWh and 0 therms with approximately $1.0 million in additional statewide direct implementation budget being committed.  A third round of approvals is scheduled for mid-July.

- All UC Campuses approved for funding in the first two approval cycles have been notified of their approval and are preparing invoices for payment by the utility partners.  The Cal State campuses are going through the process of securing co-funding as only a portion of their projects will be paid for by the partnership.

- The MBCx Team has developed a draft solicitation package to be used to request commissioning project nominations from campuses.  The solicitation package is currently undergoing review and comment by team members and should be finalized in July.

- The Master Agreement has been signed by five of the six partners and is currently awaiting final partner signature.  Full execution is expected by mid-July.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

The EM&V Team issued the RFP to potential bidders on May 10.  Responses were received and reviewed in early June.  XXXXX was selected as program EM&V contractor.  The “Kickoff Meeting” is expected to be conducted in early July.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

The partnership has renamed this program element as “Monitoring Based Commissioning” (MBC) to better reflect the actual scope of the activity.  The program goals and overall approach remain the same.