| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Bakersfield/Kern County Program – PGC |
| Program Number: | 1325-04 |
| Month: | March 2005 |

- Program Status

Program Description

Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), Southern California Gas Company (SoCalGas), the City of Bakersfield (City), the County of Kern (County), and Staples/Hutchinson and Associates, Inc. (Staples/Hutchinson) entered into a partnership to reduce energy use by providing energy efficiency information and direct installation of energy efficient equipment to the City and County’s local community.

Specifically, this partnership will offer direct install services to hard-to-reach customers, home buyers, and small businesses; free energy audits to both residential and nonresidential hard-to-reach customers; marketing and outreach to encourage participation in statewide energy efficiency programs; municipal building energy efficiency retrofits; support for codes and standards enforcement; and local training seminars for residential contractors as well as design/build firms and engineers and architects working on commercial properties.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | $7,885 | 1% | $70,669 | 7% | $192,709 | 19% | $263,378 | 26% | $929,331 |
| Admin | $154,625 | $5,751 | 4% | $68,168 | 44% |  |  | $68,168 | 44% | $86,457 |
| Marketing | $32,308 |  |  |  |  |  |  |  |  | $32,308 |
| DI | $813,067 | $2,134 | 0% | $2,501 | 0% | $192,709 | 24% | $195,210 | 24% | $810,566 |
| EM&V |  |  | NA |  | NA |  | NA |  | NA |  |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 520 |  |  |  |  | 110 | 21% | 110 | 21% | 520 |
| Annual kWh | 2,082,199 |  |  |  |  | 596,493 | 29% | 596,493 | 29% | 2,082,199 |
| Lifecyc kWh | 29,477,295 |  |  |  |  | 8,020,614 | 27% | 8,020,614 | 27% | 29,477,295 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Audits of Municipal facilities in Kern County | 5 | 0 | 0% | 5 | 100% | 0 | 0% | 5 | 100% | 0 |
| In-home surveys | 960 | 0 | 0% | 0 | 0% | 319 | 33% | 319 | 33% | 641 |

  - Activities/Accomplishments

    - Administrative -

- Administrative activities related to standard program implementation included the monthly partnership coordination meeting of all partners in Bakersfield on March 24, 2005  in Bakersfield; telephone calls, e-mails and meetings between PG&E and Staples Marketing and between PG&E and potential residential services vendors; telephone calls and e-mails at each utility to plan 2005 activities; meetings, telephone calls and e-mails between the City of Bakersfield, County of Kern and PG&E and between the County of Kern and SCE to discuss progress in municipal building retrofits; and between utilities to coordinate marketing activities.

- On March 17, an orientation session was held for office staff at the Bakersfield Energy Watch office held to cover PG&E’s procedures for obtaining the three customer account numbers needed for each residential or business premise.  A subsequent meeting was held with the energy efficiency survey staff to integrate those procedures into the current practice.

    - Marketing -

The Bakersfield & Kern County Energy Watch advertising schedule for March continued to concentrate on radio.  Radio commercials ran for three weeks in March on six local stations: KUZZ, KKBB, KERN, KDFO, and Spanish radio stations LOBO and KCHJ.

The radio schedule generated 44 phone requests for residential energy surveys in March..  Another 160 requests for residential energy surveys resulted from realtor referrals and special events.

Bakersfield & Kern County Energy Watch staffed a booth at the Ranch Market on March 4, 7-8, 11, 14-15 and 18, which generated 313 requests for energy surveys. Energy Watch staffed a booth at the Bakersfield Health Fair which generated 40 requests.

    - Direct Implementation –

Education and Training: While there were no training courses specifically offered by Energy Watch during March, the partnership was active in promoting the following Industrial Seminar:

- Prime Movers Industrial Seminar, March 19, 2005 – This course presented attendees with a look at the financial component of natural gas/diesel engines versus electrical pumping costs.  The course not only addressed financial considerations, but also involved an in-depth discussion of the air quality impacts affecting agricultural installations in the Valley.  The session was attended by 24 local business people and the course was received very well.  The seminar was held at Hodel’s Restaurant in Bakersfield and was a part of PG&E’s Industrial Seminar series.

In April, the 3 following workshops will be offered in Bakersfield and the Energy Watch program will have a significant role in the promotion and facilitation of these workshops:

- April 14, 2005, The First Business Customer Energy Efficiency Workshop – The workshop will focus on delivering information on various “Statewide Energy Efficiency Technologies” as well as information on the state’s various Demand Response Programs.  In addition, various manufacturers’ representatives will present the latest in technological advances in energy efficiency such as lighting and heating, ventilation and air conditioning.  The workshop will be held at Hodel’s Restaurant and will run from 9:00 a.m. to 3:00 p.m.

- April 21, 2005, The Restaurant and Food Services Technologies Workshop – Attendees of the workshop will hear the latest in food service energy efficiency during a 2 hour presentation by Richard Young of The Food Services Technology Center in San Ramon, California.  Mr. Young will address various improvements and their energy efficiency benefits for such technologies such as: lighting, refrigeration and cooking equipment.  The workshop will be held from 9:00 a.m. to 11:00 a.m. at Hodel’s Restaurant in Bakersfield.

- April 28, 2005, Proper Procedures for Charging Air Conditioners and Heat Pumps – In this workshop, attendees will receive a detailed review of checking refrigerant charge and air flow for all residential refrigerant types.  Terry Norris of Advanced Energy Corporation will deliver the class which will include actual hands on charging on several HVAC systems.  The session will be held from 8:00 a.m. to 4:00 p.m. at the East Bakersfield Senior Center in Bakersfield and N.A.T.E. continuing education credit can be earned by attending.

There are no Energy Watch Training and Education Events currently scheduled for May 2005. However, as in the past, we will continue to identify the needs of the community and develop courses to meet those needs in the timeliest manner possible.  We shall also continue to promote programs offered by all the partners that may provide benefit to our community.

Realtor Program:  Staff from the Energy Watch office in Bakersfield continues to make presentations to partner Realtor® firms.  Coupons offering free energy surveys are sent out to homebuyers and requests for homebuyer home energy surveys are scheduled by the Energy Watch office.  In addition, staff is partnering with both not-for-profit and profit businesses and organizations to distribute Energy Watch information to their employees.

      - Audits, Site Surveys and Partnerships -

PG&E and SCE continued work with the city of Bakersfield and the county of Kern on municipal building energy efficiency retrofits, and some retrofits have started.

During March, Bakersfield & Kern County energy survey staff completed 50 non-residential surveys. No HVAC tune-ups were completed.  A monthly total of  176 CFLs, 2 2-tube ballasts, 254 4-tube ballasts, 1,020 48” fluorescent tubes, 9 occupancy sensors and no (zero) LED exit signs were installed in non-residential buildings. This is PG&E service area only.

During the month of March, Staples Marketing accomplished 573 residential energy surveys, which resulted in distribution of 2,865 CFLs and installation of 60 programmable thermostats to households in PG&E service area.

The residential direct install component provided services for 128 single family and 0 multifamily PG&E customers, and 10 single family and 53 multifamily SCE customers in March 2005.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| MEASURE/ACTIVITY NAME | Paid Units | Committed Units |
| --- | --- | --- |
| Single Family Direct Install |  |  |
| ES Screw-in CFL (21 to 30 watts) for calc. use 25 Watts |  | 1,236 |
| ES Interior Hardwired CFL Fixtures (30 Watts) |  | 1,182 |
| ES Programmable Thermostats |  | 102 |
| Multi-family Direct Install |  |  |
| ES Screw-in CFL (21 to 30 watts) for calc. use 25 Watts |  | 1,045 |
| ES Interior Hardwired CFL Fixtures (30 Watts) |  | 998 |
| ES Exterior Hardwired CFL Fixtures (27 Watts) |  | 727 |
| ES Programmable Thermostats |  | 16 |
| T-5 or T-8 Int. lamps with electronic ballasts - (4 ft. 1 lamp) |  |  |
| T-5 or T-8 Int. lamps with electronic ballasts - (4 ft. 2 lamps) |  |  |
| T-5 or T-8 Int. lamps with electronic ballasts - (8 ft. 1 lamp) |  |  |
| T-5 or T-8 Int. lamps with electronic ballasts - (8 ft. 2 lamps) |  |  |
| SPC PLUS |  |  |
| Lighting |  | 24,700 kWh |
| HVAC/Refrigeration |  | 59,030 kWh |
| Motors/Other |  | 3,560 kWh |

      - Calculated and Actual Payment Reconciliation -

Since actual incentives payable to customers are capped at maximum program rebate levels with certain measures qualified for partial incentive payment only, the financial incentives to customers in Tab 1A - Expenditures Worksheet may differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

Energy savings and peak demand reduction recorded by SCE may differ from those calculated in the Workbook because measure energy savings/peak demand reduction can vary by market segment or climate zone.

    - EM&V

XXXXX, the consultant conducting the evaluations of seven of PG&E’s partnership programs received Energy Division approval to proceed with implementation of its evaluation plan on October 29, 2004. Survey design is proceeding and the revised EM&V project schedule has been reflected in tab 6 of PG&E’s workbook.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

PG&E, SCE and SCG filed revised Program Implementation Plans (PIP) and workbooks for this program on June 15, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP. In addition, all Energy Watch partners have provided Staples Marketing with supplies of informational materials regarding other energy efficiency programs to be handed out at special events scheduled to promote Energy Watch and statewide energy efficiency programs.

- Changes to Subcontractors or Staffing

None

- Additional Items

None