| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local City of Pomona Program – PGC |
| Program Number: | 1326-04 |
| Month: | October 2004 |

- Program Status

Program Description

The City of Pomona (the “City”) and Southern California Edison (”SCE”), have teamed up to implement a set of innovative strategies with the objective of overcoming market barriers to reach underserved markets within the City of Pomona.  The goal of this program is to create permanent energy savings by utilizing both the mechanisms and partnerships unique to local governments, and also the existing infrastructure within the City of Pomona government.  The partnership between SCE and the City of Pomona ensures that all the ideas in this proposal are complementary to those already offered by the Utility.  The City proposes to retrofit a number of city facilities with high efficiency equipment including T8 lights, premium efficiency HVAC units and LED Pedestrian Indicators, reducing the city’s energy usage.  The outreach portion of this program will be targeted to the hard-to-reach residential and non-residential customers within the City of Pomona.  First, this is a local program tailored specifically to the City of Pomona.  Secondly, it utilizes specific local institutions and networks to aid in program marketing and delivery.  Third, it focuses primarily on hard-to-reach residential markets (multi-family, low-income and owner tenant "split incentive" situations), and underserved commercial markets (small and very small businesses, retail, groceries, and restaurants).  Fourth, we segment the market further than previous programs have done, to tailor outreach and delivery methods to specific sub groups.  Finally, we train local vendors and technicians on the various resources available to them to market and implement energy efficiency projects.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $651,023 | $21,827 | 3% | $187,942 | 29% | $25,958 | 4% | $213,900 | 33% | $463,080 |
| Admin | $129,094 | $9,635 | 7% | $55,120 | 43% | $4,702 | 4% | $59,822 | 46% | $73,974 |
| Marketing | $247,446 | $12,191 | 5% | $53,132 | 21% | $21,256 | 9% | $74,388 | 30% | $194,314 |
| DI | $250,484 |  |  | $79,500 | 32% |  |  | $79,500 | 32% | $170,984 |
| EM&V | $23,999 |  |  | $190 | 1% |  |  | $190 | 1% | $23,809 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Oct-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 47 |  |  |  |  |  |  |  |  | 47 |
| Annual kWh | 482,650 |  |  |  |  |  |  |  |  | 482,650 |
| Lifecyc kWh | 7,594,458 |  |  |  |  |  |  |  |  | 7,594,458 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Retrofit Element

    - Retrofit element consists of retrofitting 12 City of Pomona buildings with light fixtures, CFL’s, occupancy sensors and packaged air conditioning units. In addition, all of the City’s pedestrian indicators will be retrofitted with LED type indicators.

    - SCE conducted comprehensive audits of the proposed facilities and have finalized the specific types of ECMs and quantities to be replaced in each facility.

    - SCE will provide technical assistance to the City of Pomona in the development of an RFP.

    - Pomona Public Works Department received 3 quotes from LED indicator vendors.  The lowest bid provided an average unit installed cost of $100 compared to the estimated amount of $147 for type A and $251 for type C shown in the workbook.  Three hundred additional units will be purchased with the remainder of the funds.  Public works projected that they may be able to install 908 indicators by December 31, 2004.

    - SCE made a reserve fund payment of $79,500.00 to the City of Pomona to cover 50% of the purchase cost of the LED pedestrian indicators.  City of Pomona Public Works department will provide in-kind labor contribution to manage the installation of those units.

- Education and Outreach

- The partners have identified the following channels for information dissemination and will work with Pomona’s Public Information Officer to place program announcements in City newsletters, website design and also contacting chambers of commerce:

  - e-newsletters (English and Spanish) - 200 individuals

  - Quarterly newsletter - residence only

  - Small business visitation group - team of 3 - about 10 to 15 a week each.

  - Cable Show - throughout the City - Pomona

  - Chambers of Commerce

  - Hispanic Chamber of Commerce

- A purchase order from SCE was established for XXXXX to implement the marketing/outreach program.  XXXXX submitted five invoices for the amount of $24,584.15, $13,965.00, $19,686.04, $17,175.41 and $25,958.15 to cover the marketing and outreach activities. The first four invoices were paid and reported in the workbook under sub-contractor expenditures.  The fifth invoice of $25,958.15 is shown in the workbook as committed.

    - Marketing –

- All marketing outreach activities in Pomona, being coordinated by XXXXX, will be executed under the “Pomona Energy IQ Program”.  The program logo that will be utilized consistently across all marketing materials, handouts, and other communications is included below:

- Content development, design, and printing of the second round of energy efficiency informational brochures were completed.  A total of 50,000 residential and 6,500 business brochures have been printed.  Distribution of these brochures will be completed in November and early December.  Partial distribution of residential brochures was completed in October.

- Content development for the Pomona Energy Efficiency website was completed as well.  The website link was successfully added to the Pomona City website.  Visitors can follow the link to get Pomona specific energy efficiency information.  This was coordinated with the City of Pomona Public Relations Office.  The website is currently up and running – ahead of the December, 2004 target date.  This website can be accessed through the main page of the Pomona City website at http://www.ci.pomona.ca.us/.

- The partnership participated in the second City Event on October 5, 2004.  The event, named “Hispanic Fiesta”, was organized by the Pomona Latino Chamber of Commerce.  There were over 6,000 attendees.  Information about incentives and other resources were handed out to attendees.  Experienced energy efficiency staff was in the booth to answer any energy efficiency related questions.

- The partners successfully held the first small business meeting on October 21 with the Pomona Chamber of Commerce.  The October mixer was sponsored by the partnership and highlighted the Pomona Energy IQ Program.  There were over 60 people in attendance at this event.  A presentation was given highlighting the benefits of energy efficiency for small businesses.  Information about the Express Efficiency and Audit Programs were handed out to the attendees.

- Discussions are ongoing with the City of Pomona for coordinating Earth Day in 2005.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

SCE assisted the City of Pomona with comprehensive site audits of proposed facilities.  These facilities include fire stations, libraries, and an airport hangar.  The audited sites are listed in the table below.

Information Summary

City of Pomona Fire Stations

| Station No | Address | SqFt | Yr Built |
| --- | --- | --- | --- |
| 181 | 590 S Park | 20,562 | 1963 |
| 182 | 1059 N White | 5,840 | 1962 |
| 183 | 710 N San Antonio | 5,776 | 1954 |
| 184 | 1980 W Orange Grove | 4,125 | 1956 |
| 185 | 925 E Lexington | 3,980 | 1962 |
| 186 | 280 E Bonita | 5,952 | 1964 |
| 187 | 3325 Temple | 5,460 | 1979 |
| 188 | 18•A Village Loop | 3,330 | 1981 |
| Aero Bureau | 1905 McKinley | ~600 | Keetle |
| Prop&Evid | 910 W 4th |  |  |
| Pistol Range | 465 Humane Way |  |  |
| Willie White Park | Battram@Valera |  |  |

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

SCE’s M&V group selected XXXXX to perform the EM&V for this partnership program. A draft research plan for the City of Pomona Energy Efficiency Program Evaluation was submitted to the CPUC on August 9, 2004.

- Program Challenges

Program encountered implementation challenges with the retrofit element.  Due to a shift in program funding from LED pedestrian indicator, as requested by the CPUC, additional lighting measures were increased. The comprehensive audits conducted in the facilities from the original list of fire stations and hangar shown in the table above do not provide enough opportunities to retrofit all the proposed measures.  As such, the City of Pomona is researching other city facilities to implement the additional measures.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Partners will coordinate with SCE’s Nonresidential Hard-To-Reach program to provide 150 businesses with 100% direct installation of lighting retrofits.

- Partnership program has coordinated with KEMA-Xenergy EEGOV B.E.S.T. program to offer incentives to small hard to reach customers within the City of Pomona for replacement of various energy efficiency measures and also to jointly offer the vendor workshops.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

- The timeline for program delivery, especially for the outreach component of the program, will need to be shifted due to a delay in the final CPUC approval of the City of Pomona Partnership program.  Approval was granted on February 26, 2004.

- There are several items in the filed PIP that will require some changes as a result of the investment grade audits and from discussions with City of Pomona representatives regarding the issues itemized below.

  - Change in the outreach strategy - the email campaign will be eliminated from the marketing/outreach effort. It was determined that the email approach would not be cost effective and that there is legal concerns regarding spamming.  As such, the Partners propose to perform one additional small business meeting and one additional City event.

  - SCE has performed investment grade audits on the facilities.  The following was revealed as a result of the audits.

    - 743 4' 2-lamp fixtures that may be replaced compared to the filed quantity of 1,662 units of  4' 2-lamp fixtures.

    - 92 Occupancy sensors compared to 155 units.

    - 25 tons of cooling capacity vs. 35 tons. There were other cooling capacities identified in the audits.  However, only 25 tons were considered to be cost effective for replacement.

    - 0 sq ft. of window film vs. 1329 sq. ft.  (Pomona originally thought that a south facing wall of the public library and city hall did not have window film.  However, the audit reveals that those windows have already been covered.  The only opportunity left are windows in the various fire stations.  Due to the scattered facilities and small quantities,  it is not cost effective to install the window film at those facilities.  As such, this measure will be eliminated.)

    - Actual LED Pedestrian indicators quoted price were substantially less than originally quote.  As such, the partners were able to purchase additional 300 units.