| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Ventura County Regional Energy Alliance – PGC |
| Program Number: | 1403-04 |
| Month: | September 2004 |

- Program Status

Program Description

The Ventura County Regional Energy Alliance (VCREA), in partnership with Southern California Edison (SCE) and the Southern California Gas Company (SCG) proposes to build on the VCREA’s progress to date to further develop its core capabilities, to complete the development of its Energy Resource Center capability, and to implement a targeted Public Sector Program for public agencies throughout the Ventura County region.  This effort will utilize the strengths of the VCREA and its utility partners to jointly overcome identified participation barriers, better serve local needs and hard-to-reach customers, and increase participation in energy efficiency programs.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,273,152 | $283 | 0% | $58,344 | 5% | $38,255 | 3% | $96,599 | 8% | $1,214,808 |
| Admin | $126,899 | $283 | 0% | $23,511 | 19% | $16,821 | 13% | $40,332 | 32% | $103,388 |
| Marketing | $18,575 |  |  | $101 | 1% | $101 | 1% | $202 | 1% | $18,474 |
| DI | $1,066,896 |  |  | $34,732 | 3% | $21,333 | 2% | $56,065 | 5% | $1,032,164 |
| EM&V | $60,781 |  |  |  |  |  |  |  |  | $60,781 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the VCREA to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE receives this information, the costs now shown in the committed column will be reported in the supporting workbook.

    - Energy Effects

| Energy Effects | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,618 |  |  |  |  |  |  |  |  | 1,618 |
| Annual kWh | 6,432,343 |  |  |  |  |  |  |  |  | 6,432,343 |
| Lifecyc kWh | 97,593,078 |  |  |  |  |  |  |  |  | 97,593,078 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Conduct at least 6 sessions for businesses | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 6 |
| Conduct at least 4 events for residential customers. | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Promote VCEEC resources and energy efficiency information at 20 community events or more. | 20 | 1 | 5% | 2 | 10% | 0 | 0% | 2 | 10% | 18 |
| Respond to every customer inquiry within 48 hours. |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Reduce Energy Consumption in Major facilities of VCREA member agencies by 8 % |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Reduce peak demand in major facilities of VCREA member agencies by 5% or more |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |

  - Activities/Accomplishments

1.2.1	Administrative -

- Partners meetings were held on September 1 and 10, 2004.

    - Marketing and Outreach -

- The VCERC was promoted in three local publications of the “Flash Trash” publication for fall quarter distribution (Cities of Ventura, Fillmore and Camarillo).  Planning is underway for expanded fourth quarter coverage of the VCERC through “Flash Trash” publication and Ventura County Employees Newsletter.

- Press releases were sent to local media including “VCMAX”, which is distributed quarterly to approximately 4000 households within the county of Ventura.  A press release announcing the opening of the VCERC at its 1000 Hill Road location was also distributed to local press.

- Flyers to promote the two training sessions that were planned for September were distributed to the community via the Thousand Oaks City Hall, VCREA mailing list and the World Affairs Council mailing list.

- The VCERC was promoted in the Ventura Star Press as a result of an event held at Cal Lutheran University, Thousand Oaks, on the subject of energy.

- The VCERC was promoted to cable viewers watching the Santa Paula City Council meeting September 20, as a result of the city’s interest to join the VCREA.

- The VCERC was promoted to the Ventura Council of Governments at its September 9th meeting.

- The VCERC was promoted at a regional meeting of elected officials and business representatives hosted by SCG on September 9, 2004.

    - Direct Implementation –

- The first training events scheduled for September 22 and 23 for residential and commercial customers did not take place as planned.  However, the events were marketed in conjunction with the World Affairs Council of Ventura County and the City of Thousand Oaks as well as the VCREA mailing list.  These marketing activities provided exposure for the new energy resource center’s location and offerings.  The workshops have already been developed and will be rescheduled and marketed to a wider audience.

- The VCERC conducted outreach activities at an event held by the VCREA and the World Affairs Council of Ventura County entitled “Energy Choices and Environmental Challenges”.  The event provided an opportunity to provide information on the VCERC.  An energy “white paper” was crafted at the event and will be posted on the Center’s website vcenergy.org.

- A public RFQ process for lighting vendors was undertaken to assist in selection of qualified contractors to implement facility energy efficiencies.

- The VCERC was expanded to include lighting displays and maps.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- VCREA has continued discussions with KEMA-Xenergy regarding the potential of offering the EEGOV Business Energy Services (B.E.S.T.) Team Program to cities within Ventura County and anticipates meeting with KEMA-Xenergy staff in October to discuss further.

- VCREA has also initiated discussions with EnSave Energy Performance, Inc. regarding integrating the California Multi-Measure Farm Program into Agricultural Training programs.

- VCREA has initiated discussions with CSU-Fresno regarding assisting with training for the agricultural energy efficiency training in October.

- SCE AgTag courses and Pump Test Program along with relevant SCG offerings are also available.  These programs will be integrated into the partnership’s training activities.

- Changes to Subcontractors or Staffing

- XXXXX joined the VCREA staff as Administrative Assistant in a full-time capacity on September 8, 2004.

- Additional Items

None