| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1405-04 |
| Month: | April 2005 |

- Program Status

Program Description

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $610,987 | $209 | 0% | $419,498 | 69% | $44,517 | 7% | $464,015 | 76% | $191,489 |
| Admin | $126,157 | $21 | 0% | $61,063 | 48% | $12,988 | 10% | $74,051 | 59% | $65,094 |
| Marketing | $18,406 |  |  | $13,646 | 74% | $2,081 | 11% | $15,727 | 85% | $4,760 |
| DI | $439,384 |  |  | $337,433 | 77% | $29,447 | 7% | $366,881 | 83% | $101,950 |
| EM&V | $27,040 | $189 | 1% | $7,355 | 27% |  |  | $7,355 | 27% | $19,685 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the SBCCOG to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE processes this information, the costs shown in the committed column, will be reported in the supporting workbook.

*Includes SCE Reserve payment of $90,268

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Apr-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 4 | 100% | 0 | 0% | 4 | 100% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 1 | 8% | 6 | 50% | 0 | 0% | 6 | 50% | 6 |
| Conduct at least 4 events for residential customers. | 4 | 1 | 25% | 17 | 425% | 0 | 0% | 17 | 425% | 0 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 2 | 16% | 23 | 192% | 0 | 0% | 23 | 192% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 5 | n/a | 25 | n/a | 0 | n/a | 25 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Activities/Accomplishments

    - Administrative -

- SBESC continues to work with SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

- Team researched and reviewed options for new office space.

- Executive Director met with XXXXX, SCE Director of Energy Efficiency on the progress of the program

    - Marketing –

SBESC:

- Updated the SBESC website with current information and pictures

- Personalized promotional flyers for two training events.

- Published quarter-page advertisement in The Beach Reporter (distribution of 65,000 households for April 26 workshop

- E-mail blast to over 700 names for trainings on April 26 and 27.

- Arranged for distribution of over 2,000 flyers for April 27 and May 11 Inglewood Chamber of Commerce events.

- Prepared 24 x 36 laminated poster board for use at many events.

- Discussed print media advertising campaigns with the Daily Breeze.

- Team worked on e-newsletter concepts and format.

Outreach Activities

SBESC continues to work with member cities, public officials and community organizations to secure assistance in disseminating energy efficiency information and co-sponsoring training events.  SBESC continues to handle walk-ins and telephone calls from the community and signing out resources from the lending library.  SBESC responded to all calls to the center in less than twenty-four hours.  SBESC Program Manager:

- Met with Gas Company Partners regarding collaborating and conducting an event and training for restaurants in the South Bay.   The first step is to form a committee of restaurant owners in the South Bay.

- Spoke with Gabriella Holt regarding an appearance on the Rancho Palos Verdes cable television show.

- Spoke with XXXXX of Flex Your Power to collaborate in a local energy efficiency program with XXXXX, Deputy Secretary of Energy for the State.

- Worked with city of Torrance Councilman XXXXX, who sent letters out to the mobile home parks in the city of Torrance.   Workshops will be scheduled in May and June.

- Worked with city of Lomita Councilwoman XXXXX, who sent letters to all the mobile home parks in the city of Lomita.  We have scheduled a residential training event for May 11, 2005 at Orchard Trailer Park.

- Spoke with Southwood Homes Association in Torrance and arranged residential energy efficiency training for June 6.

- Spoke with XXXXX and arranged a residential energy efficiency training for ‘brown bag’ lunch for the League of Women Voters (Beach Cities, Torrance and Palos Verdes groups) for July 28, 2005.

    - Direct Implementation

- Training

- SBESC delivered energy efficiency workshops for residential customers during the reporting period as follows:

  - April 26 - Residential training at the SBESC.  There were 7 attendees

  - Marketing and promotion was done for a commercial training event in Inglewood on April 27 but there were no attendees.

Follow-up for training event included thank you letters and participation certificates. Most of the attendees rated the event good to excellent.

Community Event

- April 23 – Earth Day.  Manhattan Beach Approximately 3,000 visitors attended.

- April 30 – Earth Day. Redondo Beach.  Approximately 1,500 visitors attended.

Energy Efficiency Action Plan

- SBCCOG has proposed a change in the name of Planning element of the program from The ‘Energy Efficiency Action Plan’ to the ‘Energy Efficiency Assessment’.  The plan is currently being worked on and a first draft will be completed in time to be incorporated in current program.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

No activity this month.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination/Cooperation Activities

- SBESC is also exploring opportunities to cooperate with various organizations in the City of Inglewood, including a non-IOU direct install program to deliver energy efficiency training to Inglewood businesses.

- SBCCOG is participating in the Navigant CaLEEP Pilot Program.  Navigant will complete energy efficiency planning for South Bay Cities.

- Changes to Subcontractors or Staffing

None

- Additional Items

None