| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1405-04 |
| Month: | June 2005 |

- Program Status

Program Description

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $610,987 | $11,784 | 2% | $477,972 | 78% | $44,223 | 7% | $522,195 | 85% | $133,015 |
| Admin | $126,157 | $11,596 | 9% | $87,821 | 70% | $12,143 | 10% | $99,964 | 79% | $38,336 |
| Marketing | $18,406 |  |  | $15,727 | 85% | $1,442 | 8% | $17,169 | 93% | $2,679 |
| DI | $439,384 | $377 | 0% | $367,257 | 84% | $30,638 | 7% | $397,895 | 91% | $72,126 |
| EM&V | $27,040 | -$189 | -1% | $7,166 | 27% |  |  | $7,166 | 27% | $19,874 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the SBCCOG to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE processes this information, the costs shown in the committed column, will be reported in the supporting workbook.

*Includes SCE Reserve payment of $90,268

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jun-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 5 | 125% | 0 | 0% | 5 | 125% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 1 | 13% | 7 | 58% | 0 | 0% | 7 | 58% | 5 |
| Conduct at least 4 events for residential customers. | 4 | 5 | 125% | 22 | 550% | 0 | 0% | 22 | 550% | 0 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 0 | 0% | 26 | 216% | 0 | 0% | 26 | 216% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 10 | n/a | 37 | n/a | 0 | n/a | 37 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Activities/Accomplishments

    - Administrative -

- SBESC continues to work with SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

- Team signed lease and moved into new office facilities at 3868 Carson Street, Torrance.

- Team participated in meetings, conference calls and other communication with Partners regarding the existing program and planning for future program.

- Contacted SCE partners to procure additional CFL’s to be handed out at community events.

- A new Environmental Deputy was hired during the reporting period

    - Marketing and Outreach –

SBESC:

- Prepared full page ad for special Graduation edition of The Daily Breeze, June 9, circulation 222,008 households

- Prepared flyer for July 21 special workshops for religious facilities, and sent out personalized invitations to 175 local houses of worship.

- Prepared flyer for each of the four mobile home park trainings and delivered them a week ahead of the training date trainings.

- Prepared articles for SBESC E-Newsletter and SBCCOG newsletter.  Published SBESC E-newsletter June 29.

- Met with Congresswoman XXXXX Field Deputy at SBESC.

- Continue to process requests from telephone callers and visitors to the center in a timely manner.

    - Direct Implementation

- Training

- SBESC delivered energy efficiency workshops for residential customers during the reporting period as follows:

  - June 6   - Southwood Homeowners Association, Torrance, CA

  - June 8   - Knolls Mobile Home Park, Torrance, CA

  - June 21 - SK Mobile Home Park, Torrance, CA

  - June 23 - San Rafael Mobile Home Park, Harbor City, CA

  - June 30 - Skyline Mobile Home Park, Torrance, CA

- The following business training was also delivered:

  - June 22 - Business –Hotel Training, Torrance, CA

Follow-up for training event included thank you letters and participation certificates. Most

of the attendees rated the event good to excellent.

Energy Efficiency Action Plan

The plan is currently being worked on and a first draft will be completed in time to be incorporated in current program.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

No activity this month.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination/Cooperation Activities

- SBCCOG is participating in the XXXXX CaLEEP Pilot Program.  XXXXX will complete energy efficiency planning for South Bay Cities.

- Changes to Subcontractors or Staffing

None

- Additional Items

None