| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1405-04 |
| Month: | December 2004 |

- Program Status

Program Description

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $610,987 | $3,535 | 1% | $246,399 | 40% | $18,360 | 3% | $264,759 | 43% | $364,587 |
| Admin | $126,157 | $2,523 | 2% | $45,064 | 36% | $2,770 | 2% | $47,834 | 38% | $81,093 |
| Marketing | $18,406 |  |  | $16,090 | 87% | $1,106 | 6% | $17,196 | 93% | $2,316 |
| DI | $439,384 |  |  | $184,233 | 42% | $14,484 | 3% | $198,717 | 45% | $255,151 |
| EM&V | $27,040 | $1,013 | 4% | $1,013 | 4% |  |  | $1,013 | 4% | $26,028 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the SBCCOG to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE processes this information, the costs shown in the committed column, will be reported in the supporting workbook.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 1 | 25% | 4 | 100% | 0 | % | 4 | 75% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 0 | 0% | 2 | 17% | 0 | 0% | 2 | 17% | 10 |
| Conduct at least 4 events for residential customers. | 4 | 1 | 25% | 3 | 75% | 0 | 0% | 3 | 75% | 1 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 0 | 0% | 17 | 142% | 0 | 0% | 17 | 142% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 0 | n/a | 10 | n/a | 0 | n/a | 10 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Activities/Accomplishments

    - Administrative -

- SBESC continues to work SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

- SBESC followed-up with program attendees by mailing thank-you letters and personalized certificates of participation.

- SCE provided additional CARE and Energy Efficiency Program marketing materials to the SBESC.

    - Marketing –

SBESC:

- Updated the SBESC website with current information

- Marketed the January 18, 2005 workshop through:

  - Presentation to VOICE, an environmental group in Manhattan Beach.

  - Presentation and distribution of program material and information flyer to the Palos Verdes Chamber of Commerce

- Outreach Activities

SBESC continues to work with member cities, public officials and community organizations to secure assistance in disseminating energy efficiency information and co-sponsoring and endorsing of training events and displaying energy efficiency information in their facilities.  SBESC continues to handle walk-ins and telephone calls from the community and signing out resources from the lending library:

SBESC:

- Sent e-mail reminders to member cities to link to the SBESC website.

- Met with Workforce Invest Board Executive Directors and was successful in securing cooperation for two community outreach events scheduled for January 2005

- Secured cooperation from the City of Carson regarding publication of an energy efficiency article and SBESC information in the Mayor of Carson’s city wide newsletter.  The article will highlight the services being offered to the city of Carson’s mobile home community and will be distributed to 34,648 households.

- Delivered LED holiday lights to each of the fifteen South Bay cities with information on the SBESC and upcoming programs.

- Followed-up with attendees to public agencies training event regarding additional training for their cities.

- Met with the City of Inglewood regarding coordinating training with the Energy Savers Program for Inglewood’s winter seminar series for businesses.

    - Direct Implementation

- A residential energy efficiency workshop was held at the Savings Center in Torrance on December 8, 2004.  Five residents attended the event and gave an overall rating of excellent.

- An energy efficiency training for public agencies on December 14, 2004 at the Energy Savings Center in Torrance.  There were eleven attendees representing the cities of Gardena, Inglewood, Rancho Palos Verdes, and Rolling Hills Estates.  The attendees rated the event good to excellent.

- Work continues on the Energy Efficiency Action Plan.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

- None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination/Cooperation Activities

- SBESC identified, through the mobile home outreach program, mobile homes that had no heat.  The matter was referred to SCG for action.

- The local SCE Hard-to-reach Small Business Direct Install Program has been identified for participation by South Bay small businesses.  The Multi-family torchiere exchange has also been identified for the South Bay.

- SBESC is also exploring opportunities to cooperate with ASW Engineering’s HTR business energy efficiency program.

- SBESC coordinated with Mayor XXXXX of Carson regarding residential training for mobile home Parks in Carson.  These mobile homes benefit from SBESC residential energy efficiency training coupled with American Synergy Corporation’s Hard to Reach Mobile Home Program.

- Changes to Subcontractors or Staffing

None

- Additional Items

None