| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1405-04 |
| Month: | April 2004 |

- Program Status

Program Description

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $793,490 | $18,651 | 2% | $70,969 | 9% | $19,628 | 2% | $90,598 | 11% | $722,521 |
| Admin | $132,026 | $5,541 | 4% | $12,354 | 9% | $19,628 | 15% | $31,982 | 24% | $119,672 |
| Marketing | $23,000 | $1,125 | 5% | $6,376 | 28% |  |  | $6,376 | 28% | $16,624 |
| DI | $604,675 | $11,985 | 2% | $52,239 | 9% |  |  | $52,239 | 9% | $552,436 |
| EM&V | $33,789 |  |  |  |  |  |  |  |  | $33,789 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

The partnership agreement allows for an upfront payment to the SBCCOG to fund start-up costs.  Although the payment was made and recorded in the amount of $59,511, actual costs along with supporting documentation have not yet been provided to SCE.  At the time SCE receives this information, the costs will be reported in the supporting workbook.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Apr-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Conduct at least 12 sessions for businesses | 12 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 12 |
| Conduct at least 4 events for residential customers. | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 3 | 25% | 4 | 33% | 0 | 0% | 4 | 33% | 8 |
| Respond to every customer inquiry within 48 hours. |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |

  - Activities/Accomplishments

    - Administrative -

- SBCCOG/SCE/SCG Partnership Agreement executed.

- The Partners continue to plan the program and participate in program activities to facilitate joint decision making.  A partners meeting was held on April 2, 2004 at the South Bay Energy Savings Center (SBESC).

- SBESC purchased two desktop computers, one laptop computer and one color printer for use in the center.

- A Calendar of Events was created for the SBESC and posted on the SBESC Website.

- Several hundred Compact Fluorescent Lamps were co-branded (SBESC/SCE/SCG logos) for distribution at community events.

- Tracking forms were developed to capture participation and lessons learned from each event.

    - Marketing –

- The South Bay Cities Council of Governments (SBCCOG) brochure was redesigned to include information on the SBESC.

- The SBESC logo was finalized and approved.  The new logo is being used to co-brand marketing materials.

- SBESC staff met with the Chambers of Commerce and city contacts in the South Bay to discuss outreach opportunities for Energy Efficiency in the respective cities.

Outreach Activities

SBESC continues to experience a tremendous response to their efforts to educate South Bay constituents on energy efficiency:

- SBESC finalized efforts to outreach to the South Bay Hard-to-Reach (Spanish- speaking community) customers by exhibiting at the City of Hawthorne’s annual Children’s Safety Awareness Day.  SCE and SCG in-language energy efficiency materials will be distributed at the event.

- Efforts are being made to reach out to the Council of Homeowners which is an umbrella group of Homeowners Associations.  Forty different Homeowners Associations will be present at an up-coming event.  SBESC aims to exhibit at the event and to conduct training presentations in home energy efficiency.

- Eleven of the sixteen South Bay Cities were contacted regarding linking of the SBESC website to each city’s website.

    - Direct Implementation

SBESC promoted the energy efficiency center at three Earth Day events during the month of April.  CFLs, Screen Sweeps and co-branded SCE and SCG marketing materials and energy efficiency information were distributed at all events.  In-language materials (Spanish and Chinese) were also distributed.  SBESC exhibited at:

- Women in Business Conference on April 16, 2004.  There were 700 attendees.  At least 45 individuals signed up for the SBESC e-newsletters.

- Sea Lab Earth Day Community event on April 17, 2004.  The event organizers estimated attendance at 2000.  Thirty eight (38) individuals signed up for the SBESC e-newsletters.

- Manhattan Beach Earth Day Community event on April 24, 2004.  There were approximately 1000 attendees.

- On April 24, 2004 City of Lawndale representatives facilitated the taping of a half-hour television show on energy efficiency which will be distributed to the cable networks that serve the South Bay cities.  SBESC Program Manager, SBCCOG Chairman and SCE Energy Efficiency Director represented the Utilities on the panel.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

The SBESC is working with other program providers to develop and present seminars and workshops in the South Bay.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed

- Additional Items

None