| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Small Nonresidential Hard to Reach Program - Procurement |
| Program Number: | 1453-04 |
| Month: | June 2005 |

- Program Status

Program Description

The Small Nonresidential Hard To Reach Program, also known as the Small Business Equipment Retrofit Program is designed to produce cost-effective, long term annual demand and energy savings by providing no-cost energy-efficient equipment retrofits to hard-to-reach small business customers in Southern California Edison’s (SCE) service territory.  This program will also provide training and jobs for individuals in economically disadvantaged areas.  The program will target underserved communities within SCE territory by coordinating with selected community based organizations (CBOs) and faith based organizations (FBOs) to package a customized program delivery plan that fits the specific needs of their communities thereby reducing market barriers to adoption of energy efficiency alternatives in these communities.  These organizations can leverage SCE’s portfolio of energy efficiency programs that effectively deliver long term energy and peak demand savings.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $5,119,455 | $16,243 | 0% | $260,108 | 5% | $818,098 | 16% | $1,078,206 | 21% | $4,859,347 |
| Admin | $79,352 | $2,314 | 3% | $46,120 | 58% |  |  | $46,120 | 58% | $33,232 |
| Marketing | $560,000 | $9,974 | 2% | $176,403 | 32% |  |  | $176,403 | 32% | $383,597 |
| DI | $4,360,649 | $2,386 | 0% | $29,956 | 1% | $818,098 | 19% | $848,054 | 19% | $4,330,693 |
| EM&V | $119,454 | $1,569 | 1% | $7,629 | 6% |  |  | $7,629 | 6% | $111,825 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jun-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 2,632 |  |  |  |  | 551 | 21% | 551 | 21% | 2,632 |
| Annual kWh | 13,386,197 |  |  |  |  | 2,598,869 | 19% | 2,598,869 | 19% | 13,386,197 |
| Lifecyc kWh | 211,845,235 |  |  |  |  | 41,397,681 | 20% | 41,397,681 | 20% | 211,845,235 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

    - Marketing -

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

80% of installations are very small business GS1 customers

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

No activities to date.

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

XXXXX, primary contractors have added additional staff to audit facities.

- Additional Items

XXXXX has been hired to do the pre-invoice inspections. Inspections have already commenced.