| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | VeSM Advantage Plus2 Program - Procurement |
| Program Number: | 1502-04 |
| Month: | April 2005 |

- Program Status

Program Description

The VeSM Advantage Plus2 program will improve manufacturing process efficiency by up to 25%, while improving energy efficiency per unit of output up to 10%, in conjunction with a 4-step approach designed to encourage energy efficiency, meet the needs of small to large size manufactures, and provide an economic boost to the region. VeSM Advantage Plus2 focuses on process improvements that first, improve energy efficiency and second, enhance productivity.  VeSM Advantage Plus2 will:

- Identify and quantify energy efficient process improvement solutions on the shop floor through a unique Value and Energy Stream Mapping assessment (VeSM)

- Implement one or more high-impact, lower-cost energy efficient process improvement solution(s) in an approximate range of savings from 100,000 to 180,000 annual kWh savings (Tier 1 Choices) in energy waste (per participating manufacturer) in accordance with a tailored contractual agreement.

- Lead to additional implementation of one or more high-impact, higher-cost energy efficiency process improvement solution(s) requiring additional incentive to align with acceptable customer payback; identify utility and non utility incentive programs that may lead to the improvements being installed.

- Conduct energy audits to identify additional facility – related energy efficiency opportunities inherent in manufacturing facilities, to encourage upgrading equipment such as lighting, HVAC and refrigeration.

VeSM Advantage Plus2 has improved upon “lean” manufacturing principals including “value stream mapping” (a floor map of the production process) by integrating “energy use” in a unique and first of its kind assessment tool called Value and Energy Stream Mapping (VeSM).

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $940,000 | $39,096 | 4% | $110,224 | 12% | $105,000 | 11% | $215,224 | 23% | $829,776 |
| Admin | $188,500 | $9,373 | 5% | $30,265 | 16% |  |  | $30,265 | 16% | $158,235 |
| Marketing | $115,500 | $15,685 | 14% | $41,840 | 36% |  |  | $41,840 | 36% | $73,660 |
| DI | $576,000 | $14,038 | 2% | $38,118 | 7% | $105,000 | 18% | $143,118 | 25% | $537,882 |
| EM&V | $60,000 |  |  |  |  |  |  |  |  | $60,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Apr-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 235 |  |  |  |  | 53 | 23% | 53 | 23% | 235 |
| Annual kWh | 2,822,400 |  |  |  |  | 638,400 | 23% | 638,400 | 23% | 2,822,400 |
| Lifecyc kWh | 56,448,000 |  |  |  |  | 12,768,000 | 23% | 12,768,000 | 23% | 56,448,000 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Apr-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency Referral Projects From 3 Eight Hour Workshops to 100 Manufacturing Companies | 3 | 1 | 33% | 3 | 100% | 0 | 0% | 3 | 100% | 0 |
| Value Energy Stream Mapping (VeSM) MNR | 12 | 0 | 0% | 0 | 0% | 4 | 33% | 4 | 33% | 12 |
| Value Energy Stream Mapping (VeSM) LNR | 12 | 0 | 0% | 0 | 0% | 2 | 16.6% | 2 | 16.6% | 12 |
| VeSM Advantage Plus Workshops to 15 Companies Per Event | 3 | 1 | 33% | 3 | 100% | 0 | 0% | 3 | 100% | 0 |

  - Activities/Accomplishments

    - Administrative -

- XXXXX has devised project management protocols to establish roles, assign responsibilities, and track progress.

- XXXXX is cultivating ongoing relationships with LAEDC, Inland Empire and Orange County EDC partners to market workshops and solicit Program Participants.

- Local representatives from the US Small Business Administration will also participate in customer recruitment and other activities.

- Six Direct Implementation contracts (4 Medium, 2 Large) are in place.

- A Purchase Order Change request has been approved for hiring a temporary research analyst to conduct benchmarking and other industry research

    - Marketing –

- The final Workshops has been completed for the Inland Empire (Ontario) Workshop, April 20, Ontario Airport Hilton, Ontario.

- The sales meeting target has been set at 8 per month to meet the goal of generating 4-5 proposals and 2-3 contracts per month.

- Key individuals in SCE’s Economic Development section have been briefed on the Program to engage them in customer recruiting.

- VeSM Team members have conducted one-on-one meetings to discuss the Program with  the following potential participants:

    - XXXXX, Azusa

    - XXXXX, Corona

    - XXXXX, San Bernardino

    - XXXXX, Ontario

    - XXXXX, Visalia

- Three of these meetings will result in project proposals being presented in May.

- Follow-up contacts with Workshop participants, screening of potential customers, and participant intake activities continue.

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

- XXXXX Kaizen events scheduled in June and July due to customer requests

- XXXXX first Kaizen to be documented – setup/changeover reduction of around 50% from 4 hours 15 minutes to 1 hours and  30 minutes

- XXXXX and XXXXX were scheduled for first AESC site visits

- Total Projects remains at six

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

- XXXXX has been selected as the EM&V contractor in April.  Subcontractor XXXXX will handle the energy profiling and savings analysis.

- A kick off meeting has been scheduled for June.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The VeSM Advantage Plus2 program was funded via a fundshift in the amount of $940k from the DI Incentives budget of the procurement-funded Savings By Design program.