**EXHIBIT G**

*Seller’s Milestone Schedule and Material Permits*

Seller’s Milestone Schedule

| *No.* | *Date* | *Milestones* |
| --- | --- | --- |
| 1 |  | Submits interconnection application. |
| 2 |  | Files any land applications. |
| 3 |  | Files Construction Permit application(s). |
| 4 |  | Files a CEC Pre-Certification application. |
| 5 |  | Files Material Permit applications. |
| 6 |  | Receives a completed System Impact Study or Phase I Interconnection Study. |
| 7 |  | Obtains control of all lands and rights-of-way comprising the Site. |
| 8 |  | Receives a completed interconnection Facility Study or Phase II Interconnection Study. |
| 9 |  | Executes an interconnection agreement and transmission/distribution service agreement, as applicable. |
| 10 |  | Receives FERC acceptance of interconnection agreement and transmission agreement. |
| 11 |  | Receives Construction Permit. |
| 12 |  | Receives Material Permits. |
| 13 |  | Receives CEC Pre-Certification. |
| 14 |  | Executes an Engineering, Procurement and Construction (“EPC”) contract. |
| 15 |  | Procures the *[applicable electrical generating equipment]* for the Generating Facility. |
| 16 |  | Completes financing, including construction financing. |
| 17 |  | Begins construction of the Generating Facility. |
| 18 |  | Begins startup activities. |
| 19 |  | Conference with SCE Contract Manager regarding startup activities *{SCE Comment:  Conference should occur no later than 150 days prior to the Commercial Operation Date.}* |
| 19 |  | Commercial Operation Date. |
| 20 |  | Demonstrates the Contract *Capacity [and Installed DC Rating] {SCE Note: For Solar Photovoltaic}*. |
| 21 |  | Receives CEC Certification. |

Seller’s Material Permits

| *No.* | *Permits* |
| --- | --- |
| 1 |  |
| 2 |  |
| 3 |  |
| 4 |  |
| 5 |  |
| 6 |  |
| 7 |  |
| 8 |  |
| 9 |  |
| 10 |  |
| 11 |  |
| 12 |  |
| 13 |  |
| 14 |  |
| 15 |  |

*\*\*\* End of EXHIBIT G \*\**