## Facility Status
782 | CALIFORNIA ENERGY COMMISSION - ENERGY FACILITY STATUS Updated 10/15/2008
Power Plant Projects Filed Since 1996, Updated: 12/4/2012 (Note: Does not include projects filed but were withdrawn before they were approved.)
Color Key
| Operational Status |  |  |  | Expected and disclosed
| Approved |  |  |  | Future project.
| In Review |  |  |  | On hold, suspended. According to developers, the new on-line date
| On-line date is expected to be delayed beyond the date shown |  |  |  | will be determined, or project review will continue when new info ia available.
| Not Approved/Denied |  |  |  | Cancelled, withdrawn, not built, license expired.
| Projects On Line (Arranged By Online Date) | Docket Number | Status | Capacity (MW) | Const. Completed (%) | Location | Date Approved | Const. Start Date | Original OnLine Date | Current / Actual Online Date
1a | Sunrise Simple Cycle - Texaco & Edison Mission E. | 1998-AFC-04 | Operational | 320 | 100 | Kern | 12/06/2000 | 12/07/2000 | 07/01 | 06/27/2001
2 | Sutter - Calpine | 1997-AFC-02 | Operational | 540 | 100 | Sutter | 04/14/1999 | 07/01/1999 | 07/01 | 07/02/2001
3 | Los Medanos - Calpine | 1998-AFC-01 | Operational | 555 | 100 | Contra Costa | 08/17/1999 | 09/17/1999 | 07/01 | 07/09/2001
4 | Wildflower Larkspur - Intergen | 2001-EP-01 | Operational | 90 | 100 | San Diego | 04/04/2001 | 04/05/2001 | 07/01 | 07/16/2001
5 | Wildflower Indigo - Intergen | 2001-EP-02 | Operational | 135 | 100 | Riverside | 04/04/2001 | 04/05/2001 | 07/01 | 09/10/2001
6 | Drews - Alliance | 2001-EP-05 | Operational | 40 | 100 | San Bernardino | 04/25/2001 | 04/26/2001 | 09/01 | 08/15/2001
7 | Hanford - GWF | 2001-EP-07 | Operational | 95 | 100 | Kings | 05/10/2001 | 05/11/2001 | 09/01 | 09/01/2001
8 | Century - Alliance | 2001-EP-04 | Operational | 40 | 100 | San Bernardino | 04/25/2001 | 04/26/2001 | 09/01 | 09/15/2001
9 | Escondido - Calpeak | 2001-EP-10 | Operational | 49.5 | 100 | San Diego | 06/06/2001 | 06/07/2001 | 09/01 | 09/30/2001
10 | Border - Calpeak | 2001-EP-14 | Operational | 49.5 | 100 | San Diego | 07/11/2001 | 07/12/2001 | 09/01 | 10/26/2001
| Subtotal On Line 2001 |  |  | 1914
11 | King City - Calpine | 2001-EP-06 | Operational | 50 | 100 | Monterey | 05/02/2001 | 05/03/2001 | 09/01 | 01/14/2002
12 | Gilroy I - Calpine | 2001-EP-08 | Operational | 135 | 100 | Santa Clara | 05/21/2001 | 05/22/2001 | 09/01 | 02/20/2002
13 | Delta - Calpine | 1998-AFC-03 | Operational | 887 | 100 | Contra Costa | 02/09/2000 | 04/01/2000 | 07/02 | 05/10/2002
14 | Henrietta Peaker - GWF | 2001-AFC-18 | Operational | 96 | 100 | Kings | 03/05/2002 | 03/08/2002 | 06/02 | 07/01/2002
15 | Moss Landing - L.S. Power | 1999-AFC-04 | Operational | 1060 | 100 | Monterey | 10/25/2000 | 11/28/2000 | 06/02 | 07/11/2002
16a | Huntington Beach Unit 3 - AES | 2000-AFC-13 | Operational | 225 | 100 | Orange | 05/10/2001 | 05/31/2001 | 11/01 | 07/31/2002
17 | Valero Cogen (Unit 1) - Valero | 2001-AFC-05 | Operational | 51 | 100 | Solano | 10/31/2001 | 11/05/2001 | 06/02 | 10/18/2002
| Subtotal On Line 2002 |  |  | 2504
18 | La Paloma - Complete Energy Holdings | 1998-AFC-02 | Operational | 1124 | 100 | Kern | 10/06/1999 | 01/01/2000 | 03/02 | 03/07/2003
19a | Los Esteros Simple Cycle - Calpine | 2001-AFC-12 | Operational | 180 | 100 | Santa Clara | 02/07/2002 | 07/08/2002 | 05/03 | 03/07/2003
19b | Los Esteros Simple Cycle recertification - Calpine | 2003-AFC-02 | Operational | 0 | 100 | Santa Clara | 03/16/2005 | 07/08/2002 | 05/03 | 03/07/2003
20 | High Desert - Constellation | 1997-AFC-01 | Operational | 830 | 100 | San Bernardino | 05/03/2000 | 05/01/2001 | 07/03 | 04/22/2003
21 | Tracy Peaker - GWF | 2001-AFC-16 | Operational | 169 | 100 | San Joaquin | 07/17/2002 | 07/22/2002 | 04/03 | 06/01/2003
1b | Sunrise Comb. Cycle Amendment - Texaco & Edison Mission E. | 1998-AFC-04C | Operational | 265 | 100 | Kern | 11/19/2001 | 12/21/2001 | 06/03 | 06/01/2003
22 | Woodland II - Modesto Irrigation District | 2001-SPPE-01 | Operational | 80 | 100 | Stanislaus | 09/19/2001 | 02/21/2002 | 05/03 | 06/06/2003
23 | Blythe I - NextEra Energy (FPL) | 1999-AFC-08 | Operational | 520 | 100 | Riverside | 03/21/2001 | 04/27/2001 | 04/03 | 07/15/2003
24 | Elk Hills - Sempra & Oxy | 1999-AFC-01 | Operational | 500 | 100 | Kern | 12/06/2000 | 06/08/2001 | 12/02 | 07/24/2003
16b | Huntington Beach Unit 4 - AES | 2000-AFC-13 | Operational | 225 | 100 | Orange | 05/10/2001 | 05/31/2001 | 11/01 | 08/07/2003
| Subtotal On Line 2003 |  |  | 3893
25 | Donald Von Raesfeld Power Plant (Pico) - Silicon Valley Power | 2002-AFC-03 | Operational | 147 | 100 | Santa Clara | 09/09/2003 | 09/10/2003 | 12/04 | 03/24/2005
26 | Pastoria - Calpine | 1999-AFC-07 | Operational | 750 | 100 | Kern | 12/20/2000 | 10/03/2001 | 01/03 | 07/05/2005
27 | Metcalf - Calpine | 1999-AFC-03 | Operational | 600 | 100 | Santa Clara | 09/24/2001 | 01/15/2002 | 07/03 | 05/27/2005
28 | Kings River - Kings River Cons. Dist. | 2003-SPPE-02 | Operational | 97 | 100 | Fresno | 05/19/2004 | 11/01/2004 | 05/05 | 09/19/2005
29 | Magnolia - So. Ca. Power Producers | 2001-AFC-06 | Operational | 328 | 100 | Los Angeles | 03/05/2003 | 07/21/2003 | 05/05 | 09/22/2005
30 | Malburg - City of Vernon | 2001-AFC-25 | Operational | 134 | 100 | Los Angeles | 05/20/2003 | 09/11/2003 | 11/05 | 10/17/2005
31a | Mountainview Unit 3 - SCE | 2000-AFC-02 | Operational | 528 | 100 | San Bernardino | 03/21/2001 | 09/01/2001 | 06/03 | 12/09/2005
| Subtotal On Line 2005 |  |  | 2584
31b | Mountainview Unit 4 - SCE | 2000-AFC-02 | Operational | 528 | 100 | San Bernardino | 03/21/2001 | 09/01/2001 | 06/03 | 01/19/2006
32 | Cosumnes - SMUD | 2001-AFC-19 | Operational | 500 | 100 | Sacramento | 09/09/2003 | 10/31/2003 | 06/05 | 02/24/2006
33 | Walnut - Turlock Irr. Dist. | 2002-AFC-04 | Operational | 250 | 100 | Stanislaus | 02/18/2004 | 03/15/2004 | 04/06 | 02/28/2006
34 | Palomar Escondido - SDG&E | 2001-AFC-24 | Operational | 546 | 100 | San Diego | 08/06/2003 | 06/01/2004 | 03/06 | 04/01/2006
35 | Riverside En. Res. Cntr. Units 1 & 2 - City of Riverside | 2004-SPPE-01 | Operational | 96 | 100 | Riverside | 12/15/2004 | 02/23/2005 | 11/05 | 06/01/2006
36 | Ripon - Modesto Irrigation Dist | 2003-SPPE-01 | Operational | 95 | 100 | San Joaquin | 02/04/2004 | 04/01/2005 | 04/05 | 06/21/2006
| Subtotal On Line 2006 |  |  | 2015
37 | Bottle Rock Geothermal Restart | 1979-AFC-4C | Operational | 55 | 100 | Lake | 12/13/2006 | 12/19/2006 | 06/07 | 10/01/2007
38 | Roseville Combined Cycle - Roseville Electric | 2003-AFC-01 | Operational | 160 | 100 | Placer | 04/13/2005 | 08/18/2005 | 12/07 | 11/07/2007
| Subtotal On Line 2007 |  |  | 215
39 | Niland Peaker - IID | 2006-SPPE-1 | Operational | 93 | 100 | Imperial | 2006-10-11 | 6/25/2007 | 06/08 | 05/29/2008
| Subtotal On Line 2008 |  |  | 93
40 | Gateway - PG&E | 2000-AFC-01 | Operational | 530 | 100 | Contra Costa | 5/30/2001 | 8/30/2001 Resumed: 2/2007 | 08/03 | 1/4/2009
41a | Inland Empire - GE (UNIT 1) | 2001-AFC-17 | Operational | 400 | 100 | Riverside | 12/17/2003 | 8/26/2005 | 12/05 | unit 1: 1/28/09 400 MW
42 | Starwood Midway - Starwood Power | 2006-AFC-10 | Operational | 120 | 100 | Fresno | 1/16/2008 | 9/23/2008 | 06/09 | 5/1/09
43 | EIF Panoche - Energy Investors Fund | 2006-AFC-5 | Operational | 400 | 100 | Fresno | 12/19/2007 | 2/15/2008 | 11/09 | 7/1/09
44 | Otay Mesa - Calpine | 1999-AFC-05 | Operational | 590 | 100 | San Diego | 4/18/2001 | Began: 9/10/01 Restart: 6/21/04 Resumed: 5/1/07 | 07/03 | 10/3/09
| Subtotal On Line 2009 |  |  | 2040
41b | Inland Empire - GE (UNIT 2) | 2001-AFC-17 | Operational | 400 | 100 | Riverside | 12/17/2003 | 8/26/2005 | 12/05 | unit 2: 5/3/2010 400 MW
45 | Orange Grove AFC - J Power USA | 2008-AFC-4 | Operational | 96 | 100 | San Diego | 4/8/2009 | 7/16/2009 | 12/10 | 5/1/10
| Blythe I Transmission Line - NextEra Energy (FPL) | 1999-AFC-8C | Operational | na | 100 | Riverside | 10/11/2006 | 2/23/2009 | 06/07 | 6/10
46 | Humboldt Power Plant - PG&E | 2006-AFC-7 | Operational | 163 | 100 | Humboldt | 9/24/2008 | 10/11/2008 | 9/09 | 2010-10-01
47 | Colusa II Generation Station - PG&E | 2006-AFC-9 | Operational | 660 | 100 | Colusa | 4/23/2008 | 7/28/2008 | 6/10 | 12/22/2010
| Subtotal On Line 2010 |  |  | 1319
48 | Riverside Energy Resource Center Units 3 & 4 - City of Riverside | 2008-SPPE-1 | Operational | 96 | 100 | Riverside | 2/25/2009 | 1/4/2010 | 1/10 | 2/7/2011
49 | Canyon Power Plant - City of Anaheim | 2007-AFC-9C | Operational | 200 | 100 | Orange | 3/17/2010 | 4/15/2010 | 7/2011 | 12/2011
| Subtotal On Line 2011 |  |  | 296
50 | Almond Peaker Power Plant Project - Turlock Irrigation District | 2009-AFC-2C | Operational | 174 | 100 | Stanislaus | 2010-12-15 | 3/1/2011 | 3/27/2012 | 7/13/2012
51 | Mariposa Peaker Project - Diamond Energy | 2009-AFC-3C | Operational | 200 | 100 | Alameda | 5/18/2011 | 6/8/2011 | 7/2012 | 10/2012
52 | El Centro Unit 3 Repower - IID | 2006-SPPE-2C | Operational | 128 | 100 | Imperial | 2007-01-03 | 9/2010 | 4/2012 | 10/2012
53 | Tracy Combined Cycle - GWF | 2008-AFC-7C | Operational | 145 | 100 | San Joaquin | 3/24/2010 | 1/10/2011 | 8/2012 | 11/1/2012
54 | Lodi Energy Center - NCPA | 2008-AFC-10C | Operational | 255 | 100 | San Joaquin | 4/21/2010 | 7/14/2010 | 6/2012 | 9/2012
| Subtotal On Line 2012 |  |  | 902
55 | Walnut Creek Peaker - Edison Mission E. | 2005-AFC-2C | Operational | 500 | 100 | Los Angeles | 2/27/2008 | 6/2011 | N/A | 5/1/2013
56 | Marsh Landing Generating Station | 2008-AFC-3C | Operational | 760 | 100 | Contra Costa | 8/25/2010 | 1/15/2010 | 6/2013 | 5/1/2013
57 | Sentinel Peaker - CPV | 2007-AFC-3C | Operational | 850 | 100 | Riverside | 12/1/2010 | 6/2011 | 8/2013 | 5/1/2013
| Subtotal On Line 2013 |  |  | 2110
|  |  | Emergency Peakers | 684
|  |  | Small Power Plant Exemption | 589
|  |  | Large Scale Power Plants | 18612
| ON-LINE TOTAL: In Operation |  |  | 19885
| With Testing Plants |  |  | 19885
| Approved and/or Under Construction (Arranged By Date Approved) | Docket Number | Status | Capacity (MW) | Const. Completed (%) | Location | Date Approved | Const. Start Date | Original OnLine Date | Current / Actual Online Date
1 | Los Esteros Combined Cycle - Calpine | 2003-AFC-2C | Under Construction | 140 | 94.4 | Santa Clara | 10/11/2006 | 5/26/2011 | N/A | 6/2013
2 | Russell City - Calpine & GE | 2001-AFC-7C | Under Construction | 600 | 90 | Alameda | 10/03/2007 | 9/1/2010 | 2013 | 7/2013
3 | El Segundo Power Redevelopment (Dry Cooling Amendment) | 2000-AFC-14C | Under Construction | 630 | 80 | Los Angeles | 2010-06-30 | 5/6/2011 | 8/2010 | 8/2013
4 | Abengoa Mojave Solar Project - Mojave Solar LLC | 2009-AFC-5C | Under Construction | 250 | 51 | San Bernardino | 9/8/2010 | N/A | N/A | N/A
5 | Blythe Solar - NextEra Blythe Energy Center LLC | 2009-AFC-6C | Under Construction | 1000 | Hold | Riverside | 9/15/2010 | 11/4/2010 | N/A | 2015
6 | Ivanpah Solar - Brightsource | 2007-AFC-5C | Under Construction | 370 | 95 | San Bernardino | 9/22/2010 | 10/2010 | 10/2012 - 2014 | 10/2012 - 2014 Phased
7 | Genesis Solar Energy Project - NextEra Energy | 2009-AFC-8C | Under Construction | 250 | 62.2 | Riverside | 9/29/2010 | 1/17/2011 | N/A | N/A
8 | Oakley Generating Station (formerly Contra Costa) | 2009-AFC-4C | Under Construction | 624 | 10 | Contra Costa | 5/18/2011 | 6/8/2011 | 2013 | 2016
9 | Santa Clara SC-1 Data Center, Phase 2 Xeres Ventures, LLC. | 2011-SPPE-1 | Under Construction | 36 | -- | Santa Clara | 3/28/2012 | N/A | N/A | N/A
|  | Approved (Large Solar) |  | 1870
| Approved and/or Under Construction Subtotal |  |  | 3900
| Approved and/or Under Pre-Construction (Arranged By Date Approved) | Docket Number | Status | Capacity (MW) | Pre-Const. Completed (%) | Location | Date Approved | Const. Start Date | Original OnLine Date | Current / Actual Online Date
1 | Victorville Hybrid Gas-Solar - City of Victorville (513 MW Gas + 50 MW solar) | 2007-AFC-1C | Pre- Construction | 563 | 0 | San Bernardino | 7/16/2008 | Extended to July 16, 2018 | 8/2010 | TBD
2 | Avenal Energy - Avenal Power Center, LLC | 2008-AFC-1C | Pre- Construction | 600 | Delayed | Kings | 12/16/2009 | TBD | 12/2011 | TBD
3 | Hanford Combined-Cycle Power Plant (Hanford Energy Peaker Project Expansion) - GWF Energy LLC | 2001-EP-7C | Pre- Construction | 25 | 0 | Kings | 3/24/2010 | TBD | 10/2012 | TBD
4 | Henrietta Peaker Project Combined Cycle Expansion - GWF Energy LLC | 2001-AFC-18C | Pre- Construction | 25 | 0 | Kings | 3/24/2010 | TBD | 10/2012 | TBD
5 | Beacon Solar Energy Project - Beacon Solar LLC | 2008-AFC-2C | Pre- Construction | 250 | Pending | Kern | 8/25/2010 | TBD | N/A | N/A
6 | Calico Solar - Calico Solar LLC (formerly SES Solar One LLC/Stirling Energy | 2008-AFC-13C | Pre- Construction | 663.5 | Hold/80 | San Bernardino | 10/28/2010 | TBD | N/A | N/A
7 | Rice Solar Energy Project - Rice Solar Energy LLC / SolarReserve LLC | 2009-AFC-10C | Pre- Construction | 150 | 90 | Riverside | 2010-12-15 | 3/2103 | N/A | N/A
8 | Palen - Nalep Solar Project I, LLC | 2009-AFC-7C | Pre- Construction | 500 | Delayed | Riverside | 2010-12-15 | 9/2010 | N/A | N/A
9 | Hybrid Gas-Solar - City of Palmdale (520 MW gas + 50 MW solar) | 2008-AFC-9C | Pre- Construction | 570 | Pending | Los Angeles | 8/10/2011 | TBD |  | 2013 | JB 1/3/2011
10 | Watson Cogeneration Steam and Electric Reliability Project | 2009-AFC-1C | Pre- Construction | 85 | 0 | Los Angeles | 4/11/2012 | TBD | TBD | TBD
11 | Carlsbad - NRG | 2007-AFC-6 | Pre- Construction | 558 | 0 | San Diego | 5/31/2012 | TBD |  | TBD
12 | Pio Pico Energy Center - Pio Pico Energy Center LLC | 2011-AFC-1C | Pre- Construction | 300 | 0 | San Diego | 9/12/2012 | 3/2013 |  | 5/2014
| Approved and/or Under Pre-Construction Subtotal |  |  | 4289.5
| Total Large Solar (Pre-Const and Const) |  |  | 3433.5
| Total Construction (Pre-Const and Const) |  |  | 8189.5
| Approved and On Hold - Not Under Construction (Arranged By Online Date) | Docket Number | Status | Capacity (MW) | Const. Completed (%) | Location | Date Approved | Const. Start Date | Original OnLine Date | Current / Actual Online Date
1 | Black Rock 1, 2, and 3 Geothermal Power Project (formerly Salton Sea Geothermal) - Cal Energy | 2002-AFC-02C | On Hold | 159 | 0 | Imperial | 12/17/2003 | Extension approved, Const. start 12/18/2014, On Hold: pending a power purchase agreement | 01/06 | On Hold
2 | Blythe II - Caithness | 2002-AFC-01C | On Hold | 520 | 0 | Riverside | 12/14/2005 | On Hold | On Hold | On Hold
| Approved and available for construction. |  |  | 679
A | Tesla - FPL | 2001-AFC-21C | Not Built and License Expired | 1120 | 0 | Alameda | 06/16/2004 | Cancelled | N/A | Not Built and License Expired
B | San Joaquin Valley - Calpine | 2001-AFC-22C | Not Built and License Expired | 1087 | 0 | Fresno | 01/14/2004 | Cancelled | 01/2006 | Not Built and License Expired
C | Three Mountain - Covanta | 1999-AFC-02C | Not Built and License Expired | 500 | 0 | Shasta | 05/16/2001 | Cancelled | 12/2003 | Not Built and License Expired
D | Western Midway Sunset - Edison Mission Energy | 1999-AFC-09C | Not Built and License Expired | 500 | 0 | Kern | 03/21/2001 | Cancelled | 07/2003 | Not Built and License Expired
E | United Golden Gate - El Paso | 2000-AFC-05C | Not Built and License Expired | 51 | 0 | San Mateo | 03/07/2001 | Cancelled | 07/2001 | Not Built and License Expired
F | Pegasus Energy - Delta Power | 2001-EP-09C | Cancelled | 181 | 0 | San Bernardino | 06/06/2001 | Cancelled | Cancelled | Cancelled
G | Chula Vista 2 - Ramco | 2001-EP-03C | Cancelled | 62 | 0 | San Diego | 06/13/2001 | Cancelled | Cancelled | Cancelled
H | Hanford Energy Park - GWF | 2000-SPPE-01C | Cancelled | 99 | 0 | Kings | 04/11/2001 | Cancelled | Cancelled | Cancelled
I | Valero Cogen (Unit 2) - Valero | 2001-AFC-05C | Not Built and License Expired | 51 | 37 | Solano | 10/31/2001 | 02/01/2007 | 12/2002 | Not Built and License Expired
J | SF Reliability Project - CCSF | 2004-AFC-01C | License Terminated | 145 | 0 | San Francisco | 10/03/2006 | Cancelled | Cancelled | License Terminated
K | East Altamont - Calpine | 2001-AFC-04C | License Teminated | 1100 | 0 | Alameda | 08/20/2003 | 8/11 | 07/05 | License Teminated
L | Imperial Valley Solar (Formerly SES Solar Two) - Imperial Valley Solar LLC | 2008-AFC-5C | License Teminated | 709 | 0 | Imperial | 9/29/2010 | N/A | N/A | License Teminated
M | Pastoria Simple Cycle Addition - Calpine | 2005-AFC-1C | Not Built and License Expired | 160 |  | Kern | 12/18/2006 | On Hold | 06/07 | Not Built and License Expired
N | Morro Bay - L.S. Power | 2000-AFC-12C | License Withdrawn | 1200 | 0 | San Luis Obispo | 08/02/2004 Note:Commission decision not finalized pending NPDS permit |  |  | License Withdrawn
| Total Cancelled or License Expired |  |  | 6965
| Not Under Construction Subtotal |  |  | 7644
| APPROVED TOTAL |  |  | 35718.5
| Projects Not Approved (Arranged By Decision Date) | Docket Number | Process | Capacity (MW) | Project Type | Location | Date Filed | Decision Date
| Eastshore - Tierra Energy | 2006-AFC-6 | 12-mon AFC | 116 | Brownfield | Alameda | 09/22/2006 | 10/08/2008
| MMC Chula Vista Replacement - MMC Energy, Inc. | 2007-AFC-4 | 12-mon AFC | 100 | Replacement | San Diego | 8/10/2007 | 6/17/2009
| AES High Grove Power Plant | 2006-AFC-2 | 12-mon AFC | 300 | Brownfield | San Bernardino Co. | 2006-05-25 | 2010-02-04
| NOT APPROVED TOTAL |  |  | 516
| Projects In Review (Arranged In Alphabetical Order) | Docket Number | Process | Capacity (MW) [Bracketed indicates large solar] | Project Type | Location | Date Filed | Estimated Decision Date |  | Original Estimated On-line Date
1 | Clean Hydrogen Power Project - BP ARCO & Edison Mission Energy | 2008-AFC-8A | 12-mon AFC | 390 | Brownfield | Kern | 7/31/2008 -------------- Revised AFC filed 5/28/2009 -------------- Amended AFC filed 5/2/2012 | TBD |  | 9/2017
2 | CPV Vaca-Station - Competitive Power Ventures Inc. | 2008-AFC-11 | 12-mon AFC | 660 | Greenfield | Solano | 11/18/2008 | On Hold |  | TBD
3 | Hidden Hills Solar Electric Generating System BrightSource Energy, Inc. | 2011-AFC-02 | 12-mon AFC | [500] | Greenfield | Inyo County | 2011-08-05 | 5/2013 |  | 2016
4 | Huntington Beach Energy Project | 2012-AFC-02 | 12-mon AFC | 939 | Brownfield | Orange | 6/27/2012 | 6/2013 |  | Unit 1 - 6/2018
5 | Quail Brush Generating Project Quail Brush Genco, LLC. | 2011-AFC-03 | 12-mon-AFC | 100 | Greenfield | San Diego Co. | 8/2011 | TBD |  | TBD
6 | Redondo Beach Repower - AES | 12-mon-AFC | 12-mon AFC | 496 | Brownfield | Los Angeles County | 11/19/2012 | 12/2013
7 | Rio Mesa Solar Electric Generating Facility BrightSource Energy | 2011-AFC-04 | 12-mon-AFC | [500] | Greenfield | Riverside Co. | 10/14/2011 | Suspended During Review |  | Suspended During Review
8 | San Gabriel - Reliant | 2007-AFC-02 | 12-mon AFC | [656] | Expansion | San Bernardino | 4/13/2007 | Suspended During Review |  | Suspended During Review
9 | Ridgecrest - | 2009-AFC-09 | 12-mon AFC | [250] | Greenfield | Kern | 9/1/09 | Suspended During Review |  | Suspended During Review
10 | Sun Valley Peaker - Edison Mission | 2005-AFC-03 | 12-mon AFC | 500 | Greenfield | Riverside | 12/01/2005 | Under Suspension Until 2014 |  | Under Suspension Until 2014
11 | Willow Pass - Mirant | 2008-AFC-06 | 12-mon AFC | 550 | Brownfield | Contra Costa | 6/30/2008 | ? |  | TBD
| UNDER REVIEW (No Lg Solar) |  |  | 3635
| Large-scale solar under review |  |  | 1906
| Under Review Total (excludes Suspended) |  |  | 4135
| Projects Anounced (Arranged by Project Name) | Process | Plant Type | Capacity (MW) | Project Type | Location | Estimated Filing Date
1 | Phoenix Combined Heat and Power | 12-mon-AFC | Natural Gas Cogen | 163 | Brownfield | San Bernardino County | April 2013
2 | Black Rock 5 & 6 Geothermal Power Project CE Butte Energy, LLC. | 12-mon-AFC | Geothermal Steam Turbine | 235 | Greenfield | Imperial County | TBD in 2013
| ANNOUNCED TOTAL |  |  | 398
| NOTES: |  |  |  | DEFINITIONS:
| Bold text in table identifies a change from the previous report. |  |  |  | Greenfield | Undeveloped
| * Estimated on-line date if construction is not delayed. |  |  |  | Brownfield | Developed site
| ** Estimated on-line date if approved & constructed as proposed. |  |  |  | Expansion | New unit at existing site, no loss of existing generation
| Projects in italics and an "EP" Docket Number are emergency peakers |  |  |  | Repower | Modification of existing equipment
| Megawatts in [ ] are not included in totals. |  |  |  | Replacement | Demolition of old plant and construction of new plant
| {1} 1021 MW replaced with 1200 MW for a net increase of 179 MW |  |  |  | On Hold | Applicant has suspended work
| {2} Project approved but replaced by Hanford-GWF (01-EP-7). |  |  |  | Suspended | Committee has suspended the proceeding
{3} 30 MW organic rankine cycle amendment approved 5/11/05.
{4} 130 MW amendment approved 6/22/05.