Community Energy Partnership:  Building on Success

The Southern California Flagship Model

Confirmation Number ____

Partner Cities

Irvine	Corona

Santa Monica	 San Bernardino

Moreno Valley	Cathedral City			Palm Desert	Monrovia

Brea	Tustin

West Hollywood	Santa Clarita

Partner Utility: Southern California Edison

Facilitating Partner: The Energy Coalition

This flagship proposal is accompanied by three complementary 2004-2005 Program Proposals, being submitted separately:

Community Energy Partnership: Natural Gas Efficiency in the Southern California Flagship Model

Community Energy Partnership – Northern California Model

Community Energy Partnership -- San Diego Pilot Program

Contact Information:

Ted Flanigan, Managing Director, The Energy Coalition

1540 South Coast Highway, Suite 204, Laguna Beach, California 92651

tflanigan@energycoalition.org, (949) 497-5110

Table of Contents

Executive Summary	3

Section l. Program Overview	5

Program Concept

Program Rationale

Program Objectives

Special Section: The Utility Partnership	9

Section ll. Program Process	11

Program Implementation

Marketing Plan

Customer Enrollment

Materials

Payment of Incentives

Staff and Subcontractor Responsibilities

Work Plan and Timeline for Program Implementation

Section lll. Customer Description	20

Customer Description

Customer Eligibility

Customer Complaint Resolution

Geographic Area

Section lV. Measure and Activity Descriptions	24

Types of Community Activities

Energy Savings Assumptions

Section V. Performance Goals	37

Section Vl. Evaluation Measurement and Verification	38

Section Vll. Qualifications	42

Section Vlll. Budget	44

Section lX. Summary	45

Section X. Attachments	47

Executive Summary

This Community Energy Partnership proposal for $7.34 million will fund an exciting collaboration of Southern California cities and utilities committed to delivering short- and long-term energy efficiency savings in California. The Partnership builds upon the strong foundation first created by The Energy Coalition, the cities of Irvine and Santa Monica and Southern California Edison in the Two Cities pilot program, whose success subsequently led to expansion into the Six Cities Energy Project. This proposal extends the Six Cities Energy Project in the original partner cities and expands the project to six additional cities. It is submitted by The Energy Coalition and Southern California Edison on behalf of Irvine, Santa Monica, Moreno Valley, Palm Desert, Brea, West Hollywood, Corona, Cathedral City, San Bernardino, Monrovia, Tustin, and Santa Clarita.

| Southern California |  |  |  |  |
| --- | --- | --- | --- | --- |
| Community Energy Partnership City Partners |  |  |  |  |
|  | City | County | Climate Zone | Population |
| Original Six Cities |  |  |  |  |
| 1 | Irvine | Orange | 8 | 142,000 |
| 2 | Santa Monica | Los Angeles | 8 | 125,000 |
| 3 | Moreno Valley | Riverside | 10 | 142,000 |
| 4 | Palm Desert | Riverside | 10 | 40,000 |
| 5 | Brea | Orange | 8 | 40,000 |
| 6 | West Hollywood | Los Angeles | 8 | 35,000 |
| Project Expansion Cities |  |  |  |  |
| 7 | Corona | Riverside | 10 | 138,000 |
| 8 | Cathedral City | Riverside | 10 | 43,000 |
| 9 | San Bernardino | San Bernardino | 10 | 185,000 |
| 10 | Monrovia | Los Angeles | 9 | 35,000 |
| 11 | Tustin | Orange | 8 | 60,000 |
| 12 | Santa Clarita | Los Angeles | 9 | 120,000 |
| Total |  |  |  | 1,105,000 |

Building a Model Approach

The partnership between the twelve partner cities, Southern California Edison, and The Energy Coalition presented herein has become the foundation for expanding the Community Energy Partnership approach statewide. It also represents the “flagship” of four complementary proposals that constitute the building blocks of a statewide model for the Community Energy Partnership approach for the delivery of efficiency services throughout California. The other proposals expand the Southern California Flagship Model statewide to six cities within the Pacific Gas & Electric service territory and two cities in San Diego County. The fourth proposal provides a partnership with The Gas Company to include gas efficiency services within the Community Energy Partnership for the first time. Because of the results achieved over the past five years of implementation experience, the partner utilities can rely on savings generated in the cities for their energy planning and resource procurement processes.

Tenets of the Community Energy Partnership

- Cities and their utilities work together to deliver customized efficiency programs in select neighborhood energy districts.

- “Hard-to-reach” communities of customers are targeted for highly valued services.

- The PEAK Student Energy Actions program is at the core of the community energy districts.

- Relationship marketing opens doors for existing utility programs to further improve their effectiveness.

- A resource efficiency ethic is created, renewed and supported in partner cities.

And the Southern California Partnership will deliver results to its citizens:

- Over 50,000 participants

- 16,000 PEAK students and their families

- 8,000 households; 600 businesses

With significant energy savings for the power system:

- 21.56 million net annual kilowatt hours

- 107.8 million net lifecycle kilowatt hours

- 12.3 megawatts of average capacity savings: 6.1 MW peak

Responsibility:  Instead of making energy the sole responsibility of the State, or the utility, the Community Energy Partnership turns the tables and gives ultimate responsibility for energy use to the citizens -- in fact, to “hard-to-reach” and traditionally underserved energy users. Through student programs, household energy tune-ups in low and fixed income homes, neighborhood community energy rallies where efficiency products are sold at discount, and a host of local community organizing activities, the Partnership raises awareness and sustains a focus on the community’s energy use.

At the same time, the Community Energy Partnership relies on its city partners leading by example, capitalizing on the numerous economic, environmental, and social benefits that energy efficiency provides to municipal facilities, schools, and small businesses.

Credibility: The cities that come together are diverse and powerful. As the Two Cities and Six Cities Energy Project partners have already demonstrated, they are poised to take action and to use their connections to the communities they serve to build viable initiatives. More importantly, their collective program designs and planning – facilitated by The Energy Coalition – stimulate a robust set of activities that “raise the flag” about the value of smart energy management. Building on each city’s good standing in its community and the support of their serving utility with its portfolio of programs, the Community Energy Partnership delivers “hard” savings while creating a long-lasting movement towards responsible resource use.

The Model: The Community Energy Partnership is a model for reaching heretofore neglected power consumers, such as seniors on fixed incomes. It has been developed conceptually for ten years and in practice for five. The Energy Coalition established the Regional Energy Efficiency Initiative with the cities of Irvine and Santa Monica and Southern California Edison (1999-2001). Based on the success of that model, these cities mentored four other cities (2002-2003). Now six cities, in partnership with the Coalition and SCE, are poised to mentor another six cities. The Coalition is also prepared to expand the model by developing a city cluster in Northern California and a pilot in San Diego.

The Potential: The Community Energy Partnership backs this proposal with five years of experience delivering measurable results in partner cities. Hard-to-reach customers are reaping the benefits of the program, creating a win-win with the State’s power system, economy, and environment. For utilities, doors are opening, and the Partnership seems primed to deliver its potential as an effective channel for utility programs to the hard-to-reach. Essentially, the partnership builds and then continually strengthens a bridge between city residents and their utilities. Meanwhile, households are “generating” hundreds of dollars of savings, schools are generating thousands, and the communities at large are experiencing savings in the millions. And the potential is huge when tapping these customer segments: 5,000 – 10,000 MW of capacity savings by the year 2010.

Section l. Program Overview

a. Program Concept

The Community Energy Partnership is a complementary delivery mechanism for energy efficiency that draws upon the unique strengths of a myriad of energy stakeholders to create a powerful synergy.  The partnership is multidimensional. On one hand it is between cities that are out to make a difference in the energy equation. Utilities can develop strong ties by working with active cities. It is about citizens and businesses working closely with community-based organizations to improve their financial condition. It is about dedicated school administrators, teachers, and students, working with their staffs and school districts to save precious resources. It is about hearing of a community event, and telling one’s neighbor. It is about creating Energy Champions in California cities.

The Community Energy Partnership model presented herein is nothing short of a movement. It involves people working together to foster responsible energy use and management in California cities. It involves leadership and tremendous levels of volunteerism.

The Community Energy Partnership

Statewide Model

The Southern California Flagship Program

Cluster #1: Six Cities

Cluster #2: Six Cities

The Northern California Partnership

Cluster #3: Six Cities

The San Diego Pilot Program

Cluster #4: Two Cities

With five years of experience under its belt, The Energy Coalition has learned how to effectively work with cities and their serving utilities to engage the public in changing the face of California's energy equation. This proposal will expand the Community Energy Partnership model to twelve cities in Southern California with an aggregate population of approximately a million people.

* The Community Energy Partnership has been recognized with prestigious awards. In 2001, the Two Cities Energy Project was named a winner of the Governor's Environmental and Economic Leadership Award. In 2002, PEAK Student Energy Actions was awarded a 2002 Flex Your Power Award.

In every community, the Community Energy Partnership model’s approach is two-fold:

Raise Awareness: The Community Energy Partnership is rooted in education of hard-to-reach customer segments. Without an understanding of why efficiency makes sense, people will watch measures come and go. PEAK Student Energy Actions lessons, Energy Rallies with guest speakers, Quizzes and Fact Sheets distributed through Tune-Ups -- all provide persistent explanations of the benefits of efficiency. The ultimate goal is to change the way people and businesses view and use energy.

Target Participants

PEAK Students

PEAK Households

PEAK School Districts

Municipal Leaders

Mobile Home Residents

Apartment Dwellers

Community Event Participants

Homeowners in Multifamily Settings

Small Business Owners

Create Immediate Savings: The project also delivers a stream of immediate, "hard" savings through product distributions and installations. The aspect is particularly valued by low-income participants.

*  Two months after she'd completed an in-home Tune-Up in a rent-controlled building in Santa Monica, one of our contractors received a call.  "Gaby, before you came, my bill was $66," said the senior resident.  "And since the Tune-Up, it is only $46.  I just wanted to call and thank you."

b. Program Rationale

There is a strong rationale for expanding the Community Energy Partnership.

New Delivery Channel:  The Community Energy Partnership is a successful model approach for the delivery of efficiency services to hard-to-reach customers, presenting the State of California – as well as its four major investor-owned utilities – with a promising complement to current statewide efficiency programs.

Capacity Potential: The Community Energy Partnership model, ready to be tested in each major utility service territory in the State, also has huge ramifications to the State’s power system. If fully flexed on the electricity side, it has the potential to deliver 5,000 – 10,000 MW of capacity to the State from end-users heretofore largely disregarded as sources of “negawatts” or dispatchable capacity.

Running with the Ball! Currently all six cities in the project are eager to extend their initiatives. The cluster of cities is working well, the program designs are effective, the Coalition has built a solid track record of implementation experience and infrastructure but the success – albeit on track with project targets – is akin to the tip of the iceberg. Can it be replicated and maintain its high levels of enthusiasm and results? We are eager to prove that it can, and are joined by cities and citizens ready to “take the controls” of their current energy use and energy future.

Program Designation: Hardware / Incentive Program

1. The Community Energy Partnership is a hybrid model approach that incorporates both information and incentives to increase energy efficiency within California cities. Its primary focus is community organizing which is inherently an informational type of activity, but a unique feature of the program is that it couples organizing with potent efficiency demonstrations and other forms of community efficiency promotions.

2. The Commission requires that we present a recommendation as to the designation of the program as either a “hardware / incentive program,” or an “information program.” While we are uncomfortable with these distinctions, we herein classify the Community Energy Partnership as a “hardware / incentive program” because it was previously approved by the Commission under that designation. We also believe that the approach is generating real and sustainable savings.

3. We caution that the preliminary savings estimates presented in the narrative proposal and accompanying workbook are just that: They are preliminary savings estimates that have yet to be qualified as bona fide savings. The Energy Coalition’s current 2002-2003 third party initiative – the Six Cities Energy Project – was filed as a hardware/incentive program, but at this time its results have not been fully evaluated. In fact, given the nature of the program, the proof of savings that stem from behavioral change will not be forthcoming for a number of years.

c. Program Objectives

The Community Energy Partnership proposed has three main objectives:

Delivering Value in Partner Cities: The first program objective is to deliver real value to program participants and their cities. The project focuses on power consumers most in need, who tend to be the most disenfranchised by utility services. Many of these consumers don’t speak English; some are home-bound. At the city level, school districts and cities themselves are financially “against the wall” and thus get tremendous benefit from efficiency savings.

Sustaining Hard-Earned Successes: A second objective is to sustain hard-won program victories from the prior programs in Southern California. A knowledgeable program management team is in place at the Coalition, with unique experience in designing and launching community-based programs. The Partnership model’s foundation is firm and additional work can be done expeditiously and more cost-effectively.

Enhancing the Delivery Approach: The third objective is to enhance the program design and bring ever-greater benefit to the communities involved. In 2004-2005, the program will be enhanced by:

- Incorporating natural gas-savings measures.

- Featuring more sophisticated community outreach.

- Adding the promotion of existing statewide and local utility programs.

- Involving dedicated utility Energy Managers, as described below.

Special Section:  The Utility Partnership

This proposal represents the next step in the evolution of the model first pioneered by the Coalition, Southern California Edison and the cities of Santa Monica and Irvine, and presents a proven partnership of cities currently engaged with the Coalition. Now this highly effective partnership will be strengthened by close links with both electric and gas utilities that serve each city. The model will now find the optimal synergy between utility programs and the Community Energy Partnership third party initiative. And it represents an investment of resources and time by the partners. The Partnership is the beginning of an ongoing stewardship of natural resources, local and state economies, and the global environment.

The utility partnership model presented here accomplishes several objectives:

- The utility partnership will maximize societal benefit by helping residents and businesses in the partner cities take full advantage of utility services.

- Fully utilizing utility programs will avoid duplication, stretching program dollars and allowing The Energy Coalition to dig deeper with special offers in the partner cities.

- Cities will enhance their relationships with the utility to create an explicit dialogue between consumer needs and utility services.

- The utilities will get a first-hand opportunity to fully utilize this form of community organizing and complementary delivery mechanism.

Background

The Energy Coalition and Southern California Edison have a long and successful history of working in partnership for the benefit of the customers we serve. In fact, the Coalition was formed over 20 years ago to form “Energy Cooperatives” that effectively brought the capacity savings of large commercial and industrial customers to Edison. In 1999-2001, The Energy Coalition was the managing partner of the Two Cities Project, a working partnership with Edison and the cities of Irvine and Santa Monica.  The success of that visionary model was the first step in the evolutionary process that brings us to where we are today.

Because of constraints brought about by the CPUC’s formerly-adopted process for considering third-party programs, the Coalition submitted the Six Cities Energy Projectas a third party initiative, which was selected by the CPUC as a local cross-cutting program for 2002-2003. As such, it has been contractually restricted in the ways that it may partner with Edison, and this has created less than "seamless" program delivery.  However, the Energy Coalition and Southern California Edison are both very encouraged that the Commission invited partnership proposals for 2004-05 and this program proposal marks a return to our long-standing collaborative working relationship.

Working closely with the local utility provides the opportunity for a stronger, more comprehensive program. In this partnership, The Energy Coalition is pleased that all parties agree to adhering to the current working model and to maintaining high degrees of flexibility and creativity. There is much work to do in the development and focus needed to bring the Partnership process to fruition. The Energy Coalition understands the need for changing perceptions of end-users and integrating community interest and initiatives with utility resources to forge a sustainable energy partnership that serves the end-user, the utility, and the State of California.

For the 2004-2005 program years, the Community Energy Partnership will take the best of both worlds. The Partnership will be built without stripping away any program integrity or its flexibility to deliver results. The successful model program will continue to be fully managed by a partnership between the cities, Southern California Edison and the Coalition, while building in the synergy of utility programs. In this format, program dollars can be judiciously applied to activities that complement existing utility offerings.

Project Centers

The Community Energy Partnership is a hands-on approach to energy efficiency program delivery. We’ve learned that we need more, not less, staff regularly in the cities to build a program reputation to sustain enthusiasm and deliver ongoing results. To effectively organize communities, “real people, on the ground” have to be pushing for and planning events and program strategies. The 2004-2005 program features Project Centers that add personnel to the project on a per-city basis, and more importantly provide a local presence and become the physical manifestations of the Partnership.

A Project Center will be established for each six city cluster. These centers will keep the project management local and “in touch,” a key element of past program success. They also address the considerable logistics associated with the project management. Ideally, a project city will house the Project Center within its facilities. At each center there will partner staff offices, a conference room, and ample storage for project materials.

Project Energy Staff: Each of the two Project Centers will have a staff that reflects the spirit and value of the Partnership. The core project management staff of four full-time equivalent staff at the Center will be made up of Coalition, Edison, and Gas Company personnel, working shoulder-to-shoulder with city Team Leaders, their staff, and volunteers. The Centers, as well as all Partnership activities in the cities, will be supervised by senior management at The Energy Coalition.

Project Center Staff Composition

- Project Manager (full-time Coalition employee)

- Project Manager (full-time Coalition employee)

- Office Manager (full-time Coalition employee)

- Partnership Energy Manager (0.5 FTE Edison employee)

- Partnership Energy Manager (0.5 FTE Gas Company)

Edison Dedicated Staff Position: To increase the project’s linkage to existing electric efficiency programs and services, a full-time Southern California Edison professional will be dedicated to the project. This professional will split time between Project Centers. The Energy Managers will also take back customer feedback and program lessons from the Community Energy Partnership to the respective utilities to bring to bear during the statewide and local program planning process.

Executive Guidance

One of the hallmarks of the successful Two Cities pilot project was its use of an Executive Committee, made up of leadership representatives from the cities, the Coalition, and SCE, to provide guidance for the project team and to pre-approve activities and expenditures. The success of that project as a stepping stone to where we are today has demonstrated the value of having a project Executive Committee. So, as in the past, the Executive Committee for this program will be made up of officials from the cities, Edison, and the Coalition. Committee members will set strategic direction, guide work plans and approve the budget based on forecasts of quarterly expenditures. Through the Executive Committee, Edison, the Coalition and the cities all become partners at the policy level.

Section ll. Program Process

a. Program Implementation

The Community Energy Partnership works within communities to deliver sustainable energy efficiency. In the broadest terms, this is done by raising awareness, fostering trust, and creating networks of understanding of the win-win benefits that efficiency affords for communities’ collective best interests. The Coalition has repeatedly found that “hard-to-reach” citizens and businesses -- from students to seniors -- are far from reluctant to engage in community activities. Rather, they are pleased to have a means to “plug in” and are eager to reap the benefits of energy efficiency.

Working with Cities

The Community Energy Partnership process features revolutionary principles.

Focusing on Energy Districts: The Community Energy Partnership is unique in its targeted delivery of energy efficiency services. It focuses its services in select geographical “Energy Districts.” Within each of these districts, a critical mass of activity takes place to raise program awareness and visibility.

Tailoring Initiatives to City Needs: In each city and energy district, the Community Energy Partnership captures unique needs and interests and builds a stream of customized programs. Like ripples from rocks falling in a pool of water, the consequences of these initial projects converge in a way never before experienced by the classically underserved utility customers.

*  During the planning process for an Energy Rally at The Groves, a mobile home park in Irvine, members of the committee reported concerns within the park about water quality and water use. The Energy Coalition promptly contacted colleagues at Irvine Ranch Water District to engage their participation in the Rally.

City Role in the Process:  Through a collaborative process of relevant stakeholders within the city, the Partnership first identifies potential projects and energy districts. Here the discussion is broad and unrestricted. What are each city’s objectives in energy management? How can the city’s energy plan be updated to reflect the current needs of its constituents? Which neighborhoods are in greatest need? Which have the greatest potential to save energy, support the local economy, and preserve the environment? How can the Community Energy Partnership help the city achieve these goals? What project, state, federal, and other resources can be tapped? What resources does the serving utility – in this case Edison -- bring to the table?

The Strategic Build-Out of Initiatives: A strategic plan is then developed for the delivery of services to target participants in each city. The approach flourishes with community input. And it is grounded in incremental and sequential developments. Whichever initiatives are begun must effectively set the stage for the next. And it is this multiplicative effect that provides the basis for the synergy of results that leads to high levels of participation and penetration. This build out of activity is at the root of the Community Energy Partnership process.

*  The City of Palm Desert assigned a new employee to serve as team leader for the Six Cities Energy Project. Within a month, the City had begun on its first energy plan. Within six months, the City's planned new Visitor's Information Center took center stage at a design charrette focused on efficiency and green building standards. Just last month, the Team Leader was invited to participate in a conference being held by a national retailer preparing to move to Palm Desert and wanting to train all its people in more energy-efficient building methods.

Leveraging Funds: The process works to leverage its funds. The Community Energy Partnership is a channel for utility services to the partner cities and their hardest to reach citizens. The Community Energy Partnership also provides key linkages to Southern California Edison programs, Gas Company programs, water efficiency opportunities, and community development and small business services. Project funds are judiciously expended where other funding is not available and are used to strategically raise awareness through demonstrations and outreach.

###### Community Involvement: Community education touches the community at all levels.  Program participants include:

###### Senior Centers

###### Apartment Complexes

###### Mobile Home Parks

###### Neighborhood Associations

###### Community Centers

###### Homeowners Associations

###### Parks and Recreation Departments

###### Community Libraries

School Classes and Sports Teams

Senior Retirement Communities

Fire and Police Departments

Small Business Groups

Chambers of Commerce

Boy and Girl Scouts

Service Clubs (Rotary, Kiwanis)

College Fraternities and Sororities

Private Businesses

Government Agencies

Like the partnership approach itself, the process of organizing communities to take greater responsibility for their energy use and management is also multidimensional. It involves building relationships with city governments, and with their constituents. It also necessarily involves bringing in all manner of relevant stakeholders into the process. For the program to succeed, it taps volunteers and the commitment of countless individuals to save energy and money and the environment. Partnership activities involve hundreds and thousands of individuals.

*  Moreno Valley's Torchiere Trade-In drew an estimated 2,000 participants from the community. Most were there to trade in their lamps, but more than fifty people came as volunteers to support the activity. The City donated its parking lot and waste management services to deliver and pick up dumpsters. Police Explorers directed traffic. Parks and Rec volunteers set up tents. And staffing "the line" were city employees, young people from the Youth Opportunity Center, Girl Scouts and their Scout Master, church members, optimists, and a variety of boyfriends, girlfriends and family members -- all there because they believed it to be a worthwhile way to spend their Saturday.

Working within the Community

Community Organizing: Community education and organizing is the basis of the approach. The Community Energy Partnership is all about educating entire communities so that they can take the controls of their own energy futures and craft sustainable paths for themselves and future generations.

Building Trust: The Community Energy Partnership model features repeated face-to-face interactions with citizens and their community leaders, coupled with the immediate gratification of short-term efficiency gains. This lays the foundation for long-term program sustainability. Through the Community Energy Partnership, trust is built and that leads to the development of a resource efficiency ethic that ultimately sustains efficiency gains.

PEAK at the Core: At the core of the Community Energy Partnership model is the PEAK Student Energy Actions program. No other project area is as profound; no other project focal point has the potential to create a “generational transformation of attitudes.” But there is no question of the enormity of the challenge of getting any program into a school district. It takes time, time, and more time.

PEAK is rooted in a comprehensive curriculum developed by The Energy Coalition and revitalized as part of the Two Cities pilot project, reinforced with special events such as contests, exchanges, summer programs, clubs, etc. PEAK students become empowered to save energy at home, at school, and in their communities. PEAK students gain a thorough understanding of the electricity story from power plant to end-use, and why smart energy management is critical to fostering a “healthy energy future.” Students also gain a special understanding of peak demand and its environmental, economic, and political dimensions. Students take compact fluorescent lamps (CFLs) home as symbols of the movement and to catalyze far more extensive household savings.

*  A student participating in a CFL fundraising sale for his school in Palm Desert reported that his father, after hearing about the importance of CFLs, decided to re-lamp his entire hotel -- some 2,100 lamps!  (In the end, the father was referred to Edison's Express Efficiency program for a better deal than he could get from his son, but the retrofit moved forward for the benefit of the hotel, city and State!)

Delivering Bundles of Valued Services: The Community Energy Partnership approach has proven to be an appealing model from a participant standpoint not only for its energy programs, but because it bundles services that until this time have been disparate and thus sporadically utilized. Project participants are exposed to “the bigger picture” of local, state and global energy resources, and they are presented with a variety of savings opportunities through electric, gas, and water utility programs and sustainable practices. Results are not delivered in isolation.

b. The Marketing Plan

The Community Energy Partnership presented herein involves seven customer segments or what we call project participants, and two focal areas, notably “community promotions” and “municipal activities.” Each of these end-use areas and programmatic activities requires its own marketing strategy and execution. By their very nature, community education activities take a number of forms and are cross-cutting in nature, requiring custom articles for community newsletters, video productions, press releases and video news releases, e-mail communications, printed materials for distribution to participants… all manner of communications appropriate to each audience.

Campaign Coordinator: To accomplish the multifaceted marketing function, The Energy Coalition depends on the skills of a Campaign Coordinator who is responsible for developing an overall marketing plan as well as detailed activity plans for each activity. Naturally this is also done on a city-by-city basis. Experience to date has made it clear that community organizing is not an engineering function, nor an economic argument, but about effective communications skills.

* When The Energy Coalition planned an Energy Rally for residents of a Section 8 retirement home in Irvine, it became clear that many would not come because they spoke only Farsi, Chinese, or Russian. Working with management, the Campaign Coordinator found "Champions" from within the community who went to each of their friends with explanations in their own language. In addition, the Coalition sent out letters to adult children of residents, urging them to be sure their parents came to the meeting. As a result, every one of the residents was able to receive not only a free fan and free CFLs, but also was able to sign up for special low-income energy and social programs.

The City Platform: The most profound form of marketing is marketing with substance, and this is explicitly why the city partners become engaged in the Partnership: They see value in the project and are happy to present it to their constituents. The cities “market” the project on their web sites, in newsletters, through special mailings, on their city television stations, in city council meetings, and in many other ways. This gives the project credibility and sets it apart from the pack.

* Partner city Moreno Valley has taken so enthusiastically to energy efficiency that it has created its own city program, PowerWise, complete with logo, website presence, and city TV spots. Similarly, Irvine created Irvine Saves!

Relationship Marketing: Experience to date has also shown that the success of the project is largely based on “relationship marketing,” whereby program participants tell their friends, families and neighbors about the Partnership. “My brother-in-law lives a few houses away. Can he participate as well?” Participants in the Tune-Ups become Energy Champions and program advocates. City staff members become ambassadors throughout the cities, and PEAK students turn up in lots of venues championing the program and its mission of creating a “healthy energy future through smart energy management.”  Appropriate marketing specialty items -- T-shirts, window decals, stickers, frisbees, etc. -- reinforce program messages.

Media Opportunities: The Community Energy Partnership is a colorful story and presents countless media opportunities. Taking advantage of these – aggressively working the media through press releases and repeated contacts – serves to build the “buzz” about the program and to continually reinforce the project. For example, the PEAK Energy Adventure was featured in the Irvine World News, and Community Efficiency Tune-Ups were featured in the Home section of the Riverside Press Enterprise as a unique Moreno Valley opportunity. The Coalition has learned is that success to date in the six cities has clearly been a function of persistence and diligent follow-up, coupled with healthy doses of coordinated publicity.

The Community Energy Partnership has evolved dramatically in the past five years, and is now poised for its most sophisticated implementation experience. For the 2004-2005 program years we plan significantly expanded marketing and outreach effort within the partner cities to further reinforce the meaning and presence of the Community Energy Partnership. Each city’s campaign will feature a combination of the following strategies:

- Promoting the message with targeted Energy Rallies with City Officials

- Accessing City TV and Public Access to reinforce the message

- Spreading program information through local and regional media (in multiple languages)

- Using PEAK students and schools to promote all project activities

- Running Student Forums on energy and the environment in local malls

- Using elected City Officials to facilitate Energy Town Halls

- Sending targeted direct mail to promote Energy Rallies and Tune-Ups

- Working with local organizations, from churches to Chambers of Commerce, to reach their members

- Working with the utilities on joint promotions

- Fully tapping the City web sites to promote energy management

- Linking project partners with statewide energy initiatives at the local level

c. Customer Enrollment

Participants enroll in the program in a number of ways. For instance, at community promotions participants sign in and purchase discounted products. In other cases, such as the PEAK Student Energy Actions program, enrollment is through the school district itself. For the Tune-Ups, enrollment takes a more conventional marketing approach with leads qualified and then participants scheduled by the installation contractors participating in the program.

d. Materials

Efficiency measures (lamps, fixtures, aerators, etc.) used as part of the Tune-Up programs are listed elsewhere. Other program materials fall into several categories.

Student educational materials:

- PEAK Curriculum (lesson plans) -- provided for each teacher

- PEAK Software -- individual CD for each student

- PEAK supply kit -- for each classroom

- Light and Amp Logger kits -- for PEAK Energy Clubs

- CFLs -- for each student

- Take-home materials for parents

Educational materials for consumers and businesses:

- Household Tune-Up Checklist

- Household Efficiency Recommendations Fact Sheets

- Small Business Efficiency Tune-Up Checklist

- Small Business leave behind ("Big Ideas for Small Business")

- "What's Your Energy I.Q.?" --  Quiz for use at fairs and meetings

- "Quick Check: Rate Your Home on Energy Efficiency" -- for classes

- CFL and Torchiere Fact Sheets -- as "receipts" at sales or exchanges

Promotional material for events:

- Partnership brochure -- basic marketing tool

- Customized flyers -- for local mobile home parks, apartment complexes, etc.

- Ads -- for local and city newspapers

- Project banner

- Audio-visual materials for public meetings (slide show, posters, etc.)

- Private-label CFLs (boxes)

- "Door hangers" for Community Efficiency Tune-Ups

- Stickers, imprinted pens, frisbees, etc.

Program management materials:

- IMPACT -- quarterly newsletter

- Quarterly status reports -- for each participating city

- Team Leaders Bulletins

- Powerpoint presentations -- for city and Coalition staff use

- Tune-Ups Database – to track installation details

- Press releases and press kits

- Website

e. Payment of Incentives

The Community Energy Partnership delivers customized products and services to its various audiences. Any "incentive" payments are not of the typical rebate variety.

| 1. PEAK Students | All students receive a free CFL as a symbol of the program and catalyst for further action. Schools are encouraged to run art contests, for which the Partnership provides appropriate recognition items and prizes. In some schools, parent-teacher organizations help sponsor CFL sales as fundraisers for their school programs. In this case, the Partnership provides CFLs at cost or at a discount. |
| --- | --- |
| 2. PEAK Households | Households receive no direct products or services other than the single CFL brought home by the student. |
| 3. PEAK School Districts | $20,000 of Partnership funds is allocated for each school district to spend on Partnership-approved products or services. This could include technical assessments, marginal costs for higher-efficiency equipment, etc. |
| 4. Municipal Activities | $20,000 of Partnership funds is allocated for each city to spend on Partnership-approved activities or products. This could include consultants to write the city's energy plan, technical assessments, a design charrette, marginal costs for higher-efficiency equipment, etc. |
| 5. Community Promotions | Generally, educational materials and efficiency measures are provided to consumers at a significant discount, or at no cost. The Partnership may work with a specific organization to mount an energy efficiency promotion that serves as a fundraiser for the group. For city-wide events, the Partnership may pay for commercial advertising, booth rental space, etc. |
| 6. Mobile Home, Rental and Owner-Occupied Multi- Family complexes | Energy Rallies bring residents together to educate them and to kick-off in-home Community Efficiency Tune-Ups. In addition to the measures associated with the Tune-Up, the Partnership may provide advertising flyers and refreshments for residents attending the Rally. |
| 7. Small Businesses | In addition to Small Business Efficiency Tune-Ups, the Partnership will support community events and advertising to promote its Small Business "Energy Champions." |

f. Staff and Subcontractor Responsibilities

This unique project requires flexible staffing. Full-time Partnership staff is dedicated to comprehensive project management and to managing staff in the project centers. To sustain its cost-effectiveness, the Partnership hires subcontractors and temporary workers on an as-needed basis.

g. Work Plan and Timeline for Program Implementation

The program is managed by quarters. The basic work plan and timeline is as follows:

First Quarter 2004

- Coalition briefs City Councils

- Memoranda of Understanding signed by City Manager

- Convene first Team Leaders meeting

- Hold kick-off program with statewide event

- Conduct meetings with school districts

- Develop Executive Committee; schedule first meeting

Second Quarter 2004

- Executive Committee meeting

- Select and visit Energy Districts

- Develop city-specific plans

- Hold individual city kick-off events

- Execute PEAK Student Energy Artwork contest

- Develop the EM&V Plan

- Select and train contractors for Tune-Ups

Third Quarter 2004

- Hold first city-wide Community Promotions

- Schedule special Energy District activities

- Market Community Efficiency Tune-Up programs

- Market Small Business Efficiency Tune-Ups

Fourth Quarter 2004

- Executive Committee meeting

- Deliver Community Efficiency Tune-Ups

- Deliver Small Business Efficiency Tune-Ups

- Continue with city-wide events

- Hold PEAK teacher training in new districts

- Conduct mid-point project evaluation

First Quarter 2005

- Address City Councils with mid-course update

- Maintain momentum with neighborhood Tune-Ups

- Hold special events as appropriate

Second Quarter 2005

- Executive Committee meeting

- Plan broad-based public relations effort based on results to date

- Schedule phase two city-wide events

- Laud PEAK Artwork contest winners at City Councils

Third Quarter 2005

- Complete Tune-Up activities

- Hold final city events

Fourth Quarter 2005

- Executive Committee meeting

- Make plans to support on-going activities in the cities

- Complete evaluation activities

First Quarter 2006

- Final Evaluation Report

- Publicize results

- Debriefing with project partners

Section lll. Customer Description

a.  Customer Description

The Community Energy Partnership focuses on the following nine areas with target participation numbers presented:

Focal Point	Participation Targets

1. PEAK Students	16,000

2. PEAK Households	12,000

3. PEAK School Districts	8

4. Municipal Activities	12

5. Community Promotions	16,000

6. Mobile Homes	2,400

7. Rental Apartments	2,400

8. Owner-Occupied Apartments	2,400

9. Small Businesses	600

Total Project Participants	51,828

Note that the total number of participants equates to approximately 5% of the aggregate population of the twelve cities. These participants become Energy Champions, multiplying the project’s effect throughout the cities involved. This speaks to the educational aspect of the program: In order to transform communities’ energy usages, and to make communities responsible for their energy consumption and energy future, participants must understand not just “how” to save energy, but “why” doing so has local, state, national, and even global ramifications.

1. PEAK Students: 16,000

The PEAK Student Energy Actions program will continue in the cities of Irvine, Palm Desert, and Santa Monica for the 2004-2005 program years. With the existing school districts currently on board, 6,000 students will be involved with PEAK over the two-year proposed program period. Assuming that PEAK is introduced in at least five additional cities during the program period, another 10,000 students will be exposed to the PEAK learning experience, for a total of 16,000 students.

2. PEAK Households: 12,000

The PEAK Student Energy Actions program teaches the cities’ youth an appreciation of how to manage energy consumption as well as how to manage the demand for electricity so as to clear up the “electricity traffic jam.” Armed with this awareness and knowledge of how to take action, and simulations of their homes’ optimal energy use, PEAK students take the message home. And that’s where the action begins as PEAK Students become “household energy managers.” Evaluations of the PEAK program reveal tremendous savings effects in student households.

* Quote from Santa Monica PEAK teacher: "We wouldn't hope for a repeat, but one of our students' homes burned down. As the parents rebuilt, they turned their new home into a demonstration project for energy efficiency, with efficient fluorescent lighting throughout, energy-efficient appliances, low-e windows, etc. -- all thanks to inspiration and knowledge they had received from their child through our program."

For the 2004-2005 program years, the Community Energy Partnership will engage approximately 12,000 PEAK households. Note that this participation is 75% of the number of PEAK students, reflecting the fact that often a household has more than one child in the program, and that some older students have already been through the program and thus their homes’ savings are not double counted. PEAK households, incidentally, cut across income brackets and represent an area where the Community Energy Partnership addresses single family homes.

3. PEAK School Districts: 8

During the 2004-2005 program years, The Energy Coalition will work with a total of 8 school districts to implement the PEAK Student Energy Actions program. Note that this includes the three districts already on board and committed to PEAK.

3 School Districts with Ongoing Programs

District	Number of Schools Involved

Irvine Unified School District	24

Santa Monica Malibu Unified School District	6

Palm Desert Unified School District	4

2 School Districts Primed for Pilot Programs

District	Number of Schools Involved

Moreno Valley Unified School District	3

Brea Olinda Unified School District	--

3 New School Districts Yet To Be Identified

4. Municipal Activities: 12 Cities

To be effective in their communities, partner cities must be actively involved in getting their own houses in order. The Community Energy Partnership promotes a number of planning and management functions for the City itself to become a model energy consumer and a champion of smart energy management over time. The Community Energy Partnership requires its partner to be actively engaged in the smart energy management of its own facilities. Therefore, in terms of participation, all 12 partner cities will be involved.

5. Community Promotions: 16,000 Participants

Community organizing takes many forms and unexpected directions and involves all types of participants. To get students, households, and businesses “fired up” about the potentials for energy efficiency, the Community Energy Partnership hosts a variety of special events. Community Energy Rallies often use discounted product and face-to-face interaction on the benefits of efficiency. These promotions are generally held within the Energy Districts defined by the partner cities and serve to support participation in subsequent initiatives such as Community Efficiency Tune-Ups and Small Business Efficiency Tune-Ups.

* "Hard-to-reach” energy consumers tend to live in mobile homes, rental apartments and owner-occupied apartments. These consumers are identified by the respective cities and then become the focus of the Community Efficiency Tune-Ups. In turn, these customers become Energy Champions within their communities.

6. Mobile Homes: 2,400

The Community Energy Partnership has an impressive track record of working with mobile home communities. Often occupied by seniors on fixed incomes, these communities are specifically included in the Energy Districts by the partner cities and become focal points for Energy Rallies and Community Efficiency Tune-Ups.  Partnership activities are often specifically designed to bring low-income-qualified utility and social services into these communities.

7. Rental Apartments: 2,400

Rental apartments are fundamental to the Community Energy Partnership. They are often occupied by low-income consumers in need of lower utility bills as well as increased comfort and safety. The project brings Tune-Ups to this customer segment as well as Energy Rallies and other forms of special events. In many cases, programs must take into consideration those residents whose English language skills are limited.

8. Owner-Occupied Apartments: 2,400

Owner-occupied apartments in the select Energy Districts are also a target for the program. These owners are often among the most highly motivated to understand and make changes in their energy use, and they often use Community Energy Partnership resources as a springboard to other energy-saving activities. The project goal is to reach 2,400 such units in the 2004-2005 program years through Tune-Ups as well as Energy Rallies and other special events.

* In the city of Santa Monica, The Energy Coalition has appeared on stage and exchanged leads with another city-supported non-profit organization, Sustainable Works, whose 8-week-long self-help educational programs focus on a variety of conservation topics.

9. Small Businesses: 600

The Community Energy Partnership also focuses on local small businesses that often form the fabric of the community. Small Business Tune-Ups address lighting, air handling, and refrigeration efficiency opportunities head on, while checking into business owners’ unusual energy use and problem areas. Small Business Energy Champions will also serve as emissaries to colleagues and customers. During the 2004-2005 program years, the Community Energy Partnership will deliver 600 Small Business Efficiency Tune-Ups to small businesses in the twelve partner cities.

*  Small Business owners who participate in a Tune-Up become "Energy Champions." They receive a decal for their window and energy tips handouts for their customers, and appear before the city council or in city-wide advertising to promote energy awareness.

b. Customer Eligibility

Many Partnership activities -- Energy Rallies, Community Efficiency Tune-Ups -- are focused in discrete Energy Districts selected by the City. Other activities are specifically open to all residents of the City: Torchiere trade-ins are an example. Since the purpose of the program is to create widespread awareness, there is no intent or restriction to limit participation to low-income or otherwise income-qualified families, or to strict geographical limits. This position has allowed for marked increase in participation levels that in turn foster a successful project in the community.

c. Customer Complaint Resolution

The Community Energy Partnership works hard to sustain the best possible reputation, for without it, the program will fail. Fortunately, because the program is totally voluntary, and because most measures are offered or installed at little or no cost, complaints are rare. However, to maintain the highest quality of service, contractors working with the Partnership are selected and trained in all facets of installations -- and education -- that they provide. In addition, contractors are contractually required to support their work for one year through warranties. As an example, when citizens receive measures as part of a Partnership activity, they also receive the 800 number of the manufacturer or distributor.

*  Two weeks after the recent torchiere trade-in in Moreno Valley, the torchiere distributor arranged to return to the city hall parking lot where the trade-in had been held in order to resolve any problems people may have had with their lamps. This follow-up service was advertised to all participants.

*  No matter how well-prepared or well-intentioned the contractors, things can go wrong. After one mobile home Tune-Up in Brea, the air conditioner wouldn't turn on. On his own time and nickel, the contractor traced the problem to a faulty exterior cut-off switch and repaired it.

d.  Geographic Area

The Southern California Community Partnership extends to cities located within a one-two hour drive from Los Angeles. -- depending on traffic!

Section lV. Measure and Activity Descriptions

The Community Energy Partnership reflects the spirit of community organizing. It is about bringing people together who are empowered to make a difference and who are committed to creating a safe and healthy energy future. The power of the model is nothing short of fantastic: By bundling services, participants can realize hundreds of dollars of annual savings, schools can realize tens of thousands of dollars of savings, and cities can realize millions of dollars of savings. And when the model is built out, the potential savings for utilities and the State are huge.

To realize these potentials, the Community Energy Partnership works with a number of customer segments in a myriad of ways to raise awareness and get measures installed. This section presents a sector-by-sector description of the types of measures that result and the energy savings assumptions that have been used to substantiate the performance goals presented in the next section.

A specific objective of the project is to create sustainable savings by building an ethic and community responsibility. And there is no more important channel for this to develop than through the PEAK Student Energy Actions program.

# 1. PEAK Students

PEAK is a multifaceted program that involves classroom activities – both during the normal school year and as special features of summer school programs – as well as campus, household, and community activities.

Getting the Ball Rolling: The direct or “hard” savings from each PEAK student is minimal but key to triggering a far greater savings stream in PEAK schools and PEAK homes and ultimately PEAK communities. Every student (16,000) enrolled in the program is given a compact fluorescent lamp as a symbol of how energy-efficient technologies can leverage energy and dollar savings at home. Through the single CFL, a measure that will “generate” $50 of consumer savings, PEAK has catalyzed an impressive track record of home energy savings. According to SDG&E Fact Sheet titled “Little things can lead to big savings,” using CFLs will also reduce solid wastes as they last nine times as long as incandescent lamps: “Each year, the United States throws away 1.741 billion bulbs, enough to fill two Qualcomm Stadiums!” Each CFL also saves the equivalent of a 46-gallon barrel of oil.

CFL Fundraisers: An additional 10,000 CFLs will be sponsored through the Community Energy Partnership for school fundraising activities and to extend the reach of the student energy actions in school attendance districts. All told, 26,000 CFLs will be distributed through PEAK Students.

Savings Assumptions: The Energy Coalition will purchase 26,000 23-watt CFLs for the PEAK program. This wattage provides the equivalent light output of a 90-watt incandescent lamp. This was selected to assure that the CFLs are brighter than 75-watt lamps, more akin to the needs of our participants, and unquestionably bright enough to overcome perceptions of inferior technology and insufficient light. (All CFLs distributed are Energy Star rated as well.) Each lamp replacement results in a gross 67-watt savings.

For this cost effectiveness analysis, we assume that the CFLs will be used an average of 4.4 hours per day and that each one has an 8,000 hour operating life, for annual kWh usage of 107.2 kWh per year (about a $16 in annual consumer savings). As such, the 26,000 CFLs will result in annual electricity savings of 2,805,400 kWh, adjusted downward to account for the 0.8 net-to-gross ratio to 2,244,320 kWh.

Capacity savings: In terms of capacity, each CFL will save 67 watts for a total PEAK Student gross capacity savings of 1,742 kW and a net average capacity savings of 1,394 kW. Further, we assume a peak coincidence factor of 0.25 resulting in a net peak capacity contribution of 348 kWp.

# 2. PEAK Households

PEAK students become household energy managers, taking PEAK’s ethic of resource efficiency home and to their families. Their actions are multiple and diverse but focused on lighting, refrigeration, air conditioning, and water heating measures. By raising awareness within PEAK households through the kids, homes get “relamped” using fluorescent technology, new furnaces become high-e and noted to neighbors and extended family, windows and doors can get that much tighter, and clothes dryers now have sophisticated moisture sensors.

Savings actions – which in many cases feature their child’s newly learned information on smart energy management – are taken by parents voluntarily. We assume that each household will invest in some form of electrical and gas efficiency – be it behavioral or through the installation of a highly efficient appliance -- in the next five years as a result of PEAK. In many cases these actions will be supported by utility rebates, and the Community Energy Partnership serves only as a catalyst. The following is a list of energy-saving measures that accrue through this aspect of the Partnership:

Lighting Measures

- Exchange incandescent light bulbs for fluorescent bulbs

- Install energy-saving night lights, porch lights, safety lights

- Replace halogen torchiere lamps with fluorescent models

Household Electrical Appliances

- New high-efficiency refrigerators

- Refrigerator seals maintenance and repair

- Refrigerator compressor maintenance and repair

- Discard old refrigerator

- Install programmable thermostat

- Install ceiling fans

- Install solar swimming pool heating

- Behavioral:  Turn off, unplug unnecessary lights and appliances

Space Heating and Cooling Savings Measures

- Adjust thermostat

- New high-efficiency furnaces and air conditioning units

- Duct-work maintenance and repair

- Replace furnace and air conditioner filters

- Better household insulation

- Better windows, doors, and skylights

- Install window film, shades; plant shade trees

Water Heating Savings Measures

- Highly efficient clothes washers

- High-efficiency dish washers

- High-efficiency water heater installation

- Water heater insulation

- Hot water pipe insulation

- Water temperature check for optimal efficiency

- Behavioral: Use CW and DW only when full

- Install new high performance showerheads

- Install water-efficient faucet aerators

For the purposes of this proposal we assume that the 16,000 participating students will hail from 12,000 homes to account for families with multiple students in the current program and/or older students who have been engaged in the program and whose homes are already generating a savings stream from prior program participation.

Savings Assumptions: While electricity use varies dramatically among the twelve cities and the housing stocks represented in the Partnership, we assume that the average household consumes 500 kWh per month and thus 6,000 kWh annually. (Energy Information Administration 1997 data that shows that the average California household uses 6,087 kWh/year and 470 therms.) Furthermore, we assume that each participating student’s household realizes an average 10% energy savings (both gas and electric) largely through behavioral changes stimulated through student program activities. (Past program evaluations have revealed household savings as high as 15-30%.) Using the 10% value for estimated savings results in an average annual savings of 600 kWh for each of the 12,000 homes involved in the program.

Savings Estimates: The savings are projected to last an average of five years. Each PEAK family household is estimated to save 3,000 kWh as a result of its child’s participation – worth $450-500 per household over the ten-year timeframe. Each year, PEAK Households will realize gross savings of 3,600,000, adjusted to a net annual savings of 2,880,000 kWh.

Capacity savings: In terms of capacity savings for PEAK households, we assume 250 watts of gross capacity savings – equivalent to the installation of four CFLs -- and 200 net watts of average capacity savings. With 12,000 homes involved, this results in a total net capacity savings of 2,400 kW. For PEAK Households, we assign a 0.25 peak coincidence factor, disproportionately skewed to reflect the program’s demand emphasis, and realize 600 kWp.

Household Investment: We input a $100 per household average investment in energy management (for additional lights, Energy Star appliances, thermostats, shade trees, etc.) during the five years for the purposes of the cost-effectiveness calculations. Through the utility partnership each household will be introduced to Edison company rebates and program offers to reinforce this household action, resulting in additional savings not presented in this proposal.

*  The third major component of the PEAK software guides students in developing a customized "Household Energy Plan" listing and quantifying the benefits of the top 10 actions the family can take for further energy savings.

3. PEAK School Districts

Each school district participating in the PEAK Student Energy Actions program will benefit from energy savings stimulated by students’ actions along with those of their teachers and custodians as energy awareness is raised on campus. One private school that taught PEAK slashed its campus electricity bill by 30%; another school realized 15% savings despite considerable construction on campus.

Current works are in progress with both the Irvine Unified School District and the Santa Monica Malibu Unified School District to develop procedures for cutting individual campus energy use through both strategic energy assessments and mechanisms to address split incentives (as discussed below) to create district-wide savings.

PEAK Student Actions on Campus: The Energy Coalition and its partner cities work with PEAK schools in a number of ways, from policy guidance to engineering assistance. One of the most unique aspects of the partnership is the linkage between PEAK students and school facilities personnel.

*In Irvine, after school PEAK Energy Clubs made up of students go on patrol to find campus energy waste. Irvine Unified now has a goal – reinforced with large barometers of energy savings successes posted in the foyers of each school -- of saving 10% on each campus!

Technical Services: Another innovative approach developed over the past five program years has been PEAK Light and Amp Logger kits provided to participating districts. The kits are used by students and maintenance staffs to find wasted energy use, with data downloaded to computers on campus and then analyzed. This has led Irvine to realize that its “state-of-the-art” energy management system needs to be recommissioned. In Santa Monica, students armed with light meters found gross overlighting and developed strategies for cutting lighting intensity in classrooms.

Sample School District Opportunities

- Developing School District Energy Management Plans

- Supporting PEAK Student Energy Patrols

- Engineering Analyses of School Facilities

- Design Assistance for New Facilities

- Incentives for High Visibility Demonstration Project

- Incentives for Leading School Efforts

- Training for Students, Administrators, and Facility Operators

Policy Initiatives: The Community Energy Partnership works with school districts and their facilities staffs to eliminate the split incentive between school districts and individual schools. The Partnership will work with willing districts to enable individual schools to track their consumption. In some cases the Partnership will benchmark energy intensity and then track monthly consumption for significant variations that represent savings potentials.

Savings Assumptions: For the purposes of this proposal, we assume that each of the eight participating school districts will cut its overall use by an average of 5% for a five-year period. We assume that four of the eight target districts will be “large” and thus use 20,000,000 kWh per year; and that the other four are “small” and thus use 5,000,000 kWh each year. (Irvine Unified School District had a $3.5 million electric bill in FY 2002-2003 with 21 million kWh of use.)

Larger districts will realize gross savings of 500,000 kWh per year; smaller districts will save 125,000 kWh/year. Thus the average gross district electricity savings is 312,500 kWh. For the eight participating school districts gross annual savings are assumed to be 2,500,000 kWh, with net annual savings of 2,000,000 kWh.

Additional Savings in Existing Districts: Naturally the Community Energy Partnership is concerned about double counting of savings, and is fully cognizant that it is not going into “virgin territory” to reap savings in school districts and municipal facilities currently engaged in the Six Cities Energy Project. Nevertheless, for two reasons, we believe that the Community Energy Partnership will create additional savings in existing school districts and municipal facilities. First, additional project funds will be dedicated to both of these participant types to allow for additional and ever-more-sophisticated savings activities. Second, and based on the targets that the participants set for their own savings, we believe that the savings estimates used in the Six Cities Energy Project proposal were grossly conservative. Therefore, additional savings will be claimed in these sectors.

Capacity Savings: For large school districts we assume a baseline usage of 5 MW and a 10% capacity savings of 500 kW. This results in a net capacity savings of 400 kW per large district, and 1,600 kW for the four large school districts. For small school districts we assume a gross capacity savings of 125 kW, a net per-district capacity savings of 100 kW, and thus 400 kW for the four smaller school districts involved. Thus the net capacity savings for the project will be 2,000 kW. Assuming a 1.0 peak coincidence factor, the Community Energy Partnership will result in 2,000 kWp from participating districts.

School District Investment: It is assumed that each PEAK School District will match the Community Energy Partnership’s investment in its facilities during the five-year energy savings period. As input in the accompanying worksheet, the average school district investment is expected to be a minimum of $20,000.

# 4. Municipal Facilities

The Community Energy Partnership will work with municipal facilities to cut energy use throughout city government, notably in city halls, as well as community centers, libraries, police and fire stations, corporate yards, etc. For the 2004-2005 program years, the Community Energy Partnership has earmarked $20,000 per city to focus on municipal energy use and to work with public works officials and others on developing or revising each city’s energy plans with a focus on efficiency and sustainable energy management.

Energy-Saving Measures: Savings will be accomplished through a number of strategies including providing technical assistance, supporting consultants and staff to assess energy-savings opportunities, and by working with the cities to assure that they develop updated Strategic Energy Plans.

Sample Municipal Facility Opportunities

- Initial Employee Awareness-Raising Activities

- Developing City Energy Management Plans

- Engineering Analyses of Municipal Facilities

- Design Assistance for New Facilities

- Incentives for High Visibility Demonstration Project

- Incentives for Facility Operators

- Demand Responsiveness Opportunities

- Supporting Energy Advisors in City Government

Baseline Usage: For the purposes of this proposal and based on this focus, we assume that the Community Energy Partnership will stimulate average savings of 5% over a five-year period for municipal facilities. Like school districts, we designate “large” and “small” cities. For the six large partner cities with populations over 100,000 and skewed by the preponderance of partner cities in hot areas, we estimate annual electricity consumption of 10,000,000 kWh; for small cities we assume gross annual consumption of 5,000,000 kWh.

Savings Assumptions: For the purposes of estimated savings, we assume that the “average” partner city uses 7,500,000 kWh annually. Naturally, actual values vary dramatically depending on municipal water utilities, number of community centers and pools, hours of operation of libraries and other facilities, the age of the facilities, and again the city’s climate zone. Using the estimated savings value of 5% we assume gross savings of 375,000 kWh per year per city. In the case of municipalities that are extending their involvement with the Community Energy Partnership, we expect to gain an additive 5% in energy savings over a five-year period.

Projected Savings: The Community Energy Partnership will create gross annual electricity savings of 4,500,000 kWh in the twelve cities. Using the 0.8 net-to-gross value, this will result in 3,600,000 of annual kWh and 18,000,000 kWh over the five-year savings period.

Capacity Savings Assumptions: We assume that larger cities have an average capacity requirement of 2 MW for larger cities; 1 MW for smaller cities. Assuming a 10% capacity savings in each city, the project will result in 200 kW of capacity savings in large cities, and 100 kW in each small city, for a project total of 1,800 kW, and a net capacity savings of 1,440 kW. Assuming a peak coincidence factor of 1.0 results in a peak capacity savings of 1.44 MW. Note that in the hotter climate zone cities, the Community Energy Partnership will focus on the implementation of demand response strategies to realize capacity savings in key municipal facilities.

Partner City Investment: It is assumed that each partner city will match the Community Energy Partnership’s investment in its facilities during the five-year energy savings period. As input in the accompanying worksheet, the average city partner investment is expected to be a minimum of $20,000.

# 5. Community Promotions

For the 2004-2005 Southern California Flagship Model project, 16,000 participants are expected to participate in community promotions. While these events take many forms, the Community Energy Partnership will provide discounted lighting products – notably compact fluorescent lamps and fluorescent torchiere lamps – to these participants.

To develop a reasonable proxy value for the savings, the Community Energy Partnership expects to promote the installation of 24,000 CFLs to 12,000 participants, and 8,000 fluorescent torchiere lamps to 4,000 participants. In each case, the participant gets two products.

Compact Fluorescent Lamp Savings Assumptions: The Energy Coalition will purchase 24,000, 23-watt CFLs for the Community Promotions. Each lamp results in a 67-watt savings that results in 536 kWh over its 8,000 life.  The CFLs will be in place for 5 years and have an 8,000 hour operating life, for annual kWh usage of 107.2 kWh per year. As such, the 24,000 CFLs will result in annual electricity savings of 2,572,800 kWh, adjusted downward to account for the 0.8 net-to-gross ratio to 2,058,240 kWh and lifetime savings of 10,291,200 kWh.

Capacity Savings for CFLs: Each CFL distributed through the Community Promotions will result in an average capacity savings of 67 watts. As such, the gross capacity savings for the CFLs distributed will be 1,608 kW and the net capacity savings will be 1,286 kW. Assuming a peak coincidence factor of 0.25, the CFLs distributed through the Community Promotions will result in 322 kW during peak periods.

*  For many energy professionals, CFLs are extremely "old news."  The Energy Coalition tracks its CFL sales, and collects information from buyers. At a 2003 Energy Fair in Santa Monica, 44% of the CFL buyers were trying the technology for the first time!

Fluorescent Torchiere Savings Assumptions: The Community Energy Partnership will distribute 8,000 safe and efficient fluorescent torchieres in the 2004-2005 program years. Participants are required to turn in halogen torchiere lamps to participate in the program. According to the Lighting Research Center at Rensselaer Polytechnic Institute, each halogen torchiere consumes 300 watts minimum (some up to 500 watts) while the cool-burning fluorescent versions consume 58 watts.

Assuming that each lamp has a duty factor of three hours per day and savings of 242 watts, each device will result in an annual savings of 265 kWh. Although 1.35 was listed in the Energy Efficiency Policy Manual as the net-to-gross ratio, 1.0 is used here because the CPUC Workbook will not allow a ratio greater than one. Thus the net annual savings are 2,120,000 kWh for the 8,000 lamps.

* Fire Department personnel often volunteer to participate in Torchiere Trade-Ins since halogen torchiere lamps cause hundreds of fires each year.  At the first planning meeting for the Moreno Valley Trade-In, Coalition staff was introduced to the city's Fire Marshall as "the people who want to get halogen lamps off the street." Before even saying hello, he burst out with, "I hate those things!"

# Torchiere Capacity Savings: Each fluorescent torchiere distributed through the Community Promotions will avoid the need for 242 watts of capacity. (In many cases where the halogen lamp is pre-1996 vintage (Rennselaer), the capacity savings can be as high as 442 watts.) This program initiative will result in gross capacity savings of 1,936 kW. Assuming a peak coincidence factor of 0.25 the torchiere replacement will result in peak capacity savings of 484 kW.

Combined Community Promotions Savings: Electricity savings for the Community Promotions are assumed to be 4,178,240 kWh and 20,891,200 lifetime kWh. In terms of capacity, the combined Community Promotions will result in savings of 3,206 kW. Assuming a peak coincidence factor of 0.25, the community promotions will result in 806 kWp savings.

# 6. Mobile Homes

The Community Energy Partnership takes direct action in the communities it serves by offering a number of Community Efficiency Tune-Ups in each Energy District. The Tune-Ups are performed by licensed contractors, screened, selected and trained by the Partnership. Each Tune-Up takes an hour, necessarily involves the head-of-household, and results in a) the direct installation of $200 worth of goods and services in each home, and b) education about the top three things that the household can do to save energy and dollars. The Tune-Ups are provided to mobile homes, rental apartments, and owner-occupied apartments. There is also a parallel program for small businesses.

The following is a list of measures that will be provided through the Community Energy Partnership Tune-Ups. Specific measures will applicable to specific homes. Working with the head of household, the installation contractors determine the optimal savings measures and recommendations for that particular home.

Community Efficiency Tune-Up Electricity Saving Measures

Lighting Measures

- Exchange incandescent light bulbs for fluorescent bulbs

- Install energy-saving night lights, porch lights, safety lights

- Replace halogen torchiere lamps with fluorescent models

Household Electrical Appliances

- Check, replace or repair refrigerator seals

- Maintain/clean refrigerator compressor

- Discard old refrigerator

- Recommend: new refrigerator, new washing machine

- Install programmable thermostat

- Behavioral:  Turn off, unplug unnecessary lights and appliances

Space Heating and Cooling Savings Measures

- Adjust thermostat

- Replace furnace and air conditioner filters

- Caulk, weatherstrip windows, doors, and skylights

- Install ceiling fans, distribute table or standing fans

- Install window film, shades; plant shade trees

- Recommend: low-e windows, insulation

Customizing Household Measures: For each Tune-Up, contractors deliver a custom set of efficiency measures. All homes are thoroughly “checked out” using a detailed checklist and get lighting measures including CFLs, nightlights, and even hard-wired fixtures. A subset of the total number of households served – approximately one-third – will get programmable thermostats. All participants will get an assortment of efficiency measures drawing from the two dozen specific measures that contractors are authorized to install and that deliver direct energy savings. Contractors also recommend measures that in some cases, as the representative Tune-Up sample below, have larger recommended measure savings than direct install. Only direct energy savings are reported as savings in this proposal.

| Representative Tune-Up Electricity Savings |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Mobile Homes DEER Climate Zone 10 |  |  |  |  |  |
|  | # | Savings per Unit | Annual Savings (kWh) | Net Savings (kWh) | Footnote |
| Direct Install Measures |  |  |  |  |  |
| Programmable Thermostat | 1 | 351 | 351 | 280 | 1 |
| Compact Fluorescent Lamps | 5 | 107 | 536 | 429 | 2 |
| Weatherstripping (front door) | 2 | 7 | 13 | 11 | 3 |
| Nightlights | 3 | 55 | 164 | 131 | 4 |
| Total |  |  | 1,064 | 851 |  |
| Recommended Measures |  |  |  |  |  |
| High-e Refrigerator | 1 | 251 | 251 | 201 | 5 |
| Compact Fluorescent Lamps | 10 | 107 | 1,072 | 858 | 2 |
| Awnings, blinds, shade trees | 1 | 600 | 600 | 480 | 6 |
| Total |  |  | 1,923 | 1,538 |  |
| Grand Total Direct and Indirect |  |  | 2,987 | 2,390 |  |
| Sources: |  |  |  |  |  |
| 1. DEER Database, 2001 Study, SF Measure Svgs, Program Thermostats |  |  |  |  |  |
| Savings assumption based on pre-1978 vintage air conditioning systems. |  |  |  |  |  |
| 2. Based on 90-watt repl with 23 watt project CFLs, assume 3-4 hours/day |  |  |  |  |  |
| Consistent with DEER, p 298, Non-Conditioning Electric Measures |  |  |  |  |  |
| 3. DEER Database, 2001 Study, SF Values, LI Door Weatherstripping |  |  |  |  |  |
| 4. 20+ watt repl with 5 watt (or less) nightlight, 10 hrs per night |  |  |  |  |  |
| 5. DEER Database, p 298, Non-Conditioning Electric Measures |  |  |  |  |  |
| 6. Combination shading devices cut AC by 10+% of 2,000+ kWh usage |  |  |  |  |  |

Savings Assumptions: During 2004-2005 the Community Energy Partnership will provide Tune-Up services to 2,400 mobile homes. The savings will result from a) lighting measures assumed to deliver 500 annual kWh per participant (worth $48 a year in savings), b) miscellaneous efficiency measures that will save 250 kWh per participant, and c) programmable thermostats that will save 350 kWh per participant. Gas savings from Tune-Up measures – installed at the same visit – are presented in the parallel partnership proposal with The Gas Company, and add significantly to the value of each household Tune-Up for mobile homes and rental and owner-occupied apartments.

Savings Projections: Prior experience has shown that virtually every participant gets lighting and miscellaneous measures, and that one third of the mobile home participants get programmable thermostats. As a result project sector’s annual savings will be 2,220,000 kWh. Using the 0.8 net-to-gross ratio, the net annual savings will be 1,776,000 and the net lifetime savings will be 8,880,000 kWh.

Capacity Savings: The Community Energy Partnership uses a conservative net capacity savings value for each mobile home involved in the Community Efficiency Tune-Ups of 250 watts per home, for a net capacity savings of 200 watts per home, for a total capacity savings of 480 kW. Using a peak coincidence factor of 0.25, this program activity will result in 120 kWp savings.

Voluntary Capacity Savings: In addition, the Community Energy Partnership has demonstrated in prior program years that many communities have a strong willingness to chip in to the State’s capacity situation when educated to do so. Given their cohesiveness, mobile home communities have been especially engaged to cut peak consumption.

* During the California Power Crisis of 2001, The Meadows Senior Community in Irvine was prepared to cut 40% of its peak capacity during Stage 3 emergencies solely through a voluntary action plan developed by the Partnership.

# 7. Rental Apartments

The Community Energy Partnership will provide Tune-Up services to 2,400 low-moderate income apartments ranging in size from 500-1,250 square feet through direct installation services coupled with education. We assume the same energy-savings estimates for the efficiency measures as mobile homes presented above.

Savings Assumptions: During 2004-2005 the Community Energy Partnership will provide Tune-Up services to 2,400 rental apartments. The savings will result from a) lighting measures assumed to deliver 500 annual kWh per participant (worth $75 a year in savings), b) miscellaneous efficiency measures that will save 250 kWh per participant, and c) programmable thermostats that will save 350 kWh per participant.

Savings Projections: Prior experience has shown that virtually every participant gets lighting and miscellaneous measures, and that one third of the rental apartment program participants get programmable thermostats. As a result project sector’s annual savings will be 2,220,000 kWh. Using the 0.8 net-to-gross ratio, the net annual savings will be 1,776,000 and the net lifetime savings will be 8,880,000 kWh.

Capacity Savings: The Community Energy Partnership uses a conservative net capacity savings value for each rental apartment involved in the Community Efficiency Tune-Ups of 200 watts per home (80% of the value used for mobile homes), for a net capacity savings of 160 watts per home, for a total capacity savings of 384 kW. Using a peak coincidence factor of 0.25, this program activity will result in 96 kWp savings.

# 8. Owner-Occupied Apartments

The Community Energy Partnership will work with 2,400 owner-occupied apartments (condominiums) for low-moderate income participants in the 2004-2005 program years. We assume the same energy-savings estimates for the efficiency measures as mobile homes and rental apartments presented above.

| Representative Tune-Up Electricity Savings (All Electric Home) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Owner Occupied Apartments DEER Climate Zone 8 |  |  |  |  |  |
| Measure | # |  | Annual Savings (kWh) | Net Annual Savings (kWh) | Footnote |
| Direct Install Measures |  |  |  |  |  |
| Compact Flourescent Lamps | 3 | 107 | 322 | 257 | 1 |
| Nightlights | 1 | 55 | 55 | 44 | 2 |
| Fluorescent Torchiere | 1 | 265 | 265 | 212 | 3 |
| Showerhead | 1 | 148 | 148 | 118 | 4 |
| Faucet Aerators (1 unit) | 2 | 58 | 116 | 93 | 4 |
| Pipe Wrap | 1 | 76 | 76 | 61 | 4 |
| Water Heater Blanket | 1 | 201 | 201 | 161 | 4 |
| Total |  |  | 1,182 | 946 |  |
| Recommended Measures |  |  |  |  |  |
| Energy Star clothes washer | 1 | 567 | 567 | 454 | 4 |
| Energy Star dishwasher | 1 | 130 | 130 | 104 | 4 |
| Total |  |  | 697 | 558 |  |
| Grand Total Direct and Indirect |  |  | 1,879 | 1,503 |  |
| Sources: |  |  |  |  |  |
| 1. Based on 90-watt repl with 23 w project CFLs, assume 3-4 hours/day |  |  |  |  |  |
| Consistent with DEER, p 301, Non-Conditioning Electric Measures |  |  |  |  |  |
| 2. 20+ watt replaced with 5 watt (or less) nightlight, 10 hrs per night |  |  |  |  |  |
| 3. 300+ watt halogen repl with 58 watts, average of three hours use per day |  |  |  |  |  |
| Values for water heating based on all-electric MF scenario |  |  |  |  |  |
| 4. DEER Database, 2001 Study, p 301 Non-Conditioning, Electric Measures |  |  |  |  |  |

Savings Assumptions: During 2004-2005 the Community Energy Partnership will provide Tune-Up services to 2,400 owner-occupied apartments. The savings will result from a) lighting measures assumed to deliver 500 annual kWh per participant, b) miscellaneous efficiency measures that will save 250 kWh per participant, and c) programmable thermostats that will save 350 kWh per participant.

Prior experience has shown that virtually every participant gets lighting and miscellaneous measures, and that one third of the owner-occupied participants get programmable thermostats. As a result project sector’s annual savings will be 2,220,000 kWh. Using the 0.8 net-to-gross ratio, the net annual savings will be 1,776,000 and the net lifetime savings will be 8,880,000 kWh.

Capacity Savings: The Community Energy Partnership uses a conservative net capacity savings value for each rental apartment of 200 watts per home (80% of the value used for mobile homes), for a net capacity savings of 160 watts per home, for a total capacity savings of 384 kW. Using a peak coincidence factor of 0.25, this program activity will result in 96 kWp savings.

# 9. Small Businesses

The Community Energy Partnership expects to work with 600 small businesses in the 2004-2005 program years and to implement energy-efficient measures including lighting, miscellaneous efficiency measures, and programmable thermostats. As with the mobile homes, rental apartments, and owner-occupied apartments presented above, select small businesses in each partner city will be presented with Small Business Efficiency Tune-Ups that provide each participant with a customized set of efficiency measures intended to maximize the value of the $500 spent at each location.

Savings Assumptions: During 2004-2005 the Community Energy Partnership will provide Tune-Up services to 600 small businesses. The savings will result from a) lighting measures assumed to deliver 1,500 gross annual kWh per participant (worth $225 in annual savings), b) miscellaneous efficiency measures save 500 kWh per participant, and c) programmable thermostats estimated to save 1,000 kWh/participant.

Assuming that every participant gets lighting and miscellaneous measures, and that one third of the small business participants get programmable thermostats, this sector’s gross annual savings will be 1,400,000 kWh. While most of the measures presented in this proposal use the default net-to-gross ratio of 0.8, for small businesses that have been highly reluctant to participate in other programs and that are marked by an extremely low free ridership level, the Community Energy Partnership assumes a net-to-gross ratio of 0.95 for small business activities. As such the net energy savings among these participants will be 1,330,000 annual kWh and 6,650,000 lifetime kWh.

Capacity Savings: Small business capacity savings come from lighting measures (0.6 kW net capacity), miscellaneous energy efficiency measures (0.2 kW), and programmable thermostats (1 kW) where in use. Given the penetration values presented for small businesses, the overall capacity savings are projected to be 680 kW. Assuming a 1.0 peak coincidence factor, small businesses will provide 680 kWp savings.

Section V. Performance Goals

The Community Energy Partnership, like the predecessor Six Cities Energy Project, will generate a number of short and long-term benefits thanks to the hybrid program approach featuring direct installation of measures (a form of immediate gratification) and education/information to raise awareness of smart energy management. One of the greatest benefits will be providing services to hard-to-reach customers that have not fully participated in programs before.

The 2004-2005 Community Energy Partnership in the Southern California Edison service territory is projected to save 21.56 million annualized kilowatt-hours of annual electricity savings and 107.8 million kilowatt-hours of electricity savings over the life of the measures installed. The project will also result in 12.29 average MW of capacity savings and 6.1 MW peak capacity savings. It will also result in gas and water savings. Target gas savings are presented for the project in the parallel Gas Company proposal. The following table summarizes the electricity savings that will be generated by the types of participants presented and from the measures presented in the prior section:

| Southern California Flagship Partnership |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Electricity Savings |  |  |  |  |  |
| Participant | Units | Net Energy Savings (kWh) | Lifecycle Energy Savings (kWh) | Net Capacity Savings (kW) | Peak Capacity (kW) |
| PEAK Students | 26,000 | 2,244,320 | 11,221,600 | 1,394 | 348 |
| PEAK Households | 12,000 | 2,880,000 | 14,400,000 | 2,400 | 600 |
| PEAK School Districts | 8 | 2,000,000 | 10,000,000 | 2,000 | 2,000 |
| Municipal Facilities | 12 | 3,600,000 | 18,000,000 | 1,440 | 1,440 |
| Community Promotions | 16,000 | 4,178,240 | 20,891,200 | 3,206 | 806 |
| Mobile Homes | 2,400 | 1,776,000 | 8,880,000 | 480 | 120 |
| Rental Apartments | 2,400 | 1,776,000 | 8,880,000 | 384 | 96 |
| Owner-Occupied Apts | 2,400 | 1,776,000 | 8,880,000 | 384 | 96 |
| Small Businesses | 600 | 1,330,000 | 6,650,000 | 680 | 680 |
| Total | 61,820 | 21,560,560 | 107,802,800 | 12,368 | 6,186 |

Voluntary Capacity Savings: The capacity savings from the Community Energy Partnership are unique. These are “negawatts” generated from hard-to-reach power consumers heretofore untapped for their abilities to cut peak demand. They participate irrespective of demand responsiveness incentives, real-time meters, and rate structures.  Rather than paying these consumers for their efforts at load shifting, the Partnership builds awareness and taps volunteerism, individual initiative and responsibility!

Community awareness and long-term savings: These measurable energy and capacity savings will be generated through: residential programs (targeted for senior housing, mobile home communities, hard-to-reach multifamily apartments, and low and moderate income owner-occupied apartments); small business works; PEAK home and school-based savings, and through municipal initiatives that help partner cities “get their own houses” in order. In addition, and not considered in this section of the proposal, savings will be generated from community awareness activities and long-term savings related to the program’s emphasis on charting their sustainable energy futures. While not quantified for this proposal, these long-term savings may be far more profound, and may far outstrip the short and mid-term savings presented here.

Section Vl. Program Evaluation, Measurement and Verification (EM&V)

The Community Efficiency Partnership will be subject to a dual process and impact evaluation. What worked? What didn’t? How much energy and capacity is offset through short-term measures? How much through long-term attitudinal transformations? This section of the proposal presents some background on evaluation of the Community Energy Partnership and then presents key elements of the full evaluation process.

Current Evaluation Experience: The Six Cities Energy Project – the predecessor program that was delivered in 2002-2003 – is currently being evaluated using a multifaceted approach within a budget of $100,000. Given the deliberate proximity of the evaluation firm, the budget amount has allowed for extensive field visits. It also allows for telephone sampling. But it is, naturally, limited in terms of direct metering. Perhaps this is appropriate as it is the process of community organizing and the spirit that is then built, that will be most important to evaluate. Once a project has a spirit, the spin-off and indirect savings benefits far outstrip conventional program approaches.

The Six Cities Energy Project is being evaluated in real time, and there is a final evaluation report that will be completed in spring of 2004. Thus far, the Coalition has been pleased with the evaluator’s work. To preserve the cost-effectiveness of the evaluation and to take advantage of its position “on the learning curve” for the Community Energy Partnership approach, The Energy Coalition recommends that its current evaluator – Aloha Systems of Irvine, California -- be retained for the 2004-2005 program years. The second firm that is local and understands our program sufficiently, is ASW Engineering of Tustin that has agreed to be listed herein.

Recommendation of Evaluators

#1 Aloha Systems, Irvine, California.

#2 ASW Engineering, Tustin, California

The Energy Coalition recommends that Aloha Systems of Irvine, California be retained as the Community Energy Partnership program evaluator for the 2004-2005 program years. Aloha is currently evaluating the Six Cities Energy Project, is local, and fully understands the program, allowing the majority of evaluation funds to go into site visits and reasoned technical analyses. Our alternative is ASW Engineering of Tustin, a local firm also quite familiar with the Community Energy Partnership process.

2004-2005 Evaluation Budget: The Community Energy Partnership provides an EM&V budget that represents sizable increase when compared to the Six Cities Energy Project. While the number of cities has also doubled, this increased evaluation budget will be sufficient to gain a more sophisticated evaluation of the program. In addition, mid-term results from some initial six cities activities – like student household savings – will be forthcoming in the early months of the proposed Community Energy Partnership to provide further substantiation of the model and insight as to efficacy.

Key elements of the proposed evaluation approach:

1. Measuring levels of energy and peak demand savings achieved

Measuring direct energy savings is the primary focus of the EM&V plan. In some situations this will be a relatively straightforward assessment of energy savings and demand reduction achieved as a result of making physical changes to facilities, for example providing incentives for creating a demonstration lighting project at a community museum or school facility. Traditional measurement and verification approaches to determine operating hours and demand reductions will be used.

In other situations like community promotions, the measurement of demand reduction and energy savings will necessarily rely on less exact methodologies, such as analysis of self-reported data from participants. This will be particularly true of the several thousand compact fluorescent and torchiere replacements where energy demands are relatively easily established but operating hours are far less certain.

There will be many situations in the Community Energy Partnership where the primary energy savings are behavioral in nature. Furthermore, these behavioral changes are spread out over a large number of participants. A prime example of this is the PEAK program, where the primary results in both homes and schools are either directly behavioral (such as turning off lights) or are physical results inspired by behavioral or attitudinal changes (such as a student convincing her parents to buy an energy-efficient refrigerator). These benefits will be virtually impossible to measure directly in any cost-effective manner, so they will be developed using indirect assessment means.

2. Measuring cost-effectiveness

The energy savings and demand reduction numbers provided through the EM&V analysis will be usable as revised parameters for calculations of the standard cost-effectiveness tests. Combined with the Energy Coalition’s actual costs for implementing various aspects of the program, accurate ex-post cost-effectiveness calculations will be determinable not only for the project as a whole but for its individual components as well.  When compared with the ex-ante calculations used for the official determination of meeting project goals, these cost-effectiveness results derived from the EM&V data will facilitate an assessment of similar future projects.

3. Providing up-front market assessments and baseline analyses

For the Community Energy Partnership’s customer segments, developing baseline analyses is more behavioral than technical. For the most part, the technologies deployed through the program are straightforward (such as CFLs) and replace old technologies that are even more straightforward (such as incandescent lamps). For the purposes of this evaluation, the more telling baseline issue will be assessing prior awareness of the various technologies and behaviors taught through the components of the project. The evaluation will employ market-research-style awareness assessment to make this kind of assessment, and to see just how well the project penetrated the hard-to-reach customers.

The evaluation will also survey a limited number of non-participants who were eligible for the program. This will help determine both the baseline of awareness and usage of the various efficiency technologies. It will also enable a better estimate of the market transformation component of the program, and thereby assess the value of the program that exceeds the direct value of the physical equipment supplied. For example, some energy savings will be achieved in the close-knit communities even among those not initially participating. When one neighbor sees that three of his neighbors have and like their compact fluorescent lights, he or she may go to a home improvement store and buy some, even though the Community Energy Partnership’s promotion may be over.

4. Providing ongoing feedback and corrective guidance

For the Community Energy Partnership the evaluator will be local and in frequent communication with The Energy Coalition as facilitating partner. Furthermore, because the assessment of the value of the community organizing is subjective in nature, one or more evaluation staff will observe key project meetings and volunteer at important special events to gain a first-hand perspective on their value to the city and project. After these events the evaluator will report back to The Energy Coalition, Southern California Edison and the partner cities with assessments and suggestions for process and impact improvements to maximize community savings and to make the project more cost effective.

5. Measuring effectiveness indicators of specific programs

Several sectors are addressed by the Community Energy Partnership, each of which has significantly different indicators of effectiveness. The full EM&V plan will present specific methods to measure these various indicators to grasp this variety and assess its individual and overall effectiveness. Furthermore, the exact implementation details of the project are not fixed at its onset.  An integral part of the Partnership approach is to allow the cities and schools to work with the Coalition to develop a tailored program that best suits their needs. Therefore, the EM&V plan will evolve with the project, requiring significant levels of flexibility from evaluators.

6. Assessing the overall levels of performance and success of the program

The overall performance and success of the Community Energy Partnership will be based upon a number of components. The process and impact elements of the evaluations will present the engineering and behavioral information gathered and analyzed. It will also assess an array of additional program aspects – from press coverage to volunteer spirit! --to provide an accurate and clear picture of the value of the Partnership’s innovative, diverse, comprehensive, and interwoven approach to community energy efficiency.

The process evaluation will also present and analyze additional benefits of various components of the program, some which are not directly related to energy efficiency, but nonetheless are laudable uses of public funds that contribute to the overall benefits of society. For example, among the non-energy benefits are reduced fire risk achieved by destroying hazardous high-wattage halogen torchiere lamps. The evaluation will stop short of developing financial values for these ancillary or spin-off benefits, but they will be included as telling anecdotes in the discussion of the project’s overall performance.

* As part of an Energy Rally, community residents volunteered to assemble and deliver torchiere lamps to their shut-in neighbors. When volunteers arrived at one mobile home, they found only one operating light in the entire coach. With difficulty, the elderly Korean-American owner explained that she seldom went out and never went to events, "because I can't understand."  But she had been able to decipher the flyer with the torchiere and CFL trade-in information, and had submitted her request because the lamps would be delivered.

7. Assessing whether there is a continuing need for the program

Ultimately the most important question of the EM&V process is whether the program warrants continuation. By its nature, the Community Energy Partnership is likely to be either an ineffective means of enhancing our State’s energy efficiency, or it will demonstrate itself to be something worth repeating in virtually every community. The success of the previous Two Cities Project and Six Cities Energy Project implies the likelihood of the latter, but the more complex arrangements, increased project management duties, and additional diversity among the cities will provide greater insight and evidence for this expectation. As such, the final component of the valuation will be a clear judgment of whether the program needs to “go back to the drawing boards,” or whether it does indeed warrant continuation.

Section Vll. Qualifications

Partner Cities

This proposal represents twelve diverse Southern California cities with an aggregate population of a million people strong. The cities are banded together by The Energy Coalition and are committed to making a difference and being responsible for crafting a healthy and sustainable energy future. These cities’ commitments to the Community Energy Partnership extension and expansion are exhibited as the first attachment.

Team Leaders: As part of the Memorandum of Understanding signed by each city and The Energy Coalition, each city must designate a senior official to serve as the project Team Leader in his or her community. Cities have to dedicate staff time and other in-kind services (such as traffic support and use of City Hall) to the project. It is the cities' dedication to the project, and the successes that these Team Leaders have enabled in their cities, that is the ultimate qualification for funding.

The Energy Coalition

The Energy Coalition is a 20-year old 501 c(4) non-profit organization based in Laguna Beach, California that has been developing the Community Energy Partnership model for ten years, and that now has five years of experience under its belt. Thanks to the partner six cities involved, the program was heralded for its success. In 2001, the Two Cities Energy Project – one of the Partnership’s predecessor projects -- was named a winner of the Governor's Environmental and Economic Leadership Award. The Energy Coalition was awarded a 2002 Flex Your Power Award for PEAK Student Energy Actions.

The Coalition is headed up by John B. Phillips and managed by Ted Flanigan. Virginia Nicols is our Campaign Coordinator; Sheila Bailey is our Financial Officer. Dorothy Terman is our senior PEAK consultant.

John Phillips has nearly 50 years of experience helping end-users optimize their energy use. He designed and managed energy systems for major facilities across the country, and later pioneered energy cooperatives of large users keen on learning from one and other to trim their costs and provide better services. For the past ten years, working at the senior energy policy level, Phillips has been advocating more effective means of delivering energy services to communities in California and Sweden.

Ted Flanigan has over 20 years experience designing and implementing efficiency programs. He has worked for two major utilities and consulted for over 100 utilities and energy services provides in over 30 countries. His work was recognized and funded by the John D. and Catherine T. MacArthur Foundation. As the Project Director, he will be responsible for all day-to-day managerial functions of the Community Energy Partnership. His resume is in the proposal attachments.

Virginia Nicols has over 20 years of experience with marketing concepts and engaging participants. For the Coalition, she has found creative means of stimulating record-high levels of participation in community events. Her skill is to relate the message to the audience, an invaluable attribute of the Community Energy Partnership.

Sheila Bailey has worked for The Energy Coalition for nearly 20 years and is responsible for the financial accountability of Edison ratepayers’ funds for the Community Energy Partnership. She has extensive experience with CPUC rules for program accounting and has been diligent in careful financial control to maximize program dollars that can be spent in the field.

Southern California Edison

SCE is uniquely qualified to be an active partner in the Community Energy Partnership.  In fact, SCE was one of the founding partners of the Two Cities pilot program, which was the genesis of the evolution to this current program proposal. Moreover, SCE’s experience in energy efficiency is a century long. It began assisting customers is the wise use of energy in the early 1900s, when it first began helping agricultural customers to test the efficiency of their electric pumps. Since then, SCE’s programs have been recognized with numerous national awards.

Gene Rodrigues, SCE’s Director of Energy Efficiency, has been presented with a Governor’s Environmental and Economic Leadership Award recognition for his contributions to environmental protection and resource conservation in California. SCE’s energy efficiency program managers have an average of ten years of experience in energy efficiency and related customer service activities and are supported by a veteran staff of technical experts in all facets of energy efficiency.  Edison’s design and technical support staff has over 300 years of combined experience, over two-thirds are licensed by state or federal organizations, and over half have advanced degrees. Edison’s program design and evaluation staffs also have extensive first-hand knowledge of the customer demographics unique to SCE’s service territory.

As a utility that serves all of the energy needs of all of its customers, SCE also has an existing infrastructure of support functions (such as accounting, regulatory and legal departments), systems (such as our program tracking and reporting systems) and facilities (such as our energy centers) that it uses to facilitate the implementation of its programs.  Further, Edison’s long-term relationship with the Commission and the customers it serves further ensures that program participants will be well served and protected. SCE provides full accountability to both regulators and customers that is has served for over a century and that is invaluable to ensuring that ratepayer funds are appropriately spent.

Using the experience and resources described above, SCE stands ready to work side-by-side with the program partners – notably the partner cities and The Energy Coalition -- to further satisfy its customers’ energy efficiency needs and to meet the Commission’s policy objectives that position energy efficiency resources as key to the Commission’s Energy Action Plan and to the State’s energy future.

PEAK Services

Five outstanding science teachers from Santa Monica, Irvine, and Newport Beach -- Joel Post, Linda Cady, Kathy Marvin, Laurie Hartstein, and James Gapp -- provide consulting services for PEAK, train “incoming” PEAK teachers, and develop new curriculum modules. Two PEAK teachers took the initiative to develop the summer PEAK Energy Adventure, a two-week summer science adventure that included field trips to power plants and energy patrols in the community. Four PEAK teachers have trained PEAK teachers in Sweden.

PEAK benefits greatly from the services of Dr. Dorothy Terman, the former math and sciences curriculum coordinator for Irvine Unified School District and now a multifaceted consultant whose duties range from gender equity issues (promoting science for girls) to PEAK. Dr. Terman is responsible for PEAK’s integration into existing curricula and communicating the value of PEAK’s applied teaching.

Technical Services

The Community Energy Partnership frequently draws upon the services of a number of engineering firms for technical services. Notably, ASW Engineering of Tustin has done extensive work over the years with municipal and school facilities. In addition, ASW has provided engineering consulting for PEAK and program designs. Henrikson Owens, and notably its principal – Richard Henrikson – has also been a key player for the Partnership, auditing school and municipal facilities and assisting in program design activities. In addition, Global Green USA – a non-profit organization from the partner of Santa Monica -- has been used to support super-efficient and environmentally sensitive new construction in the partner cities.

Tune-Up Installation Services

Two exceptional installation contractors make the Community Efficiency Tune-Ups successful. Ace & Sons Construction, Inc. of Riverside, California, provides services to in-land project cities with its expertise in weatherization and HVAC systems. Catalina Ballast & Bulb Co. of El Monte provides services in more coastal project cities with its expertise in lighting retrofits. Both firms possess exceptional communication skills and a wealth of experience providing direct installation services in Southern California.

Section Vlll. Budget

The Community Energy Partnership presented in this proposal requires a budget of $7,340,000. The budget reflects key lessons learned in the Six Cities Energy Project, i.e., community organizing always takes more effort than you think. The doubling also requires considerably increased management to assure sufficient resources such that project staff become present, known, and recognized in the cities. We have also learned that there is a need for increased marketing and outreach within the partner cities.

| Southern California Flagship Budget Summary |  |  |  |
| --- | --- | --- | --- |
|  | 2004 | 2005 | Total |
| Community Activities |  |  |  |
| PEAK Students | $280,000 | $280,000 | $560,000 |
| PEAK Households | $20,000 | $20,000 | $40,000 |
| PEAK School Districts | $150,000 | $150,000 | $300,000 |
| Municipal Energy Actions | $160,000 | $160,000 | $320,000 |
| Community Promotions | $240,000 | $240,000 | $480,000 |
| Mobile Home Activities | $280,000 | $280,000 | $560,000 |
| Rental Apartment Activities | $280,000 | $280,000 | $560,000 |
| Owner-Occupied Apts | $280,000 | $280,000 | $560,000 |
| Small Business Tune-Ups | $250,000 | $250,000 | $500,000 |
| Community Organizing | $225,000 | $225,000 | $450,000 |
| Marketing and Outreach | $225,000 | $225,000 | $450,000 |
| Project Center Overhead | $180,000 | $180,000 | $360,000 |
| Subtotal |  |  | $5,140,000 |
| Project Management |  |  |  |
| Project Management | $450,000 | $450,000 | $900,000 |
| Benefits | $225,000 | $225,000 | $450,000 |
| Travel Costs | $150,000 | $150,000 | $300,000 |
| Program Tracking/Reporting | $125,000 | $125,000 | $250,000 |
| Impact Evaluation | $150,000 | $150,000 | $300,000 |
| Subtotal |  |  | $2,200,000 |
| Total Budget | $3,670,000 | $3,670,000 | $7,340,000 |

Funding Flexibility: The Community Energy Partnership is unique in its flexibility. Not only can checks be cut without delay, but if a certain set of anticipated activities appear unlikely to deliver results, the Partnership can withdraw funds and reapply them in another, more promising area. Inversely, wild success with one energy efficiency strategy can warrant an infusion of project funds. The Partnership also reserves the right to shift resources between participating cities based on progress or lack thereof. This is all done with the primary program objectives in mind, that is to stimulate awareness and activity that will lead to sustained savings for eager communities and the State.

Section lX: Summary

The Community Energy Partnership works in a unique way and in doing so has been able to reach energy consumers that are most in need of energy and dollar savings. The Partnership works with participants who have been largely cynical about their prospects of having an impact at the community or state level. The Partnership educates participants and organizes communities to fundamentally change the way people think about energy and other finite resources. The Community Energy Partnership that has now grown to twelve Southern California Edison cities, representing a million Californians, will build a responsible energy ethic to transform attitudes and markets.

The California Potential

When fully extended and expanded throughout the State of California, the Community Energy Partnership can deliver up to 10,000 MW of capacity and $12 billion in consumer savings by 2010. Most importantly, the model approach is proving that "ordinary people" can be educated and inspired to reap the benefits of immediate action and become part of a process of creating a healthy energy future. Through collaboration stimulated by the cities and the strategic partnerships developed by The Energy Coalition, Community Energy Partnerships are a potent model and expression of community energy responsibility.

The Community Energy Partnership has gained the respect of each of California’s investor-owned utilities as well as the California Public Utilities Commission. This has been hard-earned, and speaks to the success of a robust set of activities in the partner cities that are at once providing immediate energy-savings benefits and building community responsibility for energy use through an energy ethic that has been heretofore missing. By partnering with utilities, the Partnership now will take another major step forward to becoming fully linked with utilities’ integrated resource plans and resource procurement plans, an essential evolution that builds a win-win-win situation between the people and their cities, the serving utilities, and the State of California.