Confirmation Number:

Program Title:  Statewide Savings By Design

Proposed by:

Southern California Edison

Contact Person:  	Don Arambula

Address:  		2131 Walnut Grove

Rosemead California  91770

Telephone:  		626-302-8179

Email address:  	don.arambula@sce.com

List of all other public goods charge programs proposed:

- Statewide Residential Appliance Recycling

- Statewide Single Family Energy Efficiency Rebates

- Statewide Multifamily Energy Efficiency Rebates

- Statewide Home Energy Efficiency Surveys

- Statewide CA Energy Star New Homes – Single Family, Multifamily programs

- Statewide Standard Performance Contract

- Statewide Express Efficiency

- Statewide Nonresidential Energy Audits

- Statewide Building Operator Certification

- Statewide Emerging Technologies

- Statewide Savings By Design

- Statewide Education and Training

- Statewide Codes and Standards Advocacy

- Local Small Nonresidential Hard to Reach

- Local Pump Test and Hydraulic Services

- Local Government Initiatives

- Local Community Partnership – 12 Cities

- Local Community Partnership - Ventura County

- Local Community Partnership - South Bay Cities Council of Governments

- Local Los Angeles County program

- Local UC/CSU program

- Local Bakersfield/Kern County

- Local City of Pomona program

Table of Contents

Statewide Savings By Design	2

I.	     Program Overview	2

II.	     Program Process	8

III.	Customer Description	17

IV.	Measure and Activity Descriptions	19

V.	    Goals	21

VI.	Program Evaluation, Measurement and Verification (EM&V)	22

VII.	Qualifications	25

VIII.	Budget	28

Statewide Savings By Design

## I.	Program Overview

A.	Program Concept

Savings By Design (SBD) is an energy efficiency program for the nonresidential new construction industry started by the investor-owned utilities (IOUs) in 1999 to provide statewide consistency, program stability, and savings persistence to the new construction market.  SBD builds on the best elements of successful new construction programs run by the investor owned utilities since the early 1990’s.  The program promotes integrated design and emphasizes early design involvement by offering building owners and their design teams a wide range of services including education, design assistance, and owner incentives as well as design team incentives.

B.	Program Rationale

The SBD proposal is for the continuation of SCE’s highly successful incentive program that was offered during 2002-2003.  The SBD program has consistently met and, in 2004 and 2005, will continue to meet the California Public Utilities Commission’s (Commission) goals and objectives for energy efficiency programs for the new construction market.  SBD delivers cost-effective, verifiable, long-term energy savings and peak demand reduction, with Commission-established Effective Useful Lives (EULs) of between 16 and 20 years (depending on end-use).  The EULs applied to the SBD program far exceed the Commission’s minimum target of three years.  By providing the technical and financial means to influence the basic design of commercial and industrial projects, SBD assures that these projects are designed and constructed correctly the first time. SBD interventions avoid the missed opportunities that result when energy efficient measures and strategies are not incorporated in a project during the construction phase and the project has to be retrofitted later at higher cost. When a building or process is built correctly from the outset, excess electrical and gas demand never impact the electric and gas transmission and distribution systems, assuring both energy savings and savings persistence.  Further, because the program is delivered before a building or process is constructed, energy savings are achieved when they create the greatest benefit and are most cost-effective for the owner.

Since 1999 the statewide SBD program has involved thousands of participants and projects and has worked with scores of design teams.  SBD field personnel at all participating utilities have influenced and enrolled 927 projects that are currently pending construction completion.  SBD implementation staff is currently working with owners, architects, and engineers to maximize the energy efficiency of more than 1,258 additional projects for eventual inclusion in the program.  The program’s innovative educational elements and implementation strategies successfully overcome market barriers and failures that inhibit adoption of cost-effective energy efficiency measures while providing lead sources for future project involvement, specifically:

- Split Incentives - Building and systems design is the purview of engineers and architects who will not be responsible for the energy costs arising from their designs, so SBD provides an information loop for industry-and-project-specific energy cost information to get to owners. Furthermore, by providing incentives to design teams, engineers and architects are given a financial stake in the projects energy efficiency characteristics.

- Performance Uncertainties – Lack of confidence in the cost-effectiveness of increased efficiency, concerns over performance of high efficiency products and design strategies, and routine over-sizing of systems to limit potential liability from design error are common in the nonresidential new construction market. SBD provides proven intervention strategies such as one-on-one project recommendations and education to all participating market actors to allay these concerns.

- Asymmetric Information and Information Search Costs – Manufacturer’s claims may be confusing and not necessarily reliable. New design practices require study prior to implementation. Architects and engineers are the primary source of information on energy and sometimes limit the flow of that information to owners in order to retain control of project parameters and schedules. To overcome these informational asymmetries, SBD provides considered, balanced, unbiased information and recommendations directly to owners as well as to architects and engineers.

- Hassle or Transaction Costs – Costs in time and money associated with an owner or designer identifying efficient practices and technologies - along with the hassle and time to convince owner or developer to upgrade efficiency features - often precludes energy efficient design and construction, even when such design changes are simple and cost-effective. SBD incentives and project-specific information provide motivation for owners and design teams to consider and implement energy efficiency improvements.

- Opportunism - Manufacturers provide the design community with tools which speed and aid the design process, but which may also subtly manipulate results to favor designs or equipment types specific to that manufacturer – without regard to maximizing efficiency or even the suitability of the equipment for the application. SBD analysis tools and assistance provide unbiased recommendations based on best practice, overcoming such opportunism.

- Service Unavailability – Often, designers offer energy efficiency services to only the most sophisticated clients while energy service companies rarely offer energy efficiency services in the new construction marketplace due to long build-outs for projects and the difficulties in establishing baselines. To counter this, SBD offers design assistance and analysis for all customers and the Systems Approach to help smaller and less sophisticated clients quantify, understand, and capture energy savings based on integrated design.

- Bounded Rationality –Designers and contractors use commodity-based approaches including standardized design practice, energy rules of thumb, and short cuts - often sacrificing quality for expedience and low first-cost. SBD provides integrated design assistance, strategies, information, and tools that allow market actors at all levels to accurately evaluate, understand, and size their projects.

- Hidden Costs – Lower levels of energy efficiency result in not only higher operating costs, but also higher maintenance costs, less comfort, shorter equipment life and less environmental quality. SBD provides project-specific cost information to decision makers and trains those individuals in the use of analysis tools that allow decision makers to understand and evaluate their own costs.

- Confusion Regarding Minimum Energy Code - Many industry decision-makers are unaware that building energy codes actually represent the highest allowable energy consumption possible for buildings in California. Building owners and even design team members often confuse meeting minimum Title 24 energy code requirements with energy efficiency. SBD tools and analysis demonstrate that energy code is only a reference point from which to evaluate cost-effective and truly energy efficient designs.

From inception, SBD innovations have produced a program that not only addresses market needs, barriers, and failures but which has also evolved in response to the changing needs of the California new construction market. This innovation will continue with the 2004-2005 program.  In addition to ongoing changes to the program to account for the tri-annual tightening of Title 24 building standards, the program is annually re-evaluated and modified to support and enhance the momentum of emerging technical, operational, cost-effective implementation processes, and best practice trends in the new construction industry.

SBD innovations allow it to adjust to emerging building trends so that it can stay relevant and cutting-edge, encouraging design teams, building owners and entire industries to be innovative themselves.  The program pursues continuous improvement in its own materials and approaches in order to supply owners and design teams with resources that will support and develop their skills related to energy efficient design. For example:

- In response to a lack of code for industrial and agricultural customers, SBD has evaluated standard practice in various industries and industrial processes in order to establish baselines for program participation. To date these include wastewater treatment plants, dairies, clean-rooms, and wineries, as well as motor and compressed air systems. These studies are among the first of their kind in the nation.

- As an increasing number of design team members desired to become proficient in energy modeling, SBD sponsors trainings and expanded incentives to encourage and motivate design teams to submit their own project modeling.

- In response to the growing awareness of the value associated with green design and the U. S Green Building Council’s Leadership in Energy and Environmental Design (LEED) program, SBD expanded its marketing strategy to find synergies with this program, both supporting the energy components of for teams already pursuing LEED and directing other design teams participating in SBD towards LEED.

- As gas supply and prices are expected to experience increasing volatility over the next few years, SBD has responded by increasing its gas incentive for gas saving energy efficiency measures.

- In anticipation of a new focus on Time Dependent Valuation (TDV) in the next round of building codes, SBD will expand its calculation and incentive methodologies to accommodate and value kW demand reduction.

- Other innovations and program changes that relate to specific objectives and deliverables as delineated in section I. C.

Finally, it is important to note that program stability is a paramount concern for SBD participants. Because in-depth energy efficiency analyses leading to substantive design and construction changes involve risk and the possibility of increased costs, programs supporting the new construction industry must provide consistency and must accommodate industry timelines – and those timelines are long.  An expedited new construction project may take three or more years from concept to build-out, while standard new construction timelines run four to seven years, and institutional, hospital, or nonstandard projects can take a decade or more.

C.	Program Objectives

The SBD program seeks to optimize energy efficiency of new construction projects, prepare the market for upcoming code change, and promote the acceptance of energy efficiency within the new construction market by providing tools and resources to standardize energy efficient design processes.  SBD will also actively reach out to market actors in areas and customer classes that have had lower program participation rates, i.e. geographic and customer classes designated as hard-to-reach.

In order to optimize the energy efficiency of individual projects, the SBD program influences nonresidential building owners, tenants and design teams to exceed current Title 24 energy efficiency standards (or other established standards for industrial and specialty processes) by a minimum of 10 percent for their new construction or renovation/remodeling projects.  SBD leverages resources from industry relationships, strategic alliances, and other public purpose programs such as the Customer Technology Application Center (CTAC) in Irwindale, Agricultural Technology Application Center (AgTAC) in Tulare, other utility administered energy centers, Information Services program and the Refrigeration and Thermal Test Center (RTTC) in Irwindale to accomplish the goals of energy savings, peak demand reduction, and long-term market change. Over a sustained period of time, these interventions impact market practice and flatten projected procurement demand, while continuing to nurture commercial and industrial project development within the new construction market.

To enhance program impact, continuity, and consistency, the utilities will:

- Work together to implement the program with owners, designers, and others in multiple service areas;

- Continue to develop and employ alternative delivery models that enable a broader scope of customer participation;

- Coordinate and share design analysis assumptions and baselines;

- Provide referrals to the appropriate utility for potential projects encountered that fall outside their own service areas;

- Conduct onsite installation verification for all completed projects;

- Collect, track, and compile comparable project information and results;

- Provide quarterly and annual progress updates detailing program accomplishments and status.  Reports in 2004–2005 comply with the Energy Division’s Reporting Instructions.

A core component of the SBD mission is to prepare the new construction industry for changes to Title 24 energy code.  SBD has consulted with the California Energy Commission (CEC) on potential program strategies to prepare market actors for code change in advance of the 2005 round of standards, currently anticipated to take effect in January 2006.  The program will continue to serve the needs of project owners and design teams in 2004 and 2005 with specific innovations and enhancements intended to help prepare the market for the upcoming code change.  Key innovations and changes include:

- The inclusion of energy efficient outdoor lighting technology and design practice in the 2004-2005 SBD incentive structure (in advance of mandated standards in 2006);

- Aligning 2004-2005 program rules with the new Federal Air Conditioner and Water Heater Standards per CEC recommendation;

- Promoting SBD for currently unregulated occupancies (facilities or occupancies not now included in Title 24) that will be subject to Title 24 in the next round of code change (e.g., lighting in unconditioned spaces);

- Development of educational and training programs for industry professionals and market actors in advance of the code adoption to provide information on code change specifics, the implications of those changes to construction practice, and strategies for maximizing code compliance margins;

- Staged introduction of incentives for various code requirements in advance of code change;

- Staged adoption of certain 2005 code elements as prerequisites for program participation.

- Increase in minimum incentive levels for industrial processes to $ 0.10/kWh and $0.60/therm to cover a greater portion of incremental measure costsand increase program participation among industrial and agricultural customers.

SBD supports the adoption of integrated design techniques and energy efficient design practice as standard industry procedure by providing tools and education to the design community.  In 2004 and 2005, SBD will continue efforts to develop new, innovative design tools and information through Energy Design Resources. Continued development of the EDR program will include updated and new tools, design briefs, case studies, and pilot projects. These resources will be developed to provide owners, architects, and engineers with the information and design aids they need to make the best possible energy efficiency design decisions. Program resources will be developed through a third party, open-bid process to best encourage creative solutions from key market actors and agents, producing a high quality, low cost product. Additionally, EDR program management will work closely with the California Energy Commission to develop specific elements and classes to train and prepare all market actors for 2005 Title 24 code changes (again, scheduled for implementation in January 2006).

Traditionally, smaller customers and those in non-urban areas have participated in the SBD program at a lower rate than larger and urban customers. In order to assure greater equity, the program will expand efforts to reach out to these customers in 2004 and 2005. Specific activities will include:

- Establishing relationships with, and providing promotional materials through, local building plan check agencies;

- Offering on-site education and training classes at regular meetings of regionally- based architectural, engineering, professional organizations, and trade groups including promotion of SBD design assistance and incentives;

- Continued development of liaisons with specific organizations representing small and medium size businesses;

- Expanding relationships with agricultural business organizations to provide industry-specific information to members;

- Outreach through Local Community Initiatives that will seek greater participation by supporting efforts of local governments with information and program materials.

- Working through utility-local government partnership programs to provide outreach that is organized and directed by local government and targeted to each community’s highest-potential small and medium sized businesses.

## II.	Program Process

A.	Program Implementation

- A coordinated array of intervention strategies is necessary to overcome the various market barriers standing in the way of sizable net benefits available from integrated, comprehensive building design.  The SBD approach targets the primary decision makers in new construction projects.  Design assistance and incentives target owners, architects, and engineers, contractors, and project managers with information and financial stimulus to encourage maximum effort in pursuit of comprehensive savings. The SBD program relies on three basic elements:  the Whole-Building Approach, the Systems Approach, and education and outreach.

- SBD’s core strategy centers on an integrated design approach to optimize energy efficiency, known as the Whole-Building Approach.  In the Whole Building Approach, design teams work closely to integrate the energy systems in buildings with complex system interactions and in large, multi-use facilities.  The Whole Building Approach attempts to target all primary decision-makers in new construction projects.  Information, technical assistance, and financial incentives for owners, architects, engineers, vendors, and contractors help transform existing organizational practices.  Design assistance and design analysis target architects and engineers with the information they need.  Financial incentives to owners help offset the incremental cost of high-efficiency technologies and incentives to design teams motivate them to evaluate energy efficiency options on behalf of their clients.

- For participants who would not normally consider or cannot use a fully integrated design approach, the Systems Approach provides a simplified, performance-based method that moves owners and design teams far beyond simple prescriptive approaches.  The Systems Approach is appropriate for small buildings with simple system interactions, for projects where the design of the energy systems is done at different phases, for projects where one energy system predominates, or where program intervention occurs late in the design.  The Systems Approach targets the subset of decision-makers involved with smaller or simpler buildings and the narrower range of efficiency options available for those buildings (e.g., a narrower range of efficiency choices and fewer choices within that range).  This approach provides information resources to building owners, their engineers and contractors, targeted design assistance to architects and engineers, and incentives to owners.

- Finally, program education and outreach strategies, focused on the successful Energy Design Resources (EDR) model, address market barriers by providing owners and designers with information, education, and tools to help them make the best possible energy efficiency choices.  All three elements include strategies that support the CEC’s goals for market transition to the 2005 Title 24 code revisions.

Delivery strategies to bring the three elements to the market utilize the training, educational, outreach, and tool development capabilities of SCE’s energy centers.  The capabilities of the energy centers are integral to program design as are alliances with organizations promoting energy efficiency and integrated design for the new construction industry.  In pursuit of these ends, SBD will coordinate with numerous organizations and agencies including, but not limited to:

  - The U. S. Green Building Council’s (USGBC) Leadership in Energy and Environmental Design (LEED) program through development of SBD materials that are used directly to substantiate the energy points component of the LEED scoring system;

  - The American Institute of Architects, California Council (AIACC) through support of the Desert Practice and Monterrey Design conferences as well as the SBD-AIACC Energy Integration Design Awards

  - The Collaborative for High Performance Schools (CHPS) though funding for the organization as well as presentation of CHPS classes and seminars and the distribution of CHPS materials;

  - The California Commissioning Collaborative (CCC) though support for, and chairmanship of, the organization as well as project commissioning support through EDR resources and the implementation of building commissioning strategies in project development and industry practices;

  - The Coalition for Adequate Schools Housing (CASH) through membership and annual meeting presentations and program support;

  - Consortium for Energy Efficiency (CEE) through support for equipment standards development and commercial building guidelines;

  - The American Society of Heating, Refrigeration, and Air Conditioning Engineers (ASHRAE) through presentations and support at local chapter meetings as well as involvement in major conferences and events;

  - The California Energy Commission (CEC) through support of codes and standards in addition to market preparation for 2005 Title 24 code adoption;

  - The Department of the State Architect (DSA) through ongoing collaboration regarding public school design;

  - The California Integrated Waste Management Board for efforts and programs to improve portable classrooms;

  - The University of California (UC) and California State University (CSU) Systems through SBD involvement in multiple campus projects.  SCE has provided its design services and incentives for many projects on the campuses of the University of California, Irvine and the University of California, Santa Barbara.

  - The Building Owner’s and Manager’s Association (BOMA) through provision of commercial energy efficiency information and program support to members.

SBD’s intervention strategies also coordinate with, and complement, separate utility and non-utility programs which seek to drive emerging technologies, transform equipment replacements markets, and promote lighting efficiency investments driven by facility remodeling and rehabilitation, and support retrofit programs. Such programs include U. S. Environmental Protection Agency’s programs for commercial and industrial buildings, National Fenestration Rating Council efforts to improve code requirements for windows, and utility Codes and Standards programs, among others. Studies funded by SBD’s education and outreach element (Energy Design Resources) substantiate technology uptake and provide a foundation for codes and standards efforts, while SBD prepares the market for those codes.

B.	Marketing Plan

Statewide Marketing

For 2004 and 2005, the statewide SBD implementation team will market to architects, engineers, energy design professionals, building owners, professional and industry associations, and contractors.  Marketing efforts include but are not limited to:

- The development and distribution of program brochures, informational inserts, industry-specific marketing pieces, and design guidelines addressed to specific market actors;

- Delivery of these materials through trade and professional organizations, design conferences, trade shows, and educational seminars and classes including Energy Design Resources training in integrated design practice, industrial energy efficiency seminars, as well as classes specific to Title 24 and future code requirements;

- Targeted information and supplemental design stipends to architects and engineers to encourage financial analyses including building simulation modeling for decision-maker use;

- Continuation of support for, and outreach efforts through, CHPS, CCC, CASH, AIACC, ASHRAE, and the CEC for meetings, programs, conferences, and activities that promote energy efficiency and integrated design for nonresidential buildings and processes to owners, design and energy professionals, government agencies, and other key market actors;

- Statewide development of Energy Design Resources including energy simulation tools, financial analysis tools, Web-based resources, continued industry standard-practice benchmarking, development and delivery of tools, training, and demonstration projects with media promotion for those efforts;

- Continued development of the SBD and Energy Design Resources Web sites.

Table 1. Statewide Marketing Materials – Annual Amounts

| Marketing Material | Quantity | Method of Distribution | Projected Cost/ Marketing Effort |
| --- | --- | --- | --- |
| Program overview (2 page informational flyer) | 2,000 – 5,000 (2004 quantity/SCE order) | Tradeshows, direct contact, classes, seminars, mail, industry events, conferences | $7,000 - $15,000 |
| Program Brochures, Brochure Inserts | 1,500 – 2,500 (2004 quantity/SCE order) | Direct customer contact and program promotion, classes, seminars, mail, tradeshows, industry events, conferences | $9,000-$22,000 |
| Design Guidelines | 2,000 (2004 quantity/SCE order) | Direct customer contact and program promotion, classes, seminars, | $8,000 |
| Energy Design Resources CD ROM /Printed Volumes | 2,000 – 2,500 (2004 quantity/SCE order) | Direct customer contact and program promotion, classes, seminars, | $28,000 - $35,000 |

Note: Marketing materials for 2005 will be similar in quantity/scope to that outlined above but will require update and reprinting to include mid-cycle Title 24 code adjustments per CEC request, as described in section I. C.

SCE Marketing

In addition to statewide marketing activities, SCE will undertake targeted marketing efforts oriented toward high-potential market sectors or actors including retail, industrial, and institutional customers among others.   Efforts will include, but are not limited to:

- Development and distribution of industry-specific case studies and testimonials relating the value of energy efficiency in terms meaningful to specific market actors;

- Promotion of energy efficiency and integrated design analysis through trade advertising, general and project-specific classes, and stakeholder meetings;

- Expanded outreach to multiple-site retailers (chain stores)

- Promotion of technical and project-specific design assistance to owners, design teams, builders, and contractors;

- Utility-specific promotions through media, one-on-one project outreach, routine calls on industry professionals, as well as through established customer relationships with building and process owners;

- Inclusion of SBD promotional information at SCE’s CTAC and AgTAC classes oriented toward new construction market actors;

- Support of, and marketing through; AIACC, agricultural industry trade and professional organizations, facility managers’ organizations, trade shows, and SCE’s information services program.

Table 2. SCE Marketing Materials

| Marketing Material | Quantity | Method of Distribution | Projected Cost/ Marketing Effort |
| --- | --- | --- | --- |
| Industry-specific case study/testimonials | 6,000 | Direct contact, Mail, website, tradeshows, industry events | $12,000 |
| Advertisement | Annual, full-page outreach to architectural and design professionals | Book of Lists | $15,000 |
| Advertisement/Promotion | 12,000 | SCE’s Power Bulletin and Business Solutions newsletters for nonresidential customers | N/A |
| Promotion | Various | Placement of news stories related to value of new construction energy efficiency with print, television, and electronic media | $30,000 |
| Promotion/Advertising | Various | Targeted marketing outreach using media and one-on-one contacts with Architects / Engineers. | Variable |

Note: Marketing materials for 2005 will be similar in number and in scope to what is outlined above

C.	Customer Enrollment

Savings By Design’s Participant Process:

    - Owners, architects, designers, engineers, contractors, or SBD representatives may initiate contact to begin project participation.

    - Once contact has been made and a qualifying project identified, the building or process owner submits a completed Participation Letter/Letter of Interest (using the appropriate form(s) provided by the utility) indicating their interest in the program.  When applicable, the design team must complete a design team Application during the preliminary or schematic design phase to establish their interest in participating, which will be reviewed and approved by the utility.

    - An SBD representative will work with the participants to determine which program path applies and how to optimize the energy efficiency of the project.

    - After the selection and design of energy efficiency enhancements is finalized, the SBD representative issues an Incentive Agreement to the owner/design team delineating the proposed project details, estimated incentive amounts, and terms and conditions.

    - The owner/design team signs, dates, and returns the Agreement to the SBD Representative.  By signing the Agreement, the owner/design team acknowledges that they have read and agree to all program eligibility requirements.  The utility’s counter-signature and date indicate funds have been reserved for the project for a period of 48 months.  Program funding is on a first-come, first-served basis.

    - If the design team participates in the Whole Building integrated design analysis and life cycle cost reporting component of the program (Whole Building, Track B), on completion of the project analysis and commitment by the owner to the energy efficiency improvements analyzed, the design team is paid 50 percent of the design team incentive along with a $3,500 integrated analysis stipend.

    - As the building is constructed energy efficiency enhancements are included in the project as described in the participant agreement.

    - Once construction is substantially complete, the owner contacts the SBD representative of the project to request an on-site verification.

    - If the project is built as agreed and the project meets all program requirements, the incentive will be paid.  If the completed design differs from that outlined in the Incentive Agreement, the incentive amount will be recalculated, and may be adjusted (up or down) to reflect the revised, estimated building performance.

    - The appropriate incentive amount is provided to the customer and design team in a single payment by check (or the updated, remaining balance of the design team incentive for those design teams participating in Track B).

D.	Materials

Customers are solely responsible for the design, selection, purchase, and ownership of the qualifying equipment, processes, and structures.  Most measures and processes will require contractor installation.  All equipment must be new and must meet the terms of the technical product specifications requirements.  Used or rebuilt equipment is not eligible for incentives.  Measures must be installed and structures constructed according to applicable codes, standards, regulations, and manufacturers instructions.  Quality installation/construction of materials, equipment, and structures is considered to be as critical to efficiency performance as the inherent efficiency of the device or structure itself.

E.	Payment of Incentives

Included in Section II.C, above.

F.	Staff and Subcontractor Responsibilities

SCE Staffing Structure

Manager - Nonresidential Programs

Manager is responsible for the general oversight of all nonresidential Energy Management programs including Savings by Design.

Manager – Program Manager

Program Manger is responsible for all aspects of program oversight and development.  Program oversight includes development and oversight of the budget; schedules; goal setting; deliverables; supervision; communication of program information; tracking and daily operations; policy development; progress achievement of program goals; data systems management; contract and resource management; review of projects for adherence to program guidelines.

Analyst – Program

The Program Analyst (PA) provides necessary data analysis, monitors program activities, budgets, and program tracking.  The PA assists in the preparation of reports and presentations.

Manager – Field Implementation

The Manager is responsible for program implementation and delivery, program development, evaluation of resource tools and case studies, and supervision of the Field Delivery Team. The Manager must ensure: industry relationships are maintained; program offerings are communicated to target markets; the necessary tools and training are available to New Construction Representatives to assist them in offering high level of quality assistance to customers and the attaining of program results; integrity of services and customer satisfaction is kept high; field activity data is recorded into the tracking system; implementation issues are resolved.

Engineer

The Engineer is responsible for reviewing and approving calculations and assumptions used in the analysis of each project accepted into the NRNC program.  They must be able to use DOE 2 based calculation tools, have a full understanding and working knowledge of different commercial, industrial, and agricultural buildings and individual systems.  Engineers also provide support to the New Construction Representatives in working with the building owner or their design team.  Engineers must also manage contracts with third party consultants.  These consultants are used to provide consultative services and energy use and savings reports.

Technical Specialists/New Construction Representatives (NCR)

New Construction Representatives are tasked with the delivery of the NRNC program.  Each representative has experience and the knowledge to guide the customer (building owner, design teams, developers, and others) through the design process to ensure maximum cost-effective energy efficiency measures are integrated into the building design and the system designs.  NCR must also track activities with customer, perform energy analyses using approved calculation tools.  They must be familiar with building designs, able to read and interpret blueprints, and manage several projects at a time.  NCR must have strong relationship building skills.

Administrative Assistance

Administrative and clerical personnel are responsible for supporting nonresidential new construction program operations.

Subcontractors

SCE in the past has utilized the expertise of a third party consultant to assist in marketing and delivery of SBD’s refrigeration component to the nonresidential new construction market.  Refrigerated warehouses, industrial plants, supermarkets, convenience stores, big box retail stores and similar businesses are significant energy users with unique needs.  These customers require attention from highly qualified and knowledgeable industry providers who have deep vertical knowledge of refrigeration technologies and broad contacts and influence within the industries.  This effort will be let through open competitive bid.  SCE is reviewing this effective use of technical expertise and focused promotion of an underserved technology to determine the best use of this resource in 2004 – 05.

As indicated in the previous section, SCE will also use consultants to provide energy evaluations and analysis of customer projects.  And to provide technical support in the form of training, design briefs, development of outreach materials, and other activities.

Subcontractors might be used to supplement NCR activities.

G.	Work Plan and Timeline for Program Implementation

Energy efficiency interventions for nonresidential new construction projects happen over extended periods of time.  To overcome market barriers and issues discussed in section I. B. relating to risk and industry time frames, SBD acts as a pipeline, continuously contacting customers, gaining trust, determining eligibility, analyzing projects, influencing energy efficiency choices, and then feeding projects into the program.  In order to retain customer confidence in the reliability of the pipeline, the 2004-2005 SBD program must be available on January 1, 2004 or immediately upon Commission approval of this proposal if that date occurs after January 1, 2004. The following timetable reflects critical dates in the SBD program cycle:

Timeline for 2004-2005 Program Implementation

| Activity/Event | Target Date |
| --- | --- |
| Program Launch | January 1, 2004 |
| Customer Call Center referral update | January 2, 2004 |
| SBD and EDR statewide website update | January 2, 2004 |
| Product brochures and inserts printed and available for distribution | January 5, 2004 |
| Calculation methodology for 2004 program changes standardized and available | January 5, 2004 |
| 2004 program changes introduced to all internal program stakeholders/promoters | January 5, 2004 |
| International Air Conditioning Heating and Refrigeration (AHR) Expo | January 26-28, 2004 |

| EDR education and outreach trainings at CTAC, AgTAC and, Various Customer and /or Other Sites | Ongoing January, 2004 through December 2005 |
| --- | --- |
| IOU Statewide SBD team meetings | Quarterly or more frequently through December 2005 |
| USGBC and locality-specific environmental events | Ongoing January, 2004 through December 2005 |
| Complete program rollout meetings with internal and external stakeholders throughout SCE service area | February 27, 2004 |
| SBD participation in SCE customer forums | February-May 2004 |
| Final agreement between CEC, IOU’s, stakeholders on format, timelines for 2005 Title 24 informational materials/classes | May 31, 2004 |
| Inter-utility agreement on time table/methods for integration of additional CEC requested program modifications | June 30, 2004 |
| AIACC-SBD Energy Integration Design Awards | July 2004 |
| Staged introduction and presentation 2005 Title 24 informational materials/classes | August 15, 2004 through December 2005 |
| American Council for an Energy Efficient Economy (ACEEE) Comm’l. Conference | August 22-27, 2004 |

| Calculations and documentation for 2005 Title 24 code impacts complete | October 31, 2004 |
| --- | --- |
| Final Utility-CEC discussion and agreement for 2nd round program upgrades to reflect Title 24 code change | November 15, 2004 |
| 2005 Title 24 code-based energy analysis calculation engine modifications complete for 2005 rollout | December 15, 2004 |
| Introduction of additional SBD program changes in anticipation of code change | January 3, 2005 |
| Customer Call Center referral updates | January 3, 2005 |
| SBD and EDR statewide website update | January 3, 2005 |
| Product brochures and inserts printed and available for distribution | January 3, 2005 |
| Calculation methodology for 2005 program upgrade standardized and available | January 3, 2005 |
| Program changes introduced to all internal program stakeholders/promoters | January 15, 2005 |
| Complete program update meetings with internal and external stakeholders throughout SCE service area | March 1, 2005 |
| SBD Participation in SCE customer forums | February-May 2005 |
| ACEEE – Industrial Conference | August 2005 |

## III.	Customer Description

A.	Customer Description

Participants in the SBD program span the spectrum of nonresidential occupancies and processes. They can include all commercial, industrial, and agricultural owners as well as their support teams of designers, developers, contractors, and energy professionals. In each market segment and geographical area, participants range from very small to extremely large. Throughout these market sectors and areas, owners and support teams share certain needs while having others that are unique to industry, market sector, or size.

B.	Customer Eligibility

To be eligible for SBD, projects must be:

- Located in the service area of a participating utility and subject to payment of the Public Goods Charge (PGC) for electric service and/or the Gas Surcharge for natural gas service as administered by the Commission;

- A project in the commercial, industrial, or agricultural market segment, and either:

- A new construction, addition, or expansion project, or

- A major renovation/remodel project, which involves building system redesign, load increase, or change of occupancy.

- At a point where design changes are feasible, preferably in the programming or schematic design phase.

- Meet minimum SBD program requirements.

To be eligible for Savings By Design participants must:

- Complete and return a “Participation Letter/Letter of Interest” to indicate the owner’s interest in the program;

- Complete a “Design Team Incentive Application” to indicate a design team’s interest to participate and to establish a design team leader for eligible Whole Building projects;

- Be willing to consider energy efficiency recommendations, which will improve building or system performance significantly beyond Title 24 (or other reference baseline) requirements;

- Provide all required documentation, including, but not limited to: selected construction documents, Title-24 documentation, integrated design analysis reports, manufacturer specifications, equipment cut sheets, and incremental cost verification, as requested;

- Sign the appropriate completed “Savings By Design Incentive Agreement(s)” prior to installing the selected energy efficient options;

- Agree to allow access to the completed facility for on-site verification and, if selected, participate in measurement and evaluation studies; and

- Agree that they will not apply for or receive any other incentive, rebates, or financing supplied using Commission Public Goods Charge funds for measures covered under SBD whether offered by vendors, local or state entities, or another utility.

C.	Customer Complaint Resolution

If a customer has a question, concern or dispute related to program policies, rules, or procedures, a program office representative will evaluate the issue and seek to resolve the dispute consistent with program rules, policies, and procedures.  If a customer has a dispute related to work performed by a licensed contractor, SCE will refer the customer to the Contractor State Licensing Board. If the customer has a dispute related to a non-licensed contractor, SCE will recommend that the customer work directly with the contractor to resolve the dispute.

D.	Geographic Area

The SBD program is available throughout the service areas of PG&E, SCE, SDG&E, and SoCal Gas with a special equity emphasis on hard to reach customer segments including those geographic areas that are transmission-constrained as identified by the California Independent System Operator (ISO) in its April 11, 2003 Summer Assessment.  It is intended that the reduction in peak demand resulting from this program will assist in the mitigation of forecasted reliability concerns within the geographic areas served by the transmission-constrained paths described in the SCE portion of the ISO Summer Assessment report.

###### PG&E

###### SCE

###### SDG&E

SoCal

Gas

Figure 1. 	Savings By Design - Area Served

The SBD program is targeted to reduce peak demand in all geographic areas of SCE's service territory, including those areas that are transmission-constrained as identified by the California Independent System Operator (ISO) in its April 11, 2003 Summer Assessment.  It is intended that the reduction in peak demand resulting from this program will assist in the mitigation of forecasted reliability concerns within the geographic areas served by the transmission-constrained paths described in the SCE portion of the ISO Summer Assessment report.

## IV.	Measure and Activity Descriptions

- Energy Savings Assumptions

Savings by design energy savings estimates are based upon historic results from this continuing program, accounting for changes in program design and budget amount.  Measures shown in the matrix are grouped by measure end-use.  For more detailed measure information refer to the Proposal workbook.

- Deviations in Standard Cost-effectiveness Values

The program utilizes the current CPUC Energy Efficiency Policy Manual for its cost-effectiveness inputs.  Incremental measure costs (IMC) are based upon historic costs estimated from this continuing program.  Since energy savings and incremental measure costs are based upon kWh as the unit of measure for the program, there is no applicable IMC from the CEC DEER database.

- Rebate Amounts

The Savings By Design Program offers two incentive approaches.  Each approach has its own incentive calculation method.

Under the Whole Building Approach, the overall efficiency of the building is evaluated using a computer simulation analysis. If the building is at least 10% better than the baseline, then incentives are available. The maximum incentive is $150,000 per free-standing building or individual meter.

The incentive rate for the Owner Incentives will vary depending on the percentage reduction below Title 24 or the applied base case.  Rates range from $0.06 to $0.18 per kWh savings.

(source: www.savingsbydesign.com)

The program also offers the System Approach.  A fixed rate of incentive is established for various systems.  The incentive is determined by multiplying the fixed incentive rate by the accepted kWh savings.

| System | Incentive Rate |
| --- | --- |
| Daylighting | $0.04 per annualized kWh savings |
| Lighting Power Density (Interior Lighting Systems) | $0.06 per annualized kWh savings |
| Heating, Ventilation, and Air Conditioning Systems | $0.12 per annualized kWh savings |
| Refrigeration Systems | $0.06 per annualized kWh savings |
| Other Systems | $0.10 per annualized kWh savings |
| Service Water Heater Systems | $0.34 per annualized therm savings |

D.	Activities Description

Education, information, and outreach efforts are necessary to the successful delivery of the SBD program.  While the portion of budget dedicated to this purpose is delineated at varying levels within the budget tables depending on the IOU, tracking and reporting for these activities will follow the same statewide procedure.  SBD will track and report:

- Online courses completed at the Energy Design Resources’ Web site, with the goal of increasing completions by at least 100 percent over 2003 results; and

- Custom project outreach efforts including design assistance, design charettes, on-site seminars, and project-specific integrated design training with the goal of maintaining 2003 training levels despite reduced budget allocation for 2004-2005 (when compared to 2003 on an annualized basis).

## V.		Goals

Energy Savings and Peak Demand Reduction

Nonresidential New Construction - Savings By Design

| Goals | Peak Demand Reduction (Net kW) | Annualized Energy Savings (Net kWh) |
| --- | --- | --- |
| 2004 | 8,788 | 44,021,353 |
| 2005 | 8,788 | 44,021,353 |
| Total | 17,557 | 88,042,706 |

SCE will expand its outreach efforts to hare-to-reach customers.  The program will enhance services offered through local government Building Code/Plan Check departments to capture small business customers’ (< 20 kW) new construction or major renovation/remodel projects.

## VI.	Program Evaluation, Measurement and Verification (EM&V)

A.  General Approach to Evaluating Program Success

This statewide EM&V plan is based on the Commission’s objectives as outlined in the Energy Efficiency Policy Manual (EE Policy Manual) and adheres to the guidelines in the International Performance Measurement and Verification Protocol (IPMVP).  This plan will continue to use the existing EE Policy Manual and established EM&V methods while the EM&V Protocols and Framework are being completed.  At such time, a detailed EM&V plan will defer to the EM&V Protocols and framework as appropriate to evaluate the program’s success.

The EM&V activities will be carried out in two studies:  the Building Efficiency Assessment Study (BEA) and the Market Characterization and Program Activity Tracking Project (MCPAT).

The 2004-2005 BEA study will build on the Nonresidential New Construction (NRNC) Building Efficiency Assessment (BEA) Studies from PY 2000 to PY 2002, and it will use a similar reporting format.  (2003 plans have been submitted for continuation of this study.)  This ongoing study has assessed the energy efficiency of Savings By Design (SBD) program participants and non-participants since the program’s inception in 1999.

The primary focus of this study in evaluating the program’s success will be to provide measured results in the form of levels of energy and peak demand savings achieved by the program.  The success of the program is also gauged by an on-going process evaluation that assesses market actor attitudes and design practices and assesses participant satisfaction.

The MCPAT study will build on the previous work performed by the past MCPAT and Savings By Design studies.  The MCPAT study has collected and reported data on nonresidential new construction market activity and Savings By Design (SBD) program activity in 2000, 2001 and 2002.  This on-going project provides bi-annual reports of statewide NRNC market and program activity.  Savings By Design program tracking information is available from the IOU partners implementing the program.  Program and market characteristics, by building type, are reported at the utility level, the county level and the statewide level.  These data are tracked on an on-going basis and developed into standardized reports to allow for assessment of the NRNC market over time.

The two main purposes of this study are to provide information for refining program design and for assessing program accomplishments.  The study is important because evaluation of energy efficiency initiatives requires knowledge of baseline market conditions and changes relative to that specific baseline over time.  The value of this activity will increase over time as time-series data accumulate.

The results provide timely feedback to program managers and policymakers and facilitate incremental improvements to program process and operations.  The results also help identify changes in design practices as a result of program operation.

B.  Approach to Measuring and Verifying Energy and Peak Demand Savings

In regards to the EM&V activities for the BEA study, this on-going study quantifies the whole-building and end-use energy savings and efficiencies of both participant and non-participant buildings.  The approach to developing these data has been used for evaluating statewide commercial new construction since 1999 and the results can be referenced back to previous data to develop time-series trends.  The study calculates savings by the end-use of systems improvements, as well as by whole building integrated design.  The information developed helps assess the success of NRNC program designs and implementation activities.

The 2004/5 BEA Study will produce gross and net program impacts.  The net-to-gross analysis will attempt to estimate the portion of the savings that can be directly credited to the program.  The results of the gross and net analysis will be discussed in an interim report.  The report will describe the analysis methodologies and summarize the results.  An annual report will be prepared that combines the various interim reports and other intermediate deliverables required in the Study, incorporating reviewers’ comments on the earlier reports, and rewriting as necessary to provide continuity and final conclusions.  For continuity, the final report will have the same structure as the PY2000-2002 reports.

The MCPAT study provides information on the full market of new construction projects.  These data are used by the BEA study to contact and assess representative samples of projects that do not participate in the Savings By Design program.

C.  Approach to Evaluating Program Success

The BEA project tracks program participant attitudes and responses to the program, including information on program design, the application process, the design assistance services provided by the programs, the timing of program events relative to project events, etc.

The study approach will be consistent with the BEA 2000-2002 approach, with modifications made as necessary to further investigate results and trends. Specifically, the study will include the following steps:

    - Conduct in-depth decision-maker interviews to assess program acceptance, and participant attitudes towards energy efficiency and to solicit feedback on program design.

    - Develop quantifiable information on the changes in building efficiency attributable to the Savings By Design program influences.  Information about the new Title 24 requirements should also be developed for a similar population of non-participating buildings.

    - Investigate trends in energy savings, characteristics and/or decision-maker attitudes.

The MCPAT study will continue to provide information for the following two areas:

NRNC market characteristics: construction value and volume, types of buildings, design team characteristics, etc.

This information is needed so that NRNC market activities can adapt and prioritize their efforts to meet the needs of the different segments. Data will be collected describing the construction value and volume of the NRNC market, types of buildings, sizes of buildings, types of owners, and design team characteristics. The characteristics of the NRNC market including the actions and changes that occur over time will be tracked.

NRNC Savings By Design (SBD) program activity tracking and penetration in the NRNC market.

Data collected will include the number of program participants, type of participants, number of projects signed up for the program, type and size of projects, type of measures installed, and geographic locations. This information is drawn from each of the Partner utilities’ internal tracking systems.  Similar to the activities conducted in PY2000-2002, the data will be integrated to support statewide and cross-utility analyses.

Using the SBD program activity data and the NRNC market characterization data, semi-annual SBD Program Tracking and Penetration Analysis Reports are prepared.  The reports will categorize and analyze the SBD program activity according to number of participants in the program, number of projects signed up for the program, type and size of projects, and energy savings.  The reports will analyze the relative penetration of the SBD program activities in the different NRNC market segments and service territories.  The reports will also document trends over time, as the Program extends its activity in the NRNC market.  Program penetration will be calculated as the fraction of total NRNC projects that participated in the SBD program.

D.  Potential EM&V Contractors

The contractors listed below can objectively and effectively evaluate program success.  As a group, their work includes impact evaluation, measurement and verification, process evaluation, market assessments, and verification of program accomplishments.  These firms have a track record of completing high quality, objective studies of energy efficiency programs either for the California investor-owned utilities or for other entities whose studies we have been able to review.  This list does not include all of the qualified evaluators who could objectively evaluate program success.  The final list of evaluation consultants will be based on several factors including future Commission decisions, the mix of approved programs and the experience of the evaluation consultants.

| ADM Associates | KVDR Consulting |
| --- | --- |
| Aloha Systems | Megdal & Associates |
| Alternative Energy Systems Consulting (AESC) | Nexant |
| Applied Management Sciences Group? | Opinion Dynamics |
| Architectural Energy Corporation (AEC) | Quantec LLC |
| ASW Engineering Management | Quantum Consulting |
| Aspen Systems Corporation | Ridge and Associates |
| EcoNorthwest | PA Consulting Group |
| Energy & Environmental Economics | Research Into Action |
| Energy Market Innovations | RLW Analytics |
| Equipoise Consulting | Robert Mowris & Associates |
| Freeman Sullivan & Co. | SBW Engineering |
| Frontier Associates | Science Applications International Corp. (SAIC) |
| GDS Associates | Skumatz Economic Research Associates (SERA) |
| Global Energy Partners | Summit Blue Consulting |
| Heschong-Mahone Group | TecMRKT Works |
| ICF Consulting | Vanward Consulting |
| Itron (RER) | Wirtshafter Associates |
| KEMA-Xenergy, Inc |  |

SBD will also undertake discussions with the CEC, the Commission, and CALMAC regarding the application and update of measurement and evaluation procedures, energy and peak demand calculation procedures, as well as the applicability to the current program of certain new construction definitions, specifically, free-ridership, and spillover.  SBD will seek to apply the results of these discussions to the 2004-2005 SBD program.

## VII.	Qualifications

A.	Primary Implementer

SCE is responsible for managing and implementing the statewide Savings By Design program within SCE’s service territory.  As a whole, SCE is uniquely qualified to provide the core of statewide and local programs that form a solid and reliable foundation of energy savings opportunities that our customers and the State can rely upon.  Over the years, SCE has developed energy efficiency experience, expertise and a support infrastructure that is second to none.  Moreover, our long-term commitment to and credibility with our customers are critical to widespread acceptance of energy efficiency information and recommendations for action.  Finally, SCE provides ironclad accountability to our regulators and the customers we’ve served for over a century that is invaluable to ensuring that public money is appropriately spent.

SCE’s experience in energy efficiency is a century long.  We began assisting customers is the wise use of energy in the early 1900s, when we first began helping our agricultural customers to test the efficiency of their electric pumps.  Beginning in the 1980’s, the energy efficiency programs designed by SCE have been nationally recognized and have helped California assume a leadership role in energy efficiency.  Continuing this tradition of excellence in energy efficiency, SCE’s 2004 - 2005 portfolio of statewide and local programs incorporates innovation into our proven track record of program success in all program areas:

Residential - SCE’s participation in the delivery of residential programs began in the early 1980s, when we began offering comprehensive audits that linked information collected in customer homes by certified energy service representatives to actual billing histories.  Through this unique service, customers received immediate audit results that directed them to rebate programs available for recommended energy-saving measure and device retrofits.  Conservation information materials were also made available to customers for the first time. Today, SCE continues this two-decade tradition through a similar close combination of residential information, energy survey, and rebate services, but updated to reflect today’s technological advances. With a staff comprised of energy efficiency experts with professional experience in other business fields, SCE has designed modern programs that offer a variety of energy efficiency tools on-line, including information, energy use calculator/estimators and an energy survey that provides instantaneous recommendations based on each participating customer’s energy use.  Strong business relationships between SCE and major retailers now enable SCE to pay incentives directly to a customer through several delivery mechanisms: as the result of an application process, at the cash register, or as part of price buy downs at the manufacturer level.  Staff with marketing knowledge develops strategies that call out the best and most efficient method of reaching the right customer group with the program mix that best matches their needs.

Nonresidential - Southern California Edison has provided nonresidential customers with energy efficiency programs under the direction of the Commission since 1976.  Early programs provided information to customers on how to use energy more efficiently through improved operations and maintenance practices.   Since that time, SCE’s programs have evolved, expanded, and diversified into a comprehensive mixture of information and incentive programs.  SCE is a national leader in the development and operation of performance-based energy efficiency incentive programs including DSM Bidding and Standard Performance Contract Programs.  Our programs have grown and contracted, shifted focus and emphasis, or completely changed philosophy as needed to incorporate the changing goals of the Commission, the needs of the marketplace and input of the many stakeholders in the energy efficiency industry.  Most important, SCE’s customers have grown to trust the utility as the single, unbiased source of energy efficiency information, services and programs.  No matter what else was happening to affect customer opinion of the utility industry, our business customers continued to look to SCE for assistance in managing their energy use and costs.

New Construction – For over 20 years, Southern California Edison has designed and operated programs aimed at improving the energy efficiency of new buildings, both residential and nonresidential.  Whether through financial incentives, technology showcases, builder and consumer education, or assistance to design professionals, SCE programs have effected significant, permanent improvements in the energy efficiency of new buildings in its service territory.  Since the early 1990s, builders participating in SCE’s residential programs have built over 50,000 homes that exceeded state building standards.  For nonresidential new construction, SCE has refined and enhanced a wide array of educational and design assistance tools, including free state-of-the-art online technical assistance, for the commercial building industry.  We have a well-respected group of design professionals on our staff including architects and engineers, and we have established alliances throughout the design and construction industry with organizations such as AIA, ASHRAE, IES, AEE, IEEE, CEE.

The program design and implementation team who plan, administer, deliver and support our programs provides unparalleled expertise in energy efficiency programs.  Our program managers have an average of ten years of experience in energy efficiency and related customer service activities and are supported by a veteran staff of technical experts in all facets of energy efficiency.  Our design and technical support staff have over 300 years of combined experience, over two-thirds are licensed by state or federal organizations, and over half have advanced degrees.  Our program design and evaluation staffs also have extensive first-hand knowledge of the customer demographics unique to SCE’s service territory.  After all, for over 100 years we’ve lived and worked with the customers we serve.

Finally, as a utility who serves all of the energy needs of all of our customers, SCE also has an existing infrastructure of support functions (such as accounting, regulatory and legal departments), systems (such as our program tracking and reporting systems) and facilities (such as our energy centers) that we use to facilitate the successful implementation of our programs.  Further, our long-term relationship with the Commission and the customers we serve further ensures that our customers will be well served and protected.  Using the experience and resources described above, SCE stands ready to satisfy our customers’ energy efficiency needs and meet the Commission’s policy objectives.

B.	Subcontractors

Subcontractors to be determined by an open bid process

C.	Resumes or Description of Service

David Bruder, Lead IOU Project Manager

Mr. Bruder is a registered mechanical engineer with over 22 years of experience in energy efficiency program management, facility design and construction.  As a project engineer for a major engineering and construction firm, David led and coordinated multi-discipline teams of engineers and architects in the design of large, complex industrial facilities.  At Southern California Edison, David oversees all aspects of a portfolio of non-residential energy efficiency programs, including DSM Bidding, Standard Performance Contracts, and Express Efficiency.  His responsibilities include design and implementation of programs, as well as managing cost and schedule, and tracking and reporting program status to management and the CPUC.

Janith Johnson, Nonresidential New Construction Programs, Manager

Janith Johnson brings over 13 years of experience in energy efficiency program development, analysis, and implementation to the Savings By Design delivery team. As a licensed architect committed to making the design of high performance buildings standard practice, she brings an understanding of the design and construction industry to the utility to advance this goal. For the last seven years, Janith has led SCE’s successful Savings By Design implementation team and has had a primary role in the development and direction of the Energy Design Resources program. As technical support for previous new construction programs, she managed nearly 100 building-specific studies for customer facilities, providing her an in-depth understanding of interactive energy use in buildings.  Janith has demonstrated her ability to educate professionals by conducting training in the areas of daylighting and glazing for a large variety of industry organizations, presenting numerous technical papers at industry conferences, and teaching architecture courses at the community college level. Additionally, Janith has provided service to the design profession by holding offices in the American Institute of Architects, Inland California chapter, including president and chair of the chapter Committee on the Environment.

## VIII.	Budget

*In addition to the program budget proposed above, SCE proposes $10.4 million annually for a similar program as part of its 2004-5 procurement plans.

Estimates from internal PG&E analysis of participating industrial projects, performed in August 2003, indicates that SBD’s 2002 industrial incentives generally cover an average of only 8-12% of incremental measure cost

NRNC Market Characterization and Program Tracking (MCPAT) Report PY2002, Quantum Consulting, August 2003